## Sheet1
Código | Código Secundário | Título | Disciplina | Revisão | Versão | Nome do Projeto | Diretório | Formato Documento | A1 EQ | Status Documento | Inicio Fluxo | Fim Fluxo | Responsável da Atividade | Status Emissão | Avanço Físico % | Data Planejada | Nome do Arquivo | Tamanho do Arquivo | Data de Importação | Folhas | Data da Última Emissão | Revisão Última Emissão | Finalidade Última Emissão | Data Recebimento Markup | Revisão Recebimento Markup | Tipo Markup | Data Planejada Último Markup | Data Recebimento As Built | Data Atendimento As Built | Controle de Cópias | Finalidade Próxima Emissão | 01-Plan_Ifr | 02-Plan_Ifa | 03-Plan_Afc | 04-Tr Received | 05-Tr Rev. | 06-Tr Date | 07-Issued Assai | 08-Assai Date | 09-Recvd Assai | 10-Recvd Date | 11-Code | 12-Tr Issued | 13-Issued Date | 00-Ivb Required | 00-Ivb Priority
11413-PVN-DAE-BONGA-00004 |  | PROJECT VARIANCE NOTIFICATION (PVN) FORM-0004: OVERDUE DELIVERABLES NOTICE | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | 11413-PVN-DAE-BONGA-00004_A01.PDF | 752,04 KB | 29/04/2025 05:12:06 | [11 empty] | IFI - ISSUED FOR INFORMATION
11413-PVN-DAE-BONGA-00006 |  | SPECIALIST POWER SYSTEM STUDIES VENDOR | NÃO SE APLICA | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | 11413-PVN-DAE-BONGA-00006_A01.PDF | 561,98 KB | 08/05/2025 03:51:45 | [11 empty] | IFI - ISSUED FOR INFORMATION
11413-PVN-DAE-BONGA-0001 |  | PROJECT VARIANCE NOTIFICATION (PVN) FORM | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/07/2025 | 11413-PVN-DAE-BONGA-0001=A01.PDF | 1,54 MB | 09/07/2025 05:53:48 | [23 empty] | BNO-MABU-DAE-2025-TN-10089 | 07/09/2025
BNO-MABU-300-AA-0780-10001 |  | LNTP CLOSE-OUT REPORT | AA - PROJECT MANAGEMENT | A02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT | A4 | 0 | CANCELADO |  |  |  |  | 50 | 26/03/2025 | BNO-MABU-300-AA-0780-10001_A02.DOCX | 4,98 MB | 27/03/2025 08:49:18 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00017 | A02 | 03/12/2025
BNO-MABU-300-AA-5760-10001 |  | PROJECT EXECUTION PLAN | AA - PROJECT MANAGEMENT | A02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 19/07/2025 |  | RICARDO.SANTOS |  | 85 | 31/07/2025 | BNO-MABU-300-AA-5760-10001_A02.DOCX | 4,7 MB | 19/07/2025 05:45:30 |  | 23/04/2025 06:16:00 | A01 | IFR - ISSUED FOR REVIEW | 21/05/2025 05:38:51 | A01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  |  |  | BON-DAE-WESTPAQ-2025-TX-00379 | A02 | 07/18/2025 | BNO/MABU-SNEPCO-2025-INC-00422 | 07/19/2025
BNO-MABU-300-AA-5787-10001 |  | DATA SUBMISSION SCHEDULE | AA - PROJECT MANAGEMENT | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT | A4 | 0 | NÃO SE APLICA | 14/03/2025 |  |  |  | 0 | 09/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 05/09/2025 | 6/27/2025 | 07/11/2025 | [10 empty] | NR | NA
BNO-MABU-300-AA-5787-10002 |  | LEVEL 3 PROJECT SCHEDULE | AA - PROJECT MANAGEMENT | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT | A4 | 0 | ENG_IFR CONSOLIDATION | 10/04/2025 |  | PEDRO.FERREIRA | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 24/03/2025 | BNO-MABU-300-AA-5787-10002_R01.PDF | 1,94 MB | 10/04/2025 03:02:46 |  |  |  |  | 05/05/2025 05:37:49 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 3/24/2025 | 05/12/2025 | 5/26/2025 | BON-DAE-WESTPAQ-2025-TX-00061 | R01 | 04/09/2025 | BNO-MABU-SNEPCO-2025-INC-00146 | 04/10/2025 | BNO/EXT/MABU/00532 | 05/05/2025 | 4 | BNO-MABU-DAE-2025-TN-10040 | 05/07/2025 | NR | NA
BNO-MABU-300-AA-5800-10001 |  | INTERFACE MANAGEMENT PLAN | AA - PROJECT MANAGEMENT | A02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 19/07/2025 |  | RICARDO.SANTOS |  | 50 | 31/07/2025 | BNO-MABU-300-AA-5800-10001_A02.DOCX | 1,57 MB | 19/07/2025 05:50:10 |  | 21/05/2025 03:55:49 | R01 | IFR - ISSUED FOR REVIEW | 02/07/2025 06:07:28 | A01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  |  |  | BON-DAE-WESTPAQ-2025-TX-00379 | A02 | 07/18/2025 | BNO/MABU-SNEPCO-2025-INC-00422 | 07/19/2025 | [5 empty] | NR | NA
BNO-MABU-300-AA-6180-10001 |  | PROJECT ENGINEERING MANUAL | AA - PROJECT MANAGEMENT | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT | A4 | 0 | NÃO SE APLICA | 14/03/2025 |  |  |  | 0 | 02/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/02/2025 | 7/14/2025 | 7/28/2025 | [10 empty] | NR | NA
BNO-MABU-300-AA-6619-10001 |  | MONTHLY RISK/ OPPORTUNITY REGISTER | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT | A4 | 0 | ENG_IFR CONSOLIDATION | 28/03/2025 |  | PEDRO.FERREIRA | ISSUED AS CODE 2 - NO COMMENTS | 10 | 09/04/2025 | BNO-MABU-300-AA-6619-10001_A01.XLSX | 218,66 KB | 28/03/2025 02:35:13 |  |  |  |  | 24/06/2025 05:21:57 | A01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00046 | A01 | 3/26/2025 | BNO-MABU-SNEPCO-2025-INC-00123 | 3/28/2025 | BNO_EXT_MABU_00633 | 06/24/2025 | CODE 2 - NO COMMENTS |  |  | NR | NA
BNO-MABU-300-AA-6619-10002 |  | MONTHLY RISKOPPORTUNITY REGISTER | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 09/07/2025 |  | EDSON.SIQUEIRA |  | 50 | 09/07/2025 | BNO-MABU-300-AA-6619-10002=A01.DOCX | 1,02 MB | 09/07/2025 03:40:45 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00324 | A01 | 07/09/2025
BNO-MABU-300-AA-6945-10001 |  | DED CLOSE-OUT REPORT | AA - PROJECT MANAGEMENT | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/10/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 10/10/2025 | 11/05/2025 | 11/28/2025 | [10 empty] | NR | NA
BNO-MABU-300-AA-7180-10001 |  | SITE VISIT PLAN AND CHECKLIST | AA - PROJECT MANAGEMENT | A02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 19/07/2025 |  | RICARDO.SANTOS |  | 85 | 31/07/2025 | BNO-MABU-300-AA-7180-10001_A02.DOCX | 1,31 MB | 19/07/2025 05:52:17 |  | 07/04/2025 09:27:29 | A01 | IFA - ISSUED FOR APPROVAL | 21/06/2025 05:05:18 | A01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  |  |  | BON-DAE-WESTPAQ-2025-TX-00379 | A02 | 07/18/2025 | BNO/MABU-SNEPCO-2025-INC-00422 | 07/19/2025 |  |  |  |  | 4/23/2025
BNO-MABU-300-AA-7180-10002 |  | SITE VISIT REPORT | AA - PROJECT MANAGEMENT | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT | A4 | 0 | ENG_IFR CONSOLIDATION | 27/05/2025 |  | A.AGBOGUN | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 10/06/2025 | BNO-MABU-300-AA-7180-10002_R01.DOCX | 149,2 MB | 27/05/2025 08:55:58 |  | 27/05/2025 10:37:52 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:15:15 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00153 | R01 | 05/27/2025 | BNO-MABU-SNEPCO-2025-INC-00237 | 5/27/2025 | BNO_EXT_MABU_00600 | 06/16/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-AA-7180-10011 |  | WEEKLY PROGRESS REPORT DED WEEK 11 | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A4 | 0 | CANCELADO |  |  |  |  | 0 | 21/04/2025 | BNO-MABU-300-AA-7180-10011_A01.DOCX | 15,16 MB | 08/04/2025 01:24:49 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00058 | A01 | 04/07/2025
BNO-MABU-300-AA-7180-10012 |  | WEEKLY PROGRESS REPORT DED WEEK 12 | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A0 | 0 | CANCELADO |  |  |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 0 | 28/04/2025 | BNO-MABU-300-AA-7180-10012_A01.DOCX | 14,88 MB | 14/04/2025 04:51:40 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00068 | A01 | 4/14/2025
BNO-MABU-300-AA-7180-10013 |  | WEEKLY PROGRESS REPORT - DED - WEEK 13 | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A4 | 0 | CANCELADO |  |  |  |  | 0 | 08/05/2025 | BNO-MABU-300-AA-7180-10013_A01.PDF | 1,34 MB | 23/04/2025 05:04:04 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00076 | A01 | 4/23/2025
BNO-MABU-300-AA-7180-10014 |  | WEEKLY PROGRESS REPORT DED WEEK 14 | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | BNO-MABU-300-AA-7180-10014_A01.PDF | 2,1 MB | 28/04/2025 08:11:05 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00080 | A01 | 4/28/2025
BNO-MABU-300-AA-7180-10015 |  | WEEKLY PROGRESS REPORT DED - WEEK 15 | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | BNO-MABU-300-AA-7180-10015_A01.PDF | 1,95 MB | 05/05/2025 03:48:26 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00092 | A01 | 05/02/2025
BNO-MABU-300-AA-7180-10016 |  | WEEKLY PROGRESS REPORT - DED - WEEK 16 | NÃO SE APLICA | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | BNO-MABU-300-AA-7180-10016_A01.DOCX | 1,16 MB | 12/05/2025 01:59:29 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00100 | A01 | 05/09/2025
BNO-MABU-300-AA-7180-10017 |  | WEEKLY PROGRESS REPORT_DED_WEEK 17 | NÃO SE APLICA | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 02/06/2025 | BNO-MABU-300-AA-7180-10017=A01.PDF | 1,86 MB | 19/05/2025 09:11:49
BNO-MABU-300-AA-7180-10018 |  | DED WEEKLY PROGRESS REPORT #018 FOR WEEK 19TH MAY TO 23RD MAY 2025 | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/06/2025 | BNO-MABU-300-AA-7180-10018=A01.DOCX | 10,54 MB | 26/05/2025 08:47:05
BNO-MABU-300-AA-7180-10019 |  | WEEKLY PROGRESS REPORT - DED - WEEK 19 | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | BNO-MABU-300-AA-7180-10019=A01.DOCX | 1,61 MB | 03/06/2025 03:59:46 | [15 empty] | BON-DAE-WESTPAQ-2025-TX-00183 | A01 | 06/03/2025
BNO-MABU-300-AA-7180-10020 |  | DED WEEKLY PROGRESS REPORT # 20 | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | BNO-MABU-300-AA-7180-10020_A01.PDF | 3,07 MB | 11/06/2025 02:11:53
BNO-MABU-300-AA-7180-10021 |  | WEEKLY PROGRESS REPORT #21 FOR W/E 16-06-2025 | NÃO SE APLICA | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | BNO-MABU-300-AA-7180-10021=A01.DOCX | 2,55 MB | 17/06/2025 16:18:41
BNO-MABU-300-AA-7180-10022 |  | DED WEEKLY PROGRESS REPORT FOR WEEK 22 | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | BNO-MABU-300-AA-7180-10022=A01.DOCX | 1,91 MB | 07/07/2025 06:47:44 | [15 empty] | BON-DAE-WESTPAQ-2025-TX-00250 | A01 | 06/23/2025
BNO-MABU-300-AA-7180-10023 |  | DED WEEKLY PROGRESS REPORT #23 FOR WEEK ENDING 27-JUNE-2025 | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | BNO-MABU-300-AA-7180-10023=A01.DOCX | 1,78 MB | 30/06/2025 08:02:01 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00279 | A01_IFI | 06/30/2025 | N/A |  |  |  |  | BNO-MABU-DAE-2025-TN-10088 | 07/04/2025
BNO-MABU-300-AA-7180-10024 |  | DED WEEKLY PROGRESS REPORT FOR WE 4-07-2025 | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | BNO-MABU-300-AA-7180-10024=A01.DOCX | 1,67 MB | 07/07/2025 06:31:04 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00316 | A01 | 07/07/2025 | N/A
BNO-MABU-300-AA-7180-10025 |  | WEEKLY PROGRESS REPORT - DED - WEEK 25 | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | BNO-MABU-300-AA-7180-10025=A01.DOCX | 1,73 MB | 15/07/2025 02:41:45 | [15 empty] | BON-DAE-WESTPAQ-2025-TX-00367 | A01 | 07/14/2025
BNO-MABU-300-AA-7180-10026 |  | DED WEEKLY PROGRESS REPORT#26 | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | BNO-MABU-300-AA-7180-10026=A01.DOCX | 4,5 MB | 22/07/2025 03:26:32 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00396 | A01 | 07/22/2025
BNO-MABU-300-AA-7180-10027 |  | DED WEEKLY PROGRESS REPORT #27 FOR WEEK ENDED 25-JULY-2025 | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.003-REPORTS | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | BNO-MABU-300-AA-7180-10027=A01.DOCX | 8,68 MB | 29/07/2025 02:10:06 | [11 empty] | IFI - ISSUED FOR INFORMATION
BNO-MABU-300-AA-7403-10001 |  | MULTIDISCIPLINE DESIGN REVIEW TERMS OF REFERENCE | AA - PROJECT MANAGEMENT | A02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT | A4 | 0 | ENG_IFR CONSOLIDATION | 13/06/2025 |  | GABRIEL.SILVA | ISSUED AS CODE 2 - NO COMMENTS | 50 | 27/06/2025 | BNO-MABU-300-AA-7403-10001_A02.DOCX | 2,13 MB | 13/06/2025 01:57:08 |  | 30/05/2025 06:32:52 | A01 | IFA - ISSUED FOR APPROVAL | 23/06/2025 10:12:02 | A02 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00202 | A02 | 06/13/2025 | BNO-MABU-SNEPCO-2025-INC-00277 | 06/13/2025 | BNO/EXT/MABU/00618 | 6/19/2025 | CODE 2 - NO COMMENTS |  |  | NR | NA
BNO-MABU-300-AA-7403-10002 |  | MULTIDISCIPLINARY DESIGN REVIEW REPORT | AA - PROJECT MANAGEMENT | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 30/06/2025 |  | EDSON.SIQUEIRA |  | 50 | 11/07/2025 | BNO-MABU-300-AA-7403-10002_R01.DOCX | 6,7 MB | 30/06/2025 03:24:05 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BNO-MABU-SNEPCO-2025-INC-00294 | R01 | 06/30/2025 | BNO-MABU-SNEPCO-2025-INC-00356 | 06/30/2025 | BNO/EXT/MABU/00700 | 07/22/2025 | OVERDUE |  |  | NR | NA
BNO-MABU-300-AA-7704-10001 |  | PROJECT BASIS OF DESIGN | AA - PROJECT MANAGEMENT | A02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.01-AA-PROJECT MANAGEMENT | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 19/07/2025 |  | RICARDO.SANTOS |  | 50 | 31/07/2025 | BNO-MABU-300-AA-7704-10001_A02.DOCX | 4,05 MB | 19/07/2025 06:00:07 |  | 09/04/2025 09:34:15 | A01 | IFA - ISSUED FOR APPROVAL | 21/06/2025 05:05:20 | A01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  |  |  | BON-DAE-WESTPAQ-2025-TX-00379 | A02 | 07/18/2025 | BNO/MABU-SNEPCO-2025-INC-00422 | 07/19/2025
BNO-MABU-300-AA-8502-10002 |  | REVIEW OF 2D-3D TEMPLATES | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A0 | 0 | NÃO SE APLICA | 22/05/2025 |  |  |  | 10 | 05/06/2025 | BNO-MABU-300-AA-8502-10002=A01.DOCX | 943,45 KB | 22/05/2025 02:05:32 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00125 | A01 | 5/20/2025
BNO-MABU-300-BA-5537-10002 |  | CONSTRUCTION SCOPE OF WORK | BA - CONSTRUCTION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.02-BA-CONSTRUCTION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 05/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/05/2025 | 08/07/2025 | 8/26/2025 | [10 empty] | NR | NA
BNO-MABU-300-BA-5736-10001 |  | CONSTRUCTION EXECUTION PLAN | BA - CONSTRUCTION | R02 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.02-BA-CONSTRUCTION | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 27/06/2025 |  | A.AGBOGUN |  | 50 | 08/07/2025 | BNO-MABU-300-BA-5736-10001_R02.DOCX | 1,73 MB | 27/06/2025 02:55:11 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/08/2025 |  |  | N/A | N/A |  | BNO-MABU-SNEPCO-2025-INC-00329 | 06/24/2025 | BNO/EXT/MABU/00671 | 07/10/2025 | CODE 3 - MINOR COMMENTS
BNO-MABU-300-BA-5736-10010 |  | SITE ENGINEERING PLAN | BA - CONSTRUCTION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.02-BA-CONSTRUCTION | A0 | 0 | ENG_IFR CONSOLIDATION | 12/07/2025 |  | DCC_MBC |  | 50 | 25/07/2025 | BNO-MABU-300-BA-5736-10010_R01.DOCX | 715,43 KB | 12/07/2025 06:36:05 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/25/2025 |  |  | N/A MABU / IPMT | R01 | 07/11/2025 | BNO-MABU-SNEPCO-2025-INC-00394 | 07/11/2025 | BNO/EXT/MABU/00702 / 713 | 07/22/2025 | CODE 2 - NO COMMENTS
BNO-MABU-300-BA-6065-10003 |  | WELDING PROCEDURE SPECIFICATION AND PQRS - STRUCTURAL | BA - CONSTRUCTION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.02-BA-CONSTRUCTION | A0 | 0 | CANCELADO | 22/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 10 |  | BNO-MABU-300-BA-6065-10003_R01.DOCX | 745,86 KB | 22/05/2025 04:54:33 | [11 empty] | IFR - ISSUED FOR REVIEW | [8 empty] | BNO/EXT/MABU/00627 | 6/23/2025 | CODE 3 - MINOR COMMENTS
BNO-MABU-300-BA-7180-10001 |  | 1ST CONSTRUCTABILITY REVIEW REPORT | BA - CONSTRUCTION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.02-BA-CONSTRUCTION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 26/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/26/2025 | 10/14/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-BA-7753-10001 |  | CONSTRUCTABILITY REVIEW TERMS OF REFERENCE | BA - CONSTRUCTION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.02-BA-CONSTRUCTION | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 29/07/2025 |  | A.AGBOGUN |  | 50 | 12/08/2025 | BNO-MABU-300-BA-7753-10001_R01.DOCX | 846,09 KB | 29/07/2025 05:40:00 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00415 | R01 | 07/25/2025 | BNO/MABU-SNEPCO-2025-INC-00459 | 07/29/2025
BNO-MABU-300-BC-5798-10006 |  | SYSTEM INTEGRATION TEST (SIT) PLAN | BC - COMMISSIONING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.03-BC-COMMISSIONING | A4 | 0 | ENG_IFR COMMENTS - MABU | 27/06/2025 |  | PAULO.MAURICIO | OVERDUE (CPY) | 50 | 08/07/2025 | BNO-MABU-300-BC-5798-10006_R01.DOCX | 908,39 KB | 27/06/2025 02:43:58 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/08/2025 |  |  | N/A | N/A |  | BNO-MABU-SNEPCO-2025-INC-00329 | 06/24/2025 |  |  | OVERDUE
BNO-MABU-300-CS-0514-10001 |  | STRUCTURAL VERIFICATION REPORT - BONGA HULL PEDESTAL STRENGTH ASSESSMENT | CS - STRUCTURAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ENG_IFR CONSOLIDATION | 12/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 25/07/2025 | BNO-MABU-300-CS-0514-10001_A01.DOCX | 1,73 MB | 12/07/2025 05:46:38 |  | 27/05/2025 10:10:15 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 06:03:24 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 06/10/2025 | 07/25/2025 |  | BON-DAE-WESTPAQ-2025-TX-00350 | A01 | 07/11/2025 | BNO-MABU-SNEPCO-2025-INC-00396 | 07/11/2025 |  | 07/30/2025 | OVERDUE |  |  | R | P2
BNO-MABU-300-CS-0514-10002 |  | COROSION INHIBITOR PLATFORM IN PLACE ANALYSIS REPORT CORROSION INHIBITOR PLATFORM IN PLACE ANALYSIS REPORT | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ISSUED | 04/06/2025 | 23/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 18/06/2025 | BNO-MABU-300-CS-0514-10002_R01.DOCX | 7,21 MB | 04/06/2025 05:04:02 |  |  |  |  | 01/07/2025 06:01:26 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/18/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00185 | R01 | 06/04/2025 | BNO-MABU-SNEPCO-2025-INC-00265 | 06/04/2025 | BNO/EXT/MABU/00647 | 7/01/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025 | R | P2
BNO-MABU-300-CS-0514-10018 |  | STARBOARD SUBSEA MODULE STOOL VERIFICATION | CS - STRUCTURAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 50 | 04/08/2025 | BNO-MABU-300-CS-0514-10018_A01.DOCX | 2,88 MB | 22/07/2025 03:04:17 |  |  |  |  | 01/07/2025 06:01:28 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 06/27/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00390 | A01 | 07/22/2025 | BNO-MABU-SNEPCO-2025-INC-00429 | 07/22/2025 |  |  |  |  | 07/01/2025 | R | P2
BNO-MABU-300-CS-0514-10019 |  | WATERFLOOD MODULE STOOL VERIFICATION | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ISSUED | 10/06/2025 | 27/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 25/06/2025 | BNO-MABU-300-CS-0514-10019_R01.DOCX | 2,76 MB | 10/06/2025 07:46:12 |  |  |  |  | 01/07/2025 06:01:29 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00195 | R01 | 06/10/2025 | BNO-MABU-SNEPCO-2025-INC-00277 | 06/13/2025 | BNO/EXT/MABU/00647 | 7/01/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10099 | 07/27/2025 | R | P2
BNO-MABU-300-CS-0514-10020 |  | STARBOARD SUBSEA MODULE IN PLACE ANALYSIS VERIFICATION REPORT | CS - STRUCTURAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ENG_IFR CONSOLIDATION | 09/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 22/07/2025 | BNO-MABU-300-CS-0514-10020_A01.DOCX | 3,84 MB | 09/07/2025 12:44:53 |  | 27/05/2025 09:27:20 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:21 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00322 | A01 | 07/08/2025 | BNO/MABU-SNEPCO-2025-INC-00382 | 07/09/2025 |  | 07/30/2025 | OVERDUE |  |  | R | P2
BNO-MABU-300-CS-0514-10021 |  | WATERFLOOD MODULE DECK EXTENSIONS IN PLACE ANALYSIS VERIFICATION REPORT | CS - STRUCTURAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ISSUED | 03/07/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 16/07/2025 | BNO-MABU-300-CS-0514-10021_A01.DOCX | 18,18 MB | 03/07/2025 14:28:59 |  | 27/05/2025 09:27:20 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:22 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 05/06/2025 | 07/16/2025 |  | BON-DAE-WESTPAQ-2025-TX-00301 | A01 | 07/03/2025 | BNO-MABU-SNEPCO-2025-INC-00370 | 07/03/2025 | BNO_EXT_MABU_00694 | 07/17/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10098 | 07/24/2025 | R | P2
BNO-MABU-300-CS-0514-10022 |  | LACT MODULE STOOL VERIFICATION | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ISSUED | 04/06/2025 | 27/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 18/06/2025 | BNO-MABU-300-CS-0514-10022_R01.DOCX | 3,39 MB | 04/06/2025 10:41:54 |  |  |  |  | 01/07/2025 06:01:31 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00186 | R01 | 06/04/2025 | BNO-MABU-SNEPCO-2025-INC-00265 | 06/04/2025 | BNO/EXT/MABU/00647 | 7/01/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10099 | 07/27/2025 | R | P2
BNO-MABU-300-CS-0514-10023 |  | MR3 HPU DROPPED OBJECT PROTECTION LIFTING ANALYSIS REPORT | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ENG_IFR COMMENTS - MABU | 07/05/2025 |  | ELIANE.RAMOS | NOT ISSUED | 85 | 01/04/2025 | BNO-MABU-300-CS-0514-10023_R01.DOCX | 1,89 MB | 27/03/2025 16:44:03 |  | 28/03/2025 11:30:55 | R01 | IFR - ISSUED FOR REVIEW | 17/04/2025 14:24:38 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/1/2025 | 5/20/2025 | 6/6/2025 | BON-DAE-WESTPAQ-2025-TX-00033 | R01 | 3/21/2025 | BNO-MABU-SNEPCO-2025-INC-00115 | 3/28/2025 | BNO/EXT/MABU/00483 | 4/3/2025 | 3 | BNO-MABU-DAE-2025-TN-10024 | 4/9/2025
BNO-MABU-300-CS-0514-10024 |  | MAIN RACK 3 STRUTURAL VERIFICATION REPORT - IN PLACE ANALYSIS WITH HPU PACKAGE | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA | 14/04/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 01/04/2025 | BNO-MABU-300-CS-0514-10024_R01.DOCX | 2,82 MB | 14/04/2025 01:49:39 |  | 14/04/2025 05:49:37 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 04/01/2025 | 5/20/2025 | 06/06/2025 | BON-DAE-WESTPAQ-2025-TX-00066 | R01 | 04/11/2025 | BNO-MABU-SNEPCO-2025-INC-00149 | 4/14/2025 | BNO/EXT/MABU/00517 | 4/25/2025 |  | BNO-MABU-DAE-2025-TN-10100 | 07/28/2025 | R | P2
BNO-MABU-300-CS-0514-10026 |  | LACT, WATERFLOOD & MR2 MODULE INPLACE ANALYSIS WI PACKAGE, WI HANDLING AREA & WF DECK EXTENSION | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ENG_IFR COMMENTS - MABU | 26/06/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 04/07/2025 | BNO-MABU-300-CS-0514-10026_R01.DOCX | 5,21 MB | 26/06/2025 16:17:39 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/04/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00181 | R01 | 06/23/2025 | BNO-MABU-SNEPCO-2025-INC-00344 | 06/26/2025 | BNO_EXT_MABU_00694 | 07/17/2025 | OVERDUE
BNO-MABU-300-CS-0514-10027 |  | PORTSIDE SUBSEA MODULE AND MR3 MISCELLANEOUS CALCULATION REPORTP | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 12/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 25/07/2025 | BNO-MABU-300-CS-0514-10027_R01.DOCX | 10,34 MB | 12/07/2025 05:54:54 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/25/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00351 | R01 | 07/11/2025 | BNO-MABU-SNEPCO-2025-INC-00394 | 07/11/2025
BNO-MABU-300-CS-0514-10028 |  | STARBOARD SUBSEA MODULE MISCELLANEOUS CALCULATION REPORT | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 19/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 01/08/2025 | BNO-MABU-300-CS-0514-10028_R01.DOCX | 19,16 MB | 19/07/2025 04:59:56 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00388 | R01 | 07/19/2025 | BNO-MABU-SNEPCO-2025-INC-00421 | 07/19/2025
BNO-MABU-300-CS-0514-10029 |  | PORTSIDE SUBSEA MODULE STOOL VERIFICATION REPORT | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ISSUED | 01/07/2025 | 27/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 14/07/2025 | BNO-MABU-300-CS-0514-10029_R01.DOCX | 3,97 MB | 01/07/2025 03:38:36 |  |  |  |  | 01/07/2025 06:01:32 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 07/14/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00280 | R01 | 06/30/2025 | BNO-MABU-SNEPCO-2025-INC-00359 | 06/30/2025 | BNO/EXT/MABU/00647 | 7/01/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10099 | 07/27/2025
BNO-MABU-300-CS-0520-10002 |  | STARBOARD SUBSEA MODULE INPLACE ANALYSIS REPORT -BONGA NORTH MODIFICATIONS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ISSUED | 29/05/2025 | 23/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 12/06/2025 | BNO-MABU-300-CS-0520-10002_R01.DOCX | 12,99 MB | 29/05/2025 10:34:31 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00160 | R01 | 05/29/2025 | BNO-MABU-SNEPCO-2025-INC-00246 | 05/30/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025 | R | P2
BNO-MABU-300-CS-1448-10001 |  | WEIGHT CONTROL REPORT | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ISSUED | 14/05/2025 | 30/05/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 28/04/2025 | BNO-MABU-300-CS-1448-10001_R01.DOCX | 2,96 MB | 14/05/2025 04:27:26 |  | 14/05/2025 05:28:09 | R01 | IFR - ISSUED FOR REVIEW | 28/05/2025 02:43:16 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 4/28/2025 | 6/16/2025 | 07/03/2025 | BON-DAE-WESTPAQ-2025-TX-00103 | R01 | 5/14/2025 | BNO-MABU-SNEPCO-2025-INC-00195 | 5/14/2025 | BNO_EXT_MABU_00566 | 5/27/2025 | 3 |  |  | INFO | NA
BNO-MABU-300-CS-1448-10002 |  | WATER INJECTION TURBINE SKID - STRUCTURAL CALCULATION REPORT - LIFTING ANALYSIS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA | 14/03/2025 |  |  |  | 0 | 23/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/23/2025 | 08/11/2025 | 8/28/2025 | [10 empty] | R | P2
BNO-MABU-300-CS-2358-10001-001 |  | TUPA STRUCTURAL SUPPORT | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 01/07/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 23/06/2025 | BNO-MABU-300-CS-2358-10001-001_R01.DWG | 1,31 MB | 01/07/2025 04:08:05 | [11 empty] | IFR - ISSUED FOR REVIEW | 6/23/2025 | 08/11/2025 | 8/28/2025 | BON-DAE-WESTPAQ-2025-TX-00280 | R01 | 06/30/2025 | BNO/MABU-SNEPCO-2025-INC-00359 | 06/30/2025 | BNO/EXT/MABU/00700 | 07/22/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | R | P2
BNO-MABU-300-CS-2358-10001-002 |  | TUPA STRUCTURAL SUPPORT | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ISSUED | 01/07/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 14/07/2025 | BNO-MABU-300-CS-2358-10001-002_R01.DWG | 1,37 MB | 01/07/2025 04:15:52 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/14/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00280 | R01 | 06/30/2025 | BNO-MABU-SNEPCO-2025-INC-00359 | 06/30/2025 | BNO_EXT_MABU_00700 | 07/22/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025
BNO-MABU-300-CS-2358-10002-001 |  | SSCB CONTROL BUILDING - STRUCTURE - FOUNDATION STOOLS PART 1 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 01/07/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 30/06/2025 | BNO-MABU-300-CS-2358-10002-001_R01.DWG | 2,01 MB | 16/06/2025 07:20:20 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00208 | R01 | 06/16/2025 | BNO-MABU-SNEPCO-2025-INC-00291 | 06/16/2025 | BNO/EXT/MABU/00655 | 07/03/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10097 | 07/24/2025 | R | P2
BNO-MABU-300-CS-2358-10002-002 |  | SSCB CONTROL BUILDING - STRUCTURE - FOUNDATION STOOLS PART 2 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ISSUED | 23/07/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 30/06/2025 | BNO-MABU-300-CS-2358-10002-002_R01.DWG | 1,77 MB | 16/06/2025 07:20:55 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00208 | R01 | 06/16/2025 | BNO-MABU-SNEPCO-2025-INC-00291 | 06/16/2025 | BNO/EXT/MABU/00651 | 7/3/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10103 | 07/29/2025
BNO-MABU-300-CS-2408-10001-001 |  | BGLU MANIFOLD STRUCTURAL DRAWING | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 30/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/30/2025 | 8/18/2025 | 09/04/2025 | [10 empty] | R | P2
BNO-MABU-300-CS-3323-10001 |  | GENERAL NOTES | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA | 14/04/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 01/04/2025 | BNO-MABU-300-CS-3323-10001_R01.DWG | 1,23 MB | 14/04/2025 01:44:36 |  | 14/04/2025 05:49:37 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 04/01/2025 | 5/20/2025 | 06/06/2025 | BON-DAE-WESTPAQ-2025-TX-00066 | R01 | 04/11/2025 | BNO-MABU-SNEPCO-2025-INC-00149 | 4/14/2025 | BNO/EXT/MABU/00517 | 4/25/2025 | 3 |  |  | R | P2
BNO-MABU-300-CS-4018-10001-001 |  | WATERFLOOD MODULE DRAWINGS SHOWING STRUCTURAL REINFORCEMENTS ALL LEVELS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/09/2025 | 07/10/2025 | 7/29/2025 | [10 empty] | R | P2
BNO-MABU-300-CS-4018-10002-001 |  | STARBOARD SUBSEA MODULE DRAWINGS SHOWING STRUCTURAL REINFORCEMENTS ALL LEVELS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 02/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/02/2025 | 07/10/2025 | 7/29/2025 | [10 empty] | R | P2
BNO-MABU-300-CS-4018-10005-001 |  | WATER INJECTION TURBINE STRUCTURAL DRAWINGS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 29/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/29/2025 | 07/10/2025 | 7/29/2025 | [10 empty] | R | P2
BNO-MABU-300-CS-4018-10006-001 |  | WATERFLOOD MODULE - STRUCTURE DUE TO BONGA NORTH MODIFICATIONS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ENG_IFR COMMENTS - MABU | 19/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 01/08/2025 | BNO-MABU-300-CS-4018-10006-001_R01.DWG | 1,53 MB | 19/07/2025 05:14:24 | [11 empty] | IFR - ISSUED FOR REVIEW | 04/08/2025 | 07/10/2025 | 7/29/2025 | BON-DAE-WESTPAQ-2025-TX-00385 | R01 | 07/19/2025 | BON-DAE-WESTPAQ-2025-TX-00385 | 07/19/2025 | [5 empty] | R | P2
BNO-MABU-300-CS-4018-10006-002 |  | DEMOLITION_WATER_FLOOD_MODULE_DECK_EXTENTION_LEVEL_3 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ENG_IFR COMMENTS - MABU | 19/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 01/08/2025 | BNO-MABU-300-CS-4018-10006-002_R01.DWG | 1,43 MB | 19/07/2025 05:13:04 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00385 | R01 | 07/19/2025 | BNO-MABU-SNEPCO-2025-INC-00421 | 07/19/2025
BNO-MABU-300-CS-4018-10008-001 |  | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 1 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA | 30/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10008-001_R01.DWG | 1,33 MB | 30/05/2025 06:19:11 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:24 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00163 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00249 | 5/30/2025 | BNO_EXT_MABU_00599 | 06/16/2025 | CODE 3 - MINOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-CS-4018-10008-002 |  | WATER INJECTION TURBINE SKID STRUCTURE - LEVEL 1 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | NÃO SE APLICA | 30/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10008-002_R01.DWG | 1,36 MB | 30/05/2025 06:33:09 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:25 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00163 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00249 | 5/30/2025 | BNO_EXT_MABU_00599 | 06/16/2025 | CODE 3 - MINOR COMMENTS
BNO-MABU-300-CS-4018-10009-001 |  | WATER INJECTION TURBINE SKID - STRUCTURE - LEVEL 2 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA | 30/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10009-001_R01.DWG | 1,42 MB | 30/05/2025 06:39:23 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:27 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00163 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00249 | 5/30/2025 | BNO_EXT_MABU_00599 | 06/16/2025 | CODE 3 - MINOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-CS-4018-10009-002 |  | WATER INJECTION TURBINE SKID STRUCTURE - LEVEL 2 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | NÃO SE APLICA | 30/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10009-002_R01.DWG | 1,39 MB | 30/05/2025 06:44:40 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:28 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00163 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00249 | 5/30/2025 | BNO_EXT_MABU_00599 | 06/16/2025 | CODE 3 - MINOR COMMENTS
BNO-MABU-300-CS-4018-10010-001 |  | WATER INJECTION TURBINE SKID - STRUCTURE - ELEVATION - NORTH & SOUTH TRUSS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 30/05/2025 | 20/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10010-001_R01.DWG | 2,2 MB | 30/05/2025 06:49:55 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:30 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 05/12/2025 | 07/10/2025 | 7/29/2025 | BON-DAE-WESTPAQ-2025-TX-00163 | R01 | 05/30/2025 | BNO-MABU--SNEPCO-2025-INC-00249 | 5/30/2025 | BNO_EXT_MABU_00599 | 06/16/2025 | CODE 3 - MINOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-CS-4018-10011-001 |  | WATER INJECTION TURBINE SKID - STRUCTURE - TRANSVERSAL SECTION (E 940000) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 30/05/2025 | 20/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10011-001_R01.DWG | 2,09 MB | 30/05/2025 06:53:37 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:31 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00163 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00249 | 5/30/2025 | BNO_EXT_MABU_00599 | 06/16/2025 | CODE 3 - MINOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-CS-4018-10012-001 |  | WATER INJECTION TURBINE SKID - STRUCTURE - TRANSVERSAL SECTION (E 945000) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 30/05/2025 | 20/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10012-001_R01.DWG | 2,13 MB | 30/05/2025 06:57:27 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:33 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00163 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00249 | 5/30/2025 | BNO_EXT_MABU_00599 | 06/16/2025 | CODE 3 - MINOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-CS-4018-10013-001 |  | WATER INJECTION TURBINE SKID - STRUCTURE - TRANSVERSAL SECTION (E 950000) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 30/05/2025 | 20/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10013-001_R01.DWG | 2,13 MB | 30/05/2025 07:41:01 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:34 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00163 | r01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00249 | 5/30/2025 | BNO_EXT_MABU_00599 | 06/16/2025 | CODE 3 - MINOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-CS-4018-10014-001 |  | WATER INJECTION TURBINE SKID - STRUCTURE - DETAILS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA | 30/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10014-001_R01.DWG | 1,38 MB | 30/05/2025 07:44:17 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:36 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00163 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00249 | 5/30/2025 | BNO_EXT_MABU_00599 | 06/16/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10100 | 07/28/2025 | INFO | NA
BNO-MABU-300-CS-4018-10015-001 |  | WATERFLOOD MODULE - DECK EXTENSION (LEVEL 1) MODIFICATIONS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 16/05/2025 | 03/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 09/06/2025 | BNO-MABU-300-CS-4018-10015-001_R01.DWG | 1,42 MB | 16/05/2025 02:40:41 |  | 16/05/2025 08:29:18 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 06/09/2025 | 07/10/2025 | 7/29/2025 | BON-DAE-WESTPAQ-2025-TX-00111 | R01 | 5/16/2025 | BNO-MABU-SNEPCO-2025-INC-00203 | 5/16/2025 | BNO/EXT/MABU/00575 | 06/02/2025 | CODE 3 - MINOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-CS-4018-10015-002 |  | WATERFLOOD MODULE - DECK EXTENSION (LEVEL 1) MODIFICATIONS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ISSUED | 16/05/2025 | 03/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 09/06/2025 | BNO-MABU-300-CS-4018-10015-002_R01.DWG | 2,65 MB | 16/05/2025 02:44:41 |  | 16/05/2025 08:29:18 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 06/09/2025 | 07/10/2025 | 7/29/2025 | BON-DAE-WESTPAQ-2025-TX-00111 | R01 | 5/16/2025 | BNO-MABU-SNEPCO-2025-INC-00203 | 5/16/2025 | BNO/EXT/MABU/00575 | 06/02/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-CS-4018-10016-001 |  | WATERFLOOD MODULE - DECK EXTENSION (LEVEL 3) MODIFICATIONS | CS - STRUCTURAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ENG_IFR CONSOLIDATION | 09/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 23/07/2025 | BNO-MABU-300-CS-4018-10016-001-A01.DWG | 1,5 MB | 09/07/2025 13:00:26 |  | 16/05/2025 08:29:18 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFA - ISSUED FOR APPROVAL | 06/09/2025 | 07/23/2025 |  | BON-DAE-WESTPAQ-2025-TX-00323 | A01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00382 | 07/09/2025 | BNO/EXT/MABU/00717 (OVERDUE) | 07/28/2025 | CODE 1 - APPROVED |  |  | INFO | NA
BNO-MABU-300-CS-4018-10016-002 |  | WATERFLOOD MODULE - DECK EXTENSION (LEVEL 3) MODIFICATIONS | CS - STRUCTURAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ENG_IFR CONSOLIDATION | 09/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 23/07/2025 | BNO-MABU-300-CS-4018-10016-002_A01.DWG | 1,51 MB | 09/07/2025 13:00:47 |  | 16/05/2025 08:29:18 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFA - ISSUED FOR APPROVAL | 06/09/2025 | 07/10/2025 | 7/29/2025 | BON-DAE-WESTPAQ-2025-TX-00323 | A01 | 5/16/2025 | BNO-MABU-SNEPCO-2025-INC-00382 | 07/09/2025 | BNO/EXT/MABU/00717 (OVERDUE) | 07/28/2025 | CODE 1 - APPROVED | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025 | NR | NA
BNO-MABU-300-CS-4018-10016-003 |  | WATERFLOOD MODULE - DECK EXTENSION (LEVEL 3) MODIFICATIONS | CS - STRUCTURAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ENG_IFR CONSOLIDATION | 09/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 23/07/2025 | BNO-MABU-300-CS-4018-10016-003=A01.DWG | 1,62 MB | 09/07/2025 13:01:16 |  | 16/05/2025 08:29:18 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFA - ISSUED FOR APPROVAL | 06/09/2025 | 07/23/2025 | 7/29/2025 | BON-DAE-WESTPAQ-2025-TX-00382 | A01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00323 | 07/09/2025 | BNO/EXT/MABU/00718 (OVERDUE) | 07/28/2025 | CODE 2 - NO COMMENTS |  |  | NR | NA
BNO-MABU-300-CS-4018-10017-001 |  | STARBOARD SUBSEA MODULE - STRUCTURE - DECK EXTENSION - PIG LAUNCHER/RECIEVER (EL+109800) PART 1 | CS - STRUCTURAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 25/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 08/08/2025 | BNO-MABU-300-CS-4018-10017-001_A01.DWG | 1,61 MB | 25/07/2025 06:31:36 |  |  |  |  | 17/06/2025 06:22:17 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00414 | A01 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00447 | 07/25/2025 | BNO_EXT_MABU_00606 | 06/17/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/30/2025 | INFO | NA
BNO-MABU-300-CS-4018-10017-002 |  | STARBOARD SUBSEA MODULE - STRUCTURE - DECK EXTENSION - PIG LAUNCHER/RECIEVER (EL+109800) PART 2 | CS - STRUCTURAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 25/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 08/08/2025 | BNO-MABU-300-CS-4018-10017-002_A01.DWG | 1,62 MB | 25/07/2025 06:31:53 |  |  |  |  | 17/06/2025 06:22:18 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00414 | A01 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00447 | 07/25/2025 | BNO_EXT_MABU_00606 | 06/17/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/30/2025
BNO-MABU-300-CS-4018-10017-003 |  | STARBOARD SUBSEA MODULE - STRUCTURE - DECK EXTENSION - PIG LAUNCHER/RECIEVER (EL+109800) PART 3 | CS - STRUCTURAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 25/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 08/08/2025 | BNO-MABU-300-CS-4018-10017-003_A01.DWG | 1,4 MB | 25/07/2025 06:32:08 |  |  |  |  | 17/06/2025 06:22:19 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00414 | A01 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00447 | 07/25/2025 | BNO_EXT_MABU_00606 | 06/17/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/30/2025
BNO-MABU-300-CS-4018-10018-001 |  | STARBOARD SUBSEA MODULE - STRUCTURE - DECK EXTENSION - SMART CHOKE VALVES (EL+114802) | CS - STRUCTURAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 25/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 08/08/2025 | BNO-MABU-300-CS-4018-10018-001_A01.DWG | 1,3 MB | 25/07/2025 06:32:23 |  | 30/05/2025 10:53:14 | R01 | IFR - ISSUED FOR REVIEW | 17/06/2025 06:22:21 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00414 | A01 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00447 | 07/25/2025 | BNO_EXT_MABU_00606 | 06/17/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025 | INFO | NA
BNO-MABU-300-CS-4018-10018-002 |  | STARBOARD SUBSEA MODULE STRUCTURE - DECK EXTENSION SMART CHOKE VALVES (EL+114802) | CS - STRUCTURAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 25/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 08/08/2025 | BNO-MABU-300-CS-4018-10018-002_A01.DWG | 1,25 MB | 25/07/2025 06:32:44 |  | 30/05/2025 10:53:14 | R01 | IFR - ISSUED FOR REVIEW | 17/06/2025 06:22:22 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00414 | A01 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00447 | 07/25/2025 | BNO_EXT_MABU_00606 | 06/17/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025
BNO-MABU-300-CS-4018-10018-003 |  | STARBOARD SUBSEA MODULE STRUCTURE - DECK EXTENSION SMART CHOKE VALVES (EL+114802) | CS - STRUCTURAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 25/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 08/08/2025 | BNO-MABU-300-CS-4018-10018-003_A01.DWG | 1,26 MB | 25/07/2025 06:33:04 |  | 30/05/2025 10:53:14 | R01 | IFR - ISSUED FOR REVIEW | 17/06/2025 06:22:24 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00414 | A01 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00447 | 07/25/2025 | BNO_EXT_MABU_00606 | 06/17/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025
BNO-MABU-300-CS-4018-10019-001 |  | STARBOARD SUBSEA MODULE - STRUCTURE - INJECTION METHANOL SKID SUPPORT | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 26/06/2025 | 24/07/2025 |  |  | 100 | 08/07/2025 | BNO-MABU-300-CS-4018-10019-001_R01.DWG | 3,88 MB | 26/06/2025 04:44:06 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/08/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00252 | R01 | 06/24/2025 | BNO-MABU-SNEPCO-2025-INC-00328 | 06/24/2025 | BNO/EXT/MABU/00671 (OVERDUE) | 07/10/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10098 | 07/24/2025 | INFO | NA
BNO-MABU-300-CS-4018-10019-002 |  | METHANOL INJECTION SKID SUPPORT | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 26/06/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 08/07/2025 | BNO-MABU-300-CS-4018-10019-002_R01.DWG | 2,3 MB | 26/06/2025 04:54:58 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/08/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00252 | R01 | 06/24/2025 | BNO-MABU-SNEPCO-2025-INC-00328 | 06/24/2025 | BNO/EXT/MABU/00671 (OVERDUE) | 07/10/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10098 | 07/24/2025
BNO-MABU-300-CS-4018-10020-001 |  | PORTSIDE SUBSEA MODULE -STRUCTURE - DECK EXTENSION - MEZZANINE LEVEL - (CORROSION INHIBITOR SKID) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 30/05/2025 | 23/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10020-001_R01.DWG | 1,28 MB | 30/05/2025 07:29:11 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 20/06/2025 14:39:52 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/13/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00168 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00249 | 5/30/2025 | BNO_EXT_MABU_00622 | 06/20/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025 | INFO | NA
BNO-MABU-300-CS-4018-10020-002 |  | PORTSIDE SUBSEA MODULE -STRUCTURE – DECK EXTENSION - MEZZANINE LEVEL - (CORROSION INHIBITOR SKID) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 30/05/2025 | 23/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10020-002_R01.PDF | 822,96 KB | 30/05/2025 07:29:15 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 20/06/2025 14:39:54 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/13/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00168 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00249 | 5/30/2025 | BNO_EXT_MABU_00622 | 06/20/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025
BNO-MABU-300-CS-4018-10020-003 |  | PORTSIDE SUBSEA MODULE -STRUCTURE – DECK EXTENSION - MEZZANINE LEVEL - (CORROSION INHIBITOR SKID) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 30/05/2025 | 23/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10020-003_R01.PDF | 844,17 KB | 30/05/2025 07:29:25 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 20/06/2025 14:39:55 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/13/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00168 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00249 | 5/30/2025 | BNO_EXT_MABU_00622 | 06/20/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025
BNO-MABU-300-CS-4018-10020-004 |  | PORTSIDE SUBSEA MODULE -STRUCTURE – DECK EXTENSION - MEZZANINE LEVEL - (CORROSION INHIBITOR SKID) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 30/05/2025 | 23/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10020-004_R01.DWG | 1,4 MB | 30/05/2025 07:29:19 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 20/06/2025 14:39:56 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/13/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00168 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00249 | 5/30/2025 | BNO/EXT/MABU/00622 | 6/20/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025
BNO-MABU-300-CS-4018-10021-001 |  | STARBOARD SUBSEA MODULE - STRUCTURE - MONORAIL/EQP FOUNDATION/CONTAINMENT BASIN TO PIG LAUNCHER/RECIEVER SHEET 1 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 20/06/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 04/07/2025 | BNO-MABU-300-CS-4018-10021-001_R01.DWG | 1,44 MB | 20/06/2025 03:26:51 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00227 | R01 | 06/20/2025 | BNO/MABU-SNEPCO-2025-INC-00306 | 05/20/2025 | BNO/EXT/MABU/00661 | 07/07/2025 | CODE 2 - NO COMMENTS | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | INFO | NA
BNO-MABU-300-CS-4018-10021-002 |  | STARBOARD SUBSEA MODULE - STRUCTURE - MONORAIL/EQP FOUNDATION/CONTAINMENT BASIN TO PIG LAUNCHER/RECIEVER SHEET 2 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ISSUED | 20/06/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 04/07/2025 | BNO-MABU-300-CS-4018-10021-002_R01.DWG | 1,7 MB | 20/06/2025 03:27:28 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00227 | R01 | 06/20/2025 | BNO/MABU-SNEPCO-2025-INC-00306 | 06/20/2025 | BNO_EXT_MABU_00661 | 07/07/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025
BNO-MABU-300-CS-4018-10022-001 |  | MAIN RACK 3 - STRUCTURE - HPU DECK EXTENSION | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 21/05/2025 | 13/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 14/04/2025 | BNO-MABU-300-CS-4018-10022-001_R01.DWG | 1,74 MB | 21/05/2025 00:42:16 |  | 22/05/2025 07:22:59 | R01 | IFR - ISSUED FOR REVIEW | 17/06/2025 10:03:32 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/14/2025 | 07/10/2025 | 7/29/2025 | BON-DAE-WESTPAQ-2025-TX-00127 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00220 | 5/22/2025 | BNO/EXT/MABU/00597 | 06/10/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-CS-4018-10022-002 |  | MAIN RACK 3 - STRUCTURE - HPU DECK EXTENSION SHT.2 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 21/05/2025 | 13/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 14/04/2025 | BNO-MABU-300-CS-4018-10022-002_R01.DWG | 1,56 MB | 21/05/2025 00:47:29 |  | 22/05/2025 07:22:59 | R01 | IFR - ISSUED FOR REVIEW | 17/06/2025 10:03:33 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/14/2025 | 07/10/2025 | 7/29/2025 | BON-DAE-WESTPAQ-2025-TX-00127 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00220 | 5/22/2025 | BNO/EXT/MABU/00597 | 06/10/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-CS-4018-10022-003 |  | MAIN RACK 3 - STRUCTURE - HPU DECK EXTENSION SHT.3 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 21/05/2025 | 13/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 14/04/2025 | BNO-MABU-300-CS-4018-10022-003_R01.DWG | 1,86 MB | 21/05/2025 00:51:29 |  | 22/05/2025 07:22:59 | R01 | IFR - ISSUED FOR REVIEW | 17/06/2025 10:03:34 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/14/2025 | 07/10/2025 | 7/29/2025 | BON-DAE-WESTPAQ-2025-TX-00127 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00220 | 5/22/2025 | BNO/EXT/MABU/00597 | 06/10/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-CS-4018-10023-001 |  | WATER INJECTION TURBINE SKID - STRUCTURE - WALKWAYS AND STAIRS - PART 1 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 02/06/2025 | 01/07/2025 |  | ISSUED AS CODE 2 - NO COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-CS-4018-10023-001_R01.DWG | 2,74 MB | 02/06/2025 05:52:53 |  | 02/06/2025 07:18:47 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 06:03:26 | R01 | 2-NO COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00172 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00253 | 06/02/2025 | BNO/EXT/MABU/00602 | 6/16/2025 | CODE 2 - NO COMMENTS | BNO-MABU-DAE-2025-TN-10084 | 07/01/2025 | INFO | NA
BNO-MABU-300-CS-4018-10024-001 |  | WATER INJECTION TURBINE SKID - STRUCTURE - WALKWAYS AND STAIRS - PART 2 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 02/06/2025 | 23/06/2025 |  | ISSUED AS CODE 2 - NO COMMENTS | 50 | 09/06/2025 | BNO-MABU-300-CS-4018-10024-001_R01.DWG | 2,71 MB | 02/06/2025 05:58:50 |  | 02/06/2025 07:18:47 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 06:03:27 | R01 | 2-NO COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00172 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00253 | 06/02/2025 | BNO_EXT_MABU_00602 | 06/16/2025 | CODE 2 - NO COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025 | INFO | NA
BNO-MABU-300-CS-4018-10024-002 |  | WATER INJECTION TURBINE SKID STRUCTURE WALKWAYS AND STAIRS - PART 2 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ISSUED | 02/06/2025 | 23/06/2025 |  | ISSUED AS CODE 2 - NO COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-CS-4018-10024-002_R01.DWG | 2,74 MB | 02/06/2025 06:02:01 |  | 02/06/2025 07:18:47 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 06:03:29 | R01 | 2-NO COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00172 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00253 | 06/02/2025 | BNO_EXT_MABU_00602 | 06/16/2025 | CODE 2 - NO COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025
BNO-MABU-300-CS-4018-10025-001 |  | WATER INJECTION TURBINE SKID - STRUCTURE - TRANSVERSAL SECTION (E 935000) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 30/05/2025 | 21/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10025-001_R01.DWG | 2,08 MB | 30/05/2025 07:47:33 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:38 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00163 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00249 | 5/30/2025 | BNO_EXT_MABU_00599 | 06/16/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-CS-4018-10026-001 |  | MAIN RACK 2 - STRUCTURE - WI PUMP HANDLING AREA | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA | 12/05/2025 |  |  | ISSUED AS CODE 2 - NO COMMENTS | 50 | 14/04/2025 | BNO-MABU-300-CS-4018-10026-001_R01.DWG | 1,94 MB | 21/04/2025 06:06:30 |  | 22/04/2025 05:47:47 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 4/14/2025 | 07/10/2025 | 7/29/2025 | BON-DAE-WESTPAQ-2025-TX-00075 | R01 | 4/17/2025 | BNO-MABU-SNEPCO-2025-INC-00159 | 4/22/2025 | OVERDUE |  |  | BNO-MABU-DAE-2025-TN-10045 | 07/28/2025 | R | P2
BNO-MABU-300-CS-4018-10026-002 |  | MAIN RACK 2 - STRUCTURE - WI PUMP HANDLING AREA | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA | 21/04/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 14/04/2025 | BNO-MABU-300-CS-4018-10026-002_R01.DWG | 1,95 MB | 21/04/2025 06:07:16 |  | 22/04/2025 05:47:47 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFA - ISSUED FOR APPROVAL | 4/14/2025 | 07/10/2025 | 7/29/2025 | BON-DAE-WESTPAQ-2025-TX-00075 | R01 | 4/17/2025 | BNO-MABU-SNEPCO-2025-INC-00159 | 4/22/2025 | OVERDUE |  |  | BNO-MABU-DAE-2025-TN-10040 | 05/07/2025 | R | P2
BNO-MABU-300-CS-4018-10027-001 |  | STARBOARD SUBSEA MODULE - STRUCTURE - DECK EXTENSION (EL.108_719) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ENG_IFR CONSOLIDATION | 16/06/2025 |  | PRISCILLAMAIOLINO.RC | ISSUED AS CODE 2 - NO COMMENTS | 100 | 30/06/2025 | BNO-MABU-300-CS-4018-10027-001_R01.DWG | 2,16 MB | 16/06/2025 07:49:37 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00208 | R01 | 06/16/2025 | BNO-MABU-SNEPCO-2025-INC-00291 | 06/16/2025 | BNO/EXT/MABU/00651 | 07/03/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10098 | 07/24/2025 | INFO | NA
BNO-MABU-300-CS-4018-10027-002 |  | STARBOARD SUBSEA MODULE STRUCTURE - DECK EXTENSION (EL.+108719) | NÃO SE APLICA | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ISSUED | 23/07/2025 | 24/07/2025 |  | ISSUED AS CODE 2 - NO COMMENTS | 100 | 30/06/2025 | BNO-MABU-300-CS-4018-10027-002_R01.DWG | 2,21 MB | 16/06/2025 07:50:15 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00208 | R01 | 06/16/2025 | BNO-MABU-SNEPCO-2025-INC-00291 | 06/16/2025 | BNO_EXT_MABU_00656 | 07/04/2025 | CODE 2 - NO COMMENTS | BNO-MABU-DAE-2025-TN-10098 | 07/24/2025
BNO-MABU-300-CS-4018-10027-003 |  | STARBOARD SUBSEA MODULE STRUCTURE - DECK EXTENSION (EL.+108719) | NÃO SE APLICA | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ISSUED | 16/06/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 30/06/2025 | BNO-MABU-300-CS-4018-10027-003_R01.DWG | 2,19 MB | 16/06/2025 07:51:23 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00208 | R01 | 06/16/2025 | BNO-MABU-SNEPCO-2025-INC-00291 | 06/16/2025 | BNO_EXT_MABU_00656 | 07/03/2025 | CODE 2 - NO COMMENTS | BNO-MABU-DAE-2025-TN-10098 | 07/24/2025
BNO-MABU-300-CS-4018-10028-001 |  | WATER INJECTION TURBINE LIFTING ARRANGEMENT | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 29/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/29/2025 | 07/10/2025 | 7/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10031-001 |  | LACT MODULE ALTERATIONS DUE MR2 REINFORCEMENT | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 22/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/22/2025 | 07/10/2025 | 7/29/2025 | [10 empty] | INFO | NA
BNO-MABU-300-CS-4018-10032-001 |  | HPU SUPPORT STRUCTURE MR3 HPU SUPPORT STRUCTURE | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 22/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/22/2025 | 07/10/2025 | 7/29/2025 | [10 empty] | R | P2
BNO-MABU-300-CS-4018-10033 |  | PORT SUBSEA MODULE STOOL VERIFICATIONPORTSIDE SUBSEA MODULE STOOL VERIFICATION | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 22/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/22/2025 | 07/10/2025 | 7/29/2025 | [10 empty] | R | P2
BNO-MABU-300-CS-4018-10034 |  | LACT_ WATERFLOOD (WF) & MR2 MODULE IN PLACE ANALYSIS WITH WI PACKAGE_ WI HANDLING AREA & WF DECK EXTENSIONS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA | 14/03/2025 |  |  |  | 0 | 22/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/22/2025 | 7/10/2025 | 7/29/2025
BNO-MABU-300-CS-4018-10035-001 |  | LACT MODULE DRAWINGS SHOWING STRUCTURAL REINFORCEMENTS ALL LEVELS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/09/2025 | 07/10/2025 | 7/29/2025 | [10 empty] | INFO | NA
BNO-MABU-300-CS-4018-10036-001 |  | MAIN RACK 3 DRAWINGS SHOWING STRUCTURAL REINFORCEMENTS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 12/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 05/12/2025 | 07/10/2025 | 7/29/2025 | [10 empty] | INFO | NA
BNO-MABU-300-CS-4018-10037-001 |  | MAIN RACK 3 - STRUCTURE - HPU DROPPED OBJECT PROTECTION DRAWING | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA | 07/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 85 | 01/04/2025 | BNO-MABU-300-CS-4018-10037-001_R01.DWG | 6,71 MB | 27/03/2025 16:57:58 |  | 28/03/2025 10:54:30 | R01 | IFR - ISSUED FOR REVIEW | 17/04/2025 14:24:44 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/1/2025 | 5/20/2025 | 6/6/2025 | BON-DAE-WESTPAQ-2025-TX-00035 | R01 | 3/21/2025 | BNO-MABU-SNEPCO-2025-INC-00119 | 3/24/2025 | BNO/EXT/MABU/00483 | 4/3/2025 | 3 | BNO-MABU-DAE-2025-TN-10024 | 4/9/2025
BNO-MABU-300-CS-4018-10037-002 |  | MAIN RACK 3 - STRUCTURE - HPU DROPPED OBJECT PROTECTION DRAWING | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA | 07/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 01/04/2025 | BNO-MABU-300-CS-4018-10037-002_R01.DWG | 6,95 MB | 27/03/2025 16:57:57 |  | 28/03/2025 10:54:30 | R01 | IFR - ISSUED FOR REVIEW | 17/04/2025 14:24:42 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 04/01/2025 | 5/20/2025 | 06/06/2025 | BON-DAE-WESTPAQ-2025-TX-00035 | R01 | 3/21/2025 | BNO-MABU-SNEPCO-2025-INC-00119 | 3/24/2025 | BNO/EXT/MABU/00483 | 04/03/2025 | 3 | BNO-MABU-DAE-2025-TN-10024 | 04/09/2025 | NR | NA
BNO-MABU-300-CS-4018-10038-001 |  | WATER INJECTION TURBINE SKID - TYPICAL DETAILS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 30/05/2025 | 20/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10038-001_R01.DWG | 1,55 MB | 30/05/2025 07:54:59 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:39 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00163 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00249 | 5/30/2025 | BNO_EXT_MABU_00599 | 06/16/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-CS-4018-10038-002 |  | WATER INJECTION TURBINE SKID TYPICAL DETAILS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ISSUED | 30/05/2025 | 20/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10038-002_R01.DWG | 1,55 MB | 30/05/2025 07:57:44 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:41 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00163 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00249 | 5/30/2025 | BNO_EXT_MABU_00599 | 06/16/2025 | CODE 3 - MINOR COMMENTS
BNO-MABU-300-CS-4018-10038-003 |  | WATER INJECTION TURBINE SKID TYPICAL DETAILS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ISSUED | 30/05/2025 | 20/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-CS-4018-10038-003_R01.DWG | 1,57 MB | 30/05/2025 08:01:07 |  | 30/05/2025 08:51:06 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:42 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00163 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00249 | 5/30/2025 | BNO_EXT_MABU_00599 | 06/16/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025
BNO-MABU-300-CS-4018-10039-001 |  | WATERFLOOD MODULE - DECK EXTENSION - STAIRS AND LADDERS DETAILS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 28/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/28/2025 | 7/16/2025 | 08/04/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10040-001 |  | WATERFLOOD MODULE - DECK EXTENSION - SECTIONS AND DETAILS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 28/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/28/2025 | 7/16/2025 | 08/04/2025 | [10 empty] | INFO | NA
BNO-MABU-300-CS-4018-10041-001 |  | WATERFLOOD MODULE - DECK EXTENSION - TYPICAL DETAILS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 28/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/28/2025 | 7/16/2025 | 08/04/2025 | [10 empty] | R | P2
BNO-MABU-300-CS-4018-10042-001 |  | STARBOARD SUBSEA MODULE DROPPED OBJECT PROTECTION PART 1 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 01/07/2025 | 01/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 30/06/2025 | BNO-MABU-300-CS-4018-10042-001_R01.DWG | 2,73 MB | 16/06/2025 08:38:56 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00208 | R01 | 06/16/2025 | BNO-MABU-SNEPCO-2025-INC-00291 | 06/16/2025 | BNO/EXT/MABU/00655 | 07/03/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10100 | 07/28/2025 | R | P2
BNO-MABU-300-CS-4018-10042-002 |  | STARBOARD SUBSEA MODULE DROPPED OBJECT PROTECTION PART 2 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ISSUED | 01/07/2025 | 01/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 30/06/2025 | BNO-MABU-300-CS-4018-10042-002_R01.DWG | 2,31 MB | 16/06/2025 08:39:34 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00208 | R01 | 06/16/2025 | BNO-MABU-SNEPCO-2025-INC-00291 | 06/16/2025 | BNO/EXT/MABU/00655 | 07/03/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10100 | 07/28/2025
BNO-MABU-300-CS-4018-10042-003 |  | STARBOARD SUBSEA MODULE DROPPED OBJECT PROTECTION PART 3 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ISSUED | 01/07/2025 | 01/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 30/06/2025 | BNO-MABU-300-CS-4018-10042-003_R01.DWG | 2,46 MB | 16/06/2025 08:40:58 | [11 empty] | IFR - ISSUED FOR REVIEW | 06/30/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00208 | R01 | 06/16/2025 | BNO-MABU-SNEPCO-2025-INC-00291 | 06/16/2025 | BNO_EXT_MABU_00656 | 07/03/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10084 | 07/01/2025
BNO-MABU-300-CS-4018-10043-001 |  | STARBOARD SUBSEA MODULE - SECTIONS AND DETAILS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 01/07/2025 | 20/07/2025 |  |  | 100 | 14/07/2025 | BNO-MABU-300-CS-4018-10043-001_R01.DWG | 1,35 MB | 01/07/2025 04:26:32 | [11 empty] | IFR - ISSUED FOR REVIEW | 7/14/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00280 | R01 | 06/30/2025 | BNO-MABU-SNEPCO-2025-INC-00359 | 06/30/2025 | BNO_EXT_MABU_00694 | 07/17/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | NR | NA
BNO-MABU-300-CS-4018-10043-002 |  | BLOWDOWN PIPING AREA ACCESS 1 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ISSUED | 01/07/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 14/07/2025 | BNO-MABU-300-CS-4018-10043-002_R01.DWG | 1,34 MB | 01/07/2025 04:31:22 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/14/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00280 | R01 | 06/30/2025 | BNO-MABU-SNEPCO-2025-INC-00359 | 06/30/2025 | BNO_EXT_MABU_00694 | 07/17/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025
BNO-MABU-300-CS-4018-10044-001 |  | STARBOARD SUBSEA MODULE - TYPICAL DETAILS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | ISSUED | 29/06/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 11/07/2025 | BNO-MABU-300-CS-4018-10044-001_R01.DWG | 3,15 MB | 29/06/2025 16:28:40 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00265 | R01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-0035 | 06/29/2025 | BNO_EXT_MABU_00694 | 07/17/2025 | CODE 2 - NO COMMENTS | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | NR | NA
BNO-MABU-300-CS-4018-10045-001 |  | PORTSIDE SUBSEA MODULE - STAIRS AND LADDERS DETAILS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 21/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/21/2025 | 09/08/2025 | 9/25/2025 | [10 empty] | R | P2
BNO-MABU-300-CS-4018-10051-001 |  | STRUCTURAL PIPE SUPPORTS LAYOUTS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 23/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/23/2025 | 08/11/2025 | 8/28/2025 | [10 empty] | INFO | NA
BNO-MABU-300-CS-4018-10052-001 |  | STRUCTURAL PIPE SUPPORTS -SECTIONS AND DETAILS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 23/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/23/2025 | 08/11/2025 | 8/28/2025 | [10 empty] | INFO | NA
BNO-MABU-300-CS-4018-10053-001 |  | STRUCTURAL PIPE SUPPORTS -DRAWING INDEX | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 23/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/23/2025 | 08/11/2025 | 8/28/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10054-001 |  | STRUCTURAL CABLE TRAY SUPPORTS LAYOUTS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 15/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/15/2025 | 10/03/2025 | 10/22/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10055-001 |  | STRUCTURAL CABLE TRAY SUPPORTS -SECTIONS AND DETAILS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 15/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/15/2025 | 10/03/2025 | 10/22/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10056-001 |  | STRUCTURAL CABLE TRAY SUPPORTS -DRAWING INDEX | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 15/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/15/2025 | 10/03/2025 | 10/22/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10057-001 |  | CABLE LADDER LAYOUT SUPPORTS - MR2 LEVEL 1 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 9/22/2025 | 10/09/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10058-001 |  | CABLE LADDER LAYOUT SUPPORTS - MR3 LEVEL 1 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 9/22/2025 | 10/09/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10059-001 |  | CABLE LADDER LAYOUT SUPPORTS - MR3 LEVEL 4 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 9/22/2025 | 10/09/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10060-001 |  | CABLE LADDER LAYOUT SUPPORTS - PS LEVEL 1 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 9/22/2025 | 10/09/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10061-001 |  | CABLE LADDER LAYOUT SUPPORTS - MR2 LEVEL 4 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 9/22/2025 | 10/09/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10062-001 |  | CABLE LADDER LAYOUT SUPPORTS - SS LEVEL 1 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 9/22/2025 | 10/09/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10063-001 |  | CABLE LADDER LAYOUT SUPPORTS - MR6 LEVEL 1 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 9/22/2025 | 10/09/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10064-001 |  | CABLE LADDER LAYOUT SUPPORTS - SS LEVEL 2 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 9/22/2025 | 10/09/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10065-001 |  | CABLE LADDER LAYOUT SUPPORTS - MR4 LEVEL 1 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 9/22/2025 | 10/09/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10066-001 |  | CABLE LADDER LAYOUT SUPPORTS - MR1 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 9/22/2025 | 10/09/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10067-001 |  | CABLE LADDER LAYOUT SUPPORTS - MR5 LEVEL 1 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 9/22/2025 | 10/09/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-4018-10068-001 |  | CABLE LADDER LAYOUT SUPPORTS - VR MODULE LEVEL 1 | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 9/22/2025 | [11 empty] | NR | NA
BNO-MABU-300-CS-4018-10069-001 |  | DEMOLITION_DRAWING_WATER_INJECTION_TURBINE_SKID_STRUCTURE_EXTENSI | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 19/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 01/08/2025 | BNO-MABU-300-CS-4018-10069-001_R01.DWG | 2,86 MB | 19/07/2025 05:13:21 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00385 | R01 | 07/19/2025 | BNO-MABU-SNEPCO-2025-INC-00421 | 07/19/2025
BNO-MABU-300-CS-4018-10070-001 |  | DEMOLITION DRAWING FOR PS MODULE CORROSION INHIBITOR SKID DECK EXTENSION | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 19/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 01/08/2025 | BNO-MABU-300-CS-4018-10070-001_R01.DWG | 3,92 MB | 19/07/2025 05:13:25 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00385 | R01 | 07/19/2025 | BNO-MABU-SNEPCO-2025-INC-00421
BNO-MABU-300-CS-4018-10071-001 |  | DEMOLITION DRAWING FOR SS MODULE E LAUNCHER RECEIVER DECK EXTENSION | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 19/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 01/08/2025 | BNO-MABU-300-CS-4018-10071-001_R01.DWG | 1,48 MB | 19/07/2025 05:13:08 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00385 | R01 | 07/19/2025 | BNO-MABU-SNEPCO-2025-INC-00421 | 07/19/2025
BNO-MABU-300-CS-4018-10072-001 |  | DEMOLITION DRAWING FOR MR3 HPU DECK EXTENSION | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 19/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 01/08/2025 | BNO-MABU-300-CS-4018-10072-001_R01.DWG | 1,78 MB | 19/07/2025 05:13:30 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00385 | R01 | 07/19/2025 | BNO-MABU-SNEPCO-2025-INC-00421 | 07/19/2025
BNO-MABU-300-CS-4018-10073-001 |  | DEMOLITION DRAWING_MR2 WI PUMP HANDLING AREA | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 19/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 01/08/2025 | BNO-MABU-300-CS-4018-10073-001_R01.DWG | 2,5 MB | 19/07/2025 05:13:18 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00385 | R01 | 07/19/2025 | BNO-MABU-SNEPCO-2025-INC-00421 | 07/19/2025
BNO-MABU-300-CS-4018-10074-001 |  | DEMOLITION DRAWING FOR SS MODULE SMART CHOKE VALVE DECK EXTENSION | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 19/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 50 | 01/08/2025 | BNO-MABU-300-CS-4018-10074-001_R01.DWG | 2,78 MB | 19/07/2025 05:13:14 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00385 | R01 | 07/19/2025 | BNO-MABU-SNEPCO-2025-INC-00421 | 07/19/2025
BNO-MABU-300-CS-5721-10001 |  | STRUCTURAL DESIGN PREMISE | CS - STRUCTURAL | R02 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA |  |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 01/04/2025 | BNO-MABU-300-CS-5721-10001_R02.DOCX | 1009,22 KB | 15/05/2025 05:24:03 |  | 28/03/2025 10:33:15 | R01 | IFR - ISSUED FOR REVIEW | 15/05/2025 05:29:59 | R02 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 04/01/2025 | 5/20/2025 | 06/06/2025 | BON-DAE-WESTPAQ-2025-TX-00037 | R02 | 3/21/2025 | BNO/MABU-SNEPCO-2025-INC-00162 | 4/24/2025 | OVERDUE |  |  | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025 | R | P1
BNO-MABU-300-CS-6063-10001 |  | WEIGHT CONTROL PROCEDURE | CS - STRUCTURAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ISSUED | 19/05/2025 | 13/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 04/04/2025 | BNO-MABU-300-CS-6063-10001_A01.DOCX | 1,56 MB | 19/05/2025 02:21:54 |  | 22/05/2025 07:22:59 | A01 | IFA - ISSUED FOR APPROVAL | 17/06/2025 10:03:36 | A01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 04/04/2025 | 5/23/2025 | 06/11/2025 | BON-DAE-WESTPAQ-2025-TX-00117 | A01 | 5/16/2025 | BNO-MABU-SNEPCO-2025-INC-00154 | 4/15/2025 | BNO/EXT/MABU/00597 | 06/10/2025 | CODE 3 - MINOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-CS-7180-10001 |  | TBE FOR STRUCTURAL MATERIALS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/25/2025 | 10/13/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-7303-10001 |  | STRUCTURAL MATERIAL TAKE-OFF (MTO) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 20/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/20/2025 | 08/08/2025 | 8/27/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-7303-10003 |  | WATER INJECTION TURBINE SKID - STRUCTURE - MATERIAL LIST (MTO) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ISSUED | 22/06/2025 | 08/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 04/07/2025 | BNO-MABU-300-CS-7303-10003_R01.DOCX | 1006,87 KB | 22/06/2025 00:28:24 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/04/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00236 | R01 | 06/22/2025 | BNO/MABU-SNEPCO-2025-INC-00315 | 06/22/2025 | BNO/EXT/MABU/00658 | 07/07/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10088 | 07/08/2025 | NR | NA
BNO-MABU-300-CS-7303-10004 |  | PORT SUBSEA MODULE - STRUCTURE DECK EXTENSIONS - MATERIAL LIST (MTO)PORTSIDE SUBSEA MODULE - STRUCTURE DECK EXTENSIONS - MATERIAL LIST (MTO) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | DCC_IFR OFFICIAL TRANSMITTAL | 07/07/2025 |  | DCC_WPQ,E.DUKE |  | 50 | 21/07/2025 | BNO-MABU-300-CS-7303-10004_R01.DOCX | 1,05 MB | 07/07/2025 05:13:13 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/21/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00310 | R01 | 07/07/2025 | BNO-MABU-SNEPCO-2025-INC-00376 | 07/07/2025 | BNO/EXT/MABU/00700 | 07/22/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-CS-7303-10005 |  | WATERFLOOD MODULE - STRUCTURE - DECK EXTENSIONS LEVEL 1 & 3 - MATERIAL LIST (MTO) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 08/04/2025 | 8/21/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-7303-10006 |  | STARBOARD SUBSEA MODULE - STRUCTURE DUE TO BONGA NORTH MODIFICATIONS - MATERIAL LIST (MTO) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 14/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/14/2025 | 09/01/2025 | 9/18/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-7303-10007 |  | MAIN RACK 3 - STRUCTURE - HPU DECK EXTENSION - MATERIAL LIST (MTO) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA | 14/03/2025 |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 08/04/2025 | 8/21/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-7303-10008 |  | MAIN RACK 2 - STRUCTURE - WI PUMP HANDLING AREA - MATERIAL LIST (MTO) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ISSUED | 26/06/2025 | 24/07/2025 |  |  | 100 | 11/07/2025 | BNO-MABU-300-CS-7303-10008_R01.DOCX | 1005,63 KB | 26/06/2025 10:11:40 | [11 empty] | IFR - ISSUED FOR REVIEW | 06/26/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00259 | R01 | 06/26/2025 | BNO-MABU-SNEPCO-2025-INC-00340 | 06/26/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10097 | 07/24/2025 | NR | NA
BNO-MABU-300-CS-7303-10012 |  | STRUCTURAL PIPE SUPPORTS MTO | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 14/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/14/2025 | 09/01/2025 | 9/18/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-7303-10013 |  | STRUCTURAL CABLE TRAY SUPPORTS MTO | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 01/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/01/2025 | 10/20/2025 | 11/06/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-7303-10014 |  | REQUISITION FOR STRUCTURAL MATERIALS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 15/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/15/2025 | 9/19/2025 | 9/26/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-7303-10017 |  | WATERFLOOD MODULE - STRUCTURE DUE TO BONGA NORTH MODIFICATIONS - MATERIAL LIST (MTO) | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ISSUED | 19/06/2025 | 08/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 03/07/2025 | BNO-MABU-300-CS-7303-10017_R01.DOCX | 1,1 MB | 19/06/2025 09:43:56 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/03/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00223 | R01 | 06/19/2025 | BNO-MABU-SNEPCO-2025-INC-00305 | 06/19/2025 | BNO/EXT/MABU/00658 | 07/03/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10088 | 07/08/2025 | NR | NA
BNO-MABU-300-CS-8102-10001 |  | BONGA HULL PEDESTALS FATIGUE ASSESSMENT REPORT FOR WF. PS. LACT & SS MODULES | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA | 14/03/2025 |  |  |  | 0 | 26/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/26/2025 | 7/14/2025 | 7/31/2025 | [10 empty] | R | P2
BNO-MABU-300-CS-8102-10010 |  | WATER INJECTION TURBINE STRUCTURE CALCULATION MEMORY | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 30/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/30/2025 | 6/18/2025 | 07/07/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-8180-10003 |  | WATER INJECTION TURBINE SKID - STRUCTURAL VERIFICATION REPORT - IN PLACE ANALYSIS | CS - STRUCTURAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ISSUED | 02/07/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 15/07/2025 | BNO-MABU-300-CS-8180-10003_A01.DOCX | 5,2 MB | 02/07/2025 16:50:26 |  | 27/05/2025 10:10:15 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:44 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 05/27/2025 | 07/14/2025 |  | BON-DAE-WESTPAQ-2025-TX-00287 | A01 | 07/01/2025 | BNO-MABU-SNEPCO-2025-INC-00364 | 07/02/2025 | AN ASSAI ISSUE See 696 - N/A |  | OVERDUE | BNO-MABU-DAE-2025-TN-10097 | 07/24/2025 | R | P2
BNO-MABU-300-CS-8180-10005 |  | MAIN RACK 3 - STRUCTURAL CALCULATION REPORT - BONGA NORTH MODIFICATIONS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ISSUED | 22/05/2025 | 15/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 05/06/2025 | BNO-MABU-300-CS-8180-10005_R01.DOCX | 6,94 MB | 22/05/2025 09:41:50 |  | 22/05/2025 10:09:43 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:45 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/09/2025 | 7/28/2025 | 8/14/2025 | BON-DAE-WESTPAQ-2025-TX-00136 | R01 | 5/22/2025 | BNO-MABU-SNEPCO-2025-INC-00222 | 5/22/2025 | BNO_EXT_MABU_00599 | 06/16/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-CS-8180-10006 |  | PORT SUBSEA MODULE - STRUCTURAL CALCULATION REPORT - BONGA NORTH MODIFICATIONSPORTSIDE SUBSEA MODULE - STRUCTURAL CALCULATION REPORT - BONGA NORTH MODIFICATIONS | CS - STRUCTURAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | ENG_IFR CONSOLIDATION | 26/06/2025 |  | PRISCILLAMAIOLINO.RC | ISSUED AS CODE 2 - NO COMMENTS | 85 | 08/07/2025 | BNO-MABU-300-CS-8180-10006_A01.DOCX | 1,72 MB | 26/06/2025 04:35:08 |  | 03/04/2025 13:57:13 | R01 | IFR - ISSUED FOR REVIEW | 17/04/2025 14:24:40 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 06/09/2025 | 07/08/2025 |  | BON-DAE-WESTPAQ-2025-TX-00251 | A01 | 06/24/2025 | BNO-MABU-300-CS-8180-10006 | 06/27/2025 | BNO/EXT/MABU/00702 | 07/22/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10100 | 07/28/2025 | R | P2
BNO-MABU-300-CS-8180-10011 |  | STARBOARD SUBSEA MODULE - STRUCTURAL CALCULATION REPORT - BONGA NORTH MODIFICATIONS | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/09/2025 | 7/28/2025 | 8/14/2025 | [10 empty] | R | P2
BNO-MABU-300-CS-8180-10012 |  | STRUCTURAL PIPE SUPPORTS CALCULATIONS REPORT | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 23/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/23/2025 | 08/11/2025 | 8/28/2025 | [10 empty] | R | P2
BNO-MABU-300-CS-8180-10013 |  | STRUCTURAL CABLE TRAY SUPPORTS CALCULATIONS REPORT | CS - STRUCTURAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.05-CS-STRUCTURAL | A4 | 0 | NÃO SE APLICA | 14/03/2025 |  |  |  | 0 | 22/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/22/2025 | 10/10/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-CS-8502-10001 |  | REQUEST FOR STARBOARD SUBSEA MODULE INPLACE ANALYSIS REPORT | CS - STRUCTURAL | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 14/07/2025 | BNO-MABU-300-CS-8502-10001=A01.PDF | 487,77 KB | 14/07/2025 05:13:09 | [11 empty] | IFI - ISSUED FOR INFORMATION | [11 empty] | BNO-MABU-DAE-2025-TN-10091 | 07/14/2025
BNO-MABU-300-CS-8502-10002 |  | AS-BUILT DRAWINGS FOR MR2, MR3, LACT, WATERFLOOD, PORT SUBSEA, STARBOARD SUBSEA MODULE | CS - STRUCTURAL | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 14/07/2025 | BNO-MABU-300-CS-8502-10002=A01.PDF | 736,84 KB | 14/07/2025 05:12:37 | [11 empty] | IFI - ISSUED FOR INFORMATION | [11 empty] | BNO-MABU-DAE-2025-TN-10091 | 07/14/2025
BNO-MABU-300-CS-8502-10003 |  | REQUEST FOR CENTER OF GRAVITY (COG) OF SSCB. | CS - STRUCTURAL | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A0 | 0 | ISSUED | 20/06/2025 | 16/07/2025 |  |  | 100 | 04/07/2025 | BNO-MABU-300-CS-8502-10003_A01.DOCX | 149,8 KB | 20/06/2025 04:42:40 | [11 empty] | IFI - ISSUED FOR INFORMATION | [8 empty] | BNO/EXT/MABU/00658 | 07/07/2025 |  | BNO-MABU-DAE-2025-TN10091 | 07/14/2025
BNO-MABU-300-CS-8502-10004 |  | RFI FOR VENDOR DATA OF WI TURBINE SKID | CS - STRUCTURAL | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A0 | 0 | ENGINEERING CONSOLIDATION | 25/07/2025 |  | PRISCILLAMAIOLINO.RC |  | 0 | 08/08/2025 | BNO-MABU-300-CS-8502-10004=A01.DOCX | 154,38 KB | 25/07/2025 11:00:53 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00410 | A01 | 07/25/2025 | N/A
BNO-MABU-300-EA-0980-10001-001 |  | CONTROL SYSTEM BLOCK DIAGRAM (SHOWING INTERFACE BETWEEN ELECTRICAL AND INSTRUMENTATION & AUTOMATIONSYSTEMS.) | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 22/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/22/2025 | 6/17/2025 | 6/24/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-0980-10002-001 |  | BLOCK DIAGRAM FOR HV MCC | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 18/06/2025 | 09/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 03/07/2025 | BNO-MABU-300-EA-0980-10002-001_R01.DWG | 500,88 KB | 18/06/2025 16:26:10 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/03/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00218 | R01 | 06/18/2025 | BNO-MABU-SNEPCO-2025-INC-00303 | 06/18/2025 | BNO/EXT/MABU/00663 | 07/07/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025 | R | P2
BNO-MABU-300-EA-0980-10003-001 |  | BLOCK DIAGRAM FOR ALL THE UPS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 22/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/22/2025 | 10/24/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-EA-0980-10004-001 |  | BLOCK DIAGRAM FOR SUBSEA SYSTEM PACKAGES. CHEMICAL INJECTION AND EVERY OTHER PACKAGE | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 22/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/22/2025 | 6/17/2025 | 6/24/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-0980-10005-001 |  | BLOCK DIAGRAM FOR WATER FLOOD PUMP. CHEMICAL INJECTION AND EVERY OTHER PACKAGE | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 22/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/22/2025 | 6/17/2025 | 6/24/2025 | [10 empty] | R | P2
BNO-MABU-300-EA-0980-10006-001 |  | BLOCK DIAGRAM FOR ALL THE UPS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 26/06/2025 | 18/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 04/07/2025 | BNO-MABU-300-EA-0980-10006-001_R01.DWG | 459,72 KB | 26/06/2025 17:23:50 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/04/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00218 | R01 | 06/23/2025 | BNO-MABU-SNEPCO-2025-INC-00345 | 06/26/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10084 | 07/02/2025
BNO-MABU-300-EA-1380-10001 |  | CALCULATION REPORT - LIGHTINING PROTECTION SYSTEM (LPS) | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 23/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/23/2025 | 7/25/2025 | 08/01/2025 | [10 empty] | R | P2
BNO-MABU-300-EA-1380-10002 |  | CALCULATION REPORT - ELECTRICAL LOAD BALANCE | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 04/06/2025 | 23/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 20/06/2025 | BNO-MABU-300-EA-1380-10002_R01.XLSX | 265,96 KB | 04/06/2025 10:50:37 | [5 empty] | R01 | [5 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00187 | R01 | 06/04/2025 | BNO-MABU-SNEPCO-2025-INC-00262 | 06/05/2025 | BNO/EXT/MABU/00628 | 6/23/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025 | R | P2
BNO-MABU-300-EA-1380-10003 |  | CALCULATION REPORT - LIGHTING SYSTEM | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 22/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/22/2025 | 7/24/2025 | 7/31/2025 | [10 empty] | R | P2
BNO-MABU-300-EA-2105-10001 |  | ELECTRICAL DATASHEET FOR MOTORS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 19/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/19/2025 | 7/21/2025 | 08/11/2025 | [10 empty] | R | P2
BNO-MABU-300-EA-2105-10002 |  | ELECTRICAL DATASHEET - FLOODLIGHT LUMINARIES | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 29/06/2025 | 16/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 11/07/2025 | BNO-MABU-300-EA-2105-10002_R01.XLSX | 1,04 MB | 29/06/2025 13:19:47 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00273 | R01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00353 | 06/29/2025 | BNO/EXT/MABU/00688 RECEIVED LATE FROM CPY ON 25-07-2025 | 07/25/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10084 | 07/02/2025 | R | P2
BNO-MABU-300-EA-2105-10003 |  | ELECTRICAL DATASHEET - NORMAL & EMERGENCY ESCAPE FLUORESCENT LUMINARIES | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 29/06/2025 | 16/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 11/07/2025 | BNO-MABU-300-EA-2105-10003_R01.XLSX | 1,65 MB | 29/06/2025 13:33:44 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00273 | R01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00353 | 06/29/2025 | BNO/EXT/MABU/00688 RECEIVED ON 25-07-2025 OVERDUE | 07/25/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10084 | 07/02/2025 | R | P2
BNO-MABU-300-EA-2105-10004 |  | ELECTRICAL DATASHEET - SOCKET OUTLETS & PLUGS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 26/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/26/2025 | 7/28/2025 | 08/04/2025 | [10 empty] | NR | NA
BNO-MABU-300-EA-2105-10005 |  | ELECTRICAL DATASHEET - REMOTE CONTROL STATIONS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 16/07/2025 |  | LUIS.PAMPLIN |  | 50 | 30/07/2025 | BNO-MABU-300-EA-2105-10005_R01.XLSX | 845,86 KB | 16/07/2025 09:34:59 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/30/2025 | 7/30/2025 | 08/06/2025 | BON-DAE-WESTPAQ-2025-TX-00372 | R01 | 07/16/2025 | BNO-MABU-SNEPCO-2025-INC-00408 | 07/16/2025 | [5 empty] | NR | NA
BNO-MABU-300-EA-2105-10006 |  | ELECTRICAL DATASHEET - ISOLATORS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 16/07/2025 |  | LUIS.PAMPLIN |  | 50 | 30/07/2025 | BNO-MABU-300-EA-2105-10006_R01.XLSX | 845,59 KB | 16/07/2025 09:35:08 | [11 empty] | IFR - ISSUED FOR REVIEW | 5/30/2025 | 08/01/2025 | 08/08/2025 | BON-DAE-WESTPAQ-2025-TX-00372 | RO1 | 07/16/2025 | BNO-MABU-SNEPCO-2025-INC-00408 | 07/16/2025 | [5 empty] | NR | NA
BNO-MABU-300-EA-2105-10007 |  | ELECTRICAL DATASHEET - ELECTRICA JUNCTION BOXES | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 16/07/2025 |  | LUIS.PAMPLIN | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 30/07/2025 | BNO-MABU-300-EA-2105-10007_R01.XLSX | 872,13 KB | 16/07/2025 09:35:04 | [11 empty] | IFR - ISSUED FOR REVIEW | 06/02/2025 | 08/04/2025 | 08/11/2025 | BON-DAE-WESTPAQ-2025-TX-00372 | R01 | 07/16/2025 | BNO-MABU-SNEPCO-2025-INC-00408 | 07/16/2025 | [5 empty] | R | P2
BNO-MABU-300-EA-2335-10001-001 |  | ELECTRICAL JUNCTION BOX ( EJB) TO SPCU INTERFACE HOOKUP DRAWINGS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 27/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/27/2025 | 7/29/2025 | 7/25/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-2341-10001-001 |  | INTERCONNECTION WIRING DIAGRAMS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 12/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/12/2025 | 8/14/2025 | 09/04/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-2341-10002-001 |  | HULL INTERFACE DIAGRAM UPDATE (BON-AME-3GN-E-25090-001) | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-2384-10001-001 |  | BN KEY AC ONE LINE DIAG. SHT. 1 OF 2 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 17/07/2025 | 17/07/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 100 | 24/03/2025 | BNO-MABU-300-EA-2384-10001-001_R01.DWG | 515,53 KB | 20/03/2025 06:47:58 |  | 28/03/2025 09:20:07 | R01 | IDC - INTERNAL COMMENTS | [7 empty] | IFR - ISSUED FOR REVIEW | 3/24/2025 | 7/18/2025 | 7/25/2025 | BON-DAE-WESTPAQ-2025-TX-00027 | R01 | 3/20/2025 | BNO-MABU-SNEPCO-2025-INC-00112 | 3/20/2025 | BNO/EXT/MABU/00501 | 4/17/2025 | 4 | BNO-MABU-DAE-2025-TN-10032 | 4/23/2025 | INFO | NA
BNO-MABU-300-EA-2384-10001-002 |  | BN KEY AC ONE LINE DIAG. SHT. 2 OF 2 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 17/07/2025 | 17/07/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 100 | 24/03/2025 | BNO-MABU-300-EA-2384-10001-002_R01.DWG | 491,07 KB | 20/03/2025 07:11:08 |  | 28/03/2025 09:20:07 | R01 | IDC - INTERNAL COMMENTS | [7 empty] | IFR - ISSUED FOR REVIEW | 3/24/2025 | 7/18/2025 | 7/25/2025 | BON-DAE-WESTPAQ-2025-TX-00027 | R01 | 3/20/2025 | BNO-MABU-SNEPCO-2025-INC-00112 | 3/20/2025 | BNO/EXT/MABU/00501 | 4/17/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10032 | 4/23/2025 | INFO | NA
BNO-MABU-300-EA-2384-10002-001 |  | BN KEY ONE LINE DIAGRAM | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 17/07/2025 | 18/07/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 100 | 24/03/2025 | BNO-MABU-300-EA-2384-10002-001_R01.DWG | 659,98 KB | 20/03/2025 07:12:42 |  | 28/03/2025 09:20:07 | R01 | IDC - INTERNAL COMMENTS | [7 empty] | IFR - ISSUED FOR REVIEW | 3/24/2025 | 5/26/2025 | 06/02/2025 | BON-DAE-WESTPAQ-2025-TX-00027 | R01 | 3/20/2025 | BNO-MABU-SNEPCO-2025-INC-00112 | 3/20/2025 | BNO/EXT/MABU/00501 | 4/17/2025 |  | BNO-MABU-DAE-2025-TN-10032 | 4/23/2025 | NR | NA
BNO-MABU-300-EA-2384-10003-001 |  | BN HV MCC-C (MCC-7355-D-01) ONE LINE DIAGRAM_R01 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 10/07/2025 | 30/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 23/07/2025 | BNO-MABU-300-EA-2384-10003-001_R01.DWG | 358,64 KB | 10/07/2025 08:10:02 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/23/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00336 | R01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00387 | 07/09/2025 | BNO/EXT/MABU/00716 (OVERDUE) | 07/28/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025
BNO-MABU-300-EA-2384-10004-001 |  | BN LV (SB-7446) ONE LINE DIAGRAM | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A0 | 0 | ISSUED | 10/07/2025 | 29/07/2025 |  |  | 100 | 23/07/2025 | BNO-MABU-300-EA-2384-10004-001_R01.DWG | 4,15 MB | 10/07/2025 08:10:07 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/23/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00336 | R01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00387 | 07/09/2025 | BNO/EXT/MABU/00716 (OVERDUE) | 07/28/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025
BNO-MABU-300-EA-2384-10005-001 |  | BN EMERGENCY MCC (MCC-7457-E-01) SINGLE LINE DIAGRAM | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A0 | 0 | ISSUED | 10/07/2025 | 30/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 23/07/2025 | BNO-MABU-300-EA-2384-10005-001_R01.DWG | 405,02 KB | 10/07/2025 08:10:12 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/23/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00336 | R01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00387 | 07/09/2025 | BNO/EXT/MABU/00716 (OVERDUE) | 07/28/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025
BNO-MABU-300-EA-2384-10006-001 |  | BN LV ESSENTIAL MCC (MCC-7456-E-01) SINGLE LINE DIAGRAM SHEET 2 OF 2 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A0 | 0 | ENG_IFR COMMENTS - MABU | 15/07/2025 |  | LUIS.PAMPLIN |  | 50 | 29/07/2025 | BNO-MABU-300-EA-2384-10006-001_R01.DWG | 508,98 KB | 15/07/2025 01:43:18 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00368 | R01 | 07/14/2025 | BNO-MABU-SNEPCO-2025-INC-00405 | 07/15/2025 | BNO/EXT/MABU/00716 (OVERDUE) | 07/28/2025 | CODE 3 - MINOR COMMENTS
BNO-MABU-300-EA-2580-10001 |  | PROTECTION AND METERING DIAGRAMS FOR ALL SWITCHBOARDS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 15/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/15/2025 | 7/17/2025 | 7/24/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-2901-10001 |  | AC AND DC UPS SIZING CALCULATIONS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ENG_IFR CONSOLIDATION | 15/07/2025 |  | LUIS.PAMPLIN | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 29/07/2025 | BNO-MABU-300-EA-2901-10001_R01.DOCX | 873,94 KB | 15/07/2025 01:33:04 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00366 | R01 | 07/14/2025 | BNO-MABU-SNEPCO-2025-INC-00405 | 07/15/2025 |  |  | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-EA-2901-10002 |  | CABLE SELECTION AND SIZING CALCULATION | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 18/06/2025 | 09/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 02/07/2025 | BNO-MABU-300-EA-2901-10002_R01.ZIP | 934,47 KB | 18/06/2025 03:03:42 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/02/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00211 | R01 | 06/17/2025 | BNO/MABU-SNEPCO-2025-INC-00296 | 06/18/2025 | BNO/EXT/MABU/00658 | 07/07/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10089 | 07/09/2025 | R | P2
BNO-MABU-300-EA-3323-10001 |  | TECHNICAL BID EVALUATION REPORT FOR LIGHTING LUMINARIES | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 30/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/30/2025 | 09/01/2025 | 09/08/2025 | [10 empty] | NR | NA
BNO-MABU-300-EA-3323-10002 |  | TECHNICAL BID EVALUATION REPORT FOR POWER CABLE | EA - ELECTRICAL | R02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 03/06/2025 | 20/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 17/06/2025 | BNO-MABU-300-EA-3323-10002_R02.XLSX | 253,14 KB | 03/06/2025 04:51:30 |  | 04/06/2025 04:01:13 | R02 | IFR - ISSUED FOR REVIEW | 20/06/2025 13:56:27 | R02 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/17/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00182 | R02 | 05/09/2025 | BNO-MABU-SNEPCO-2025-INC-00262 | 06/05/2025 | BNO_EXT_MABU_00626 | 06/20/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10078 | 06/20/2025 | INFO | NA
BNO-MABU-300-EA-3323-10003 |  | TECHNICAL BID EVALUATION REPORT FOR SOCKET OUTLET & PLUGS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 07/11/2025 | 09/12/2025 | 9/19/2025 | [10 empty] | NR | NA
BNO-MABU-300-EA-3323-10004 | PRJ2501-BNO-04-ELE-PT-003 | TECHNICAL BID EVALUATION FOR EXISTING DRAWER (FEEDER) - POWELL | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 15/05/2025 | 09/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 01/08/2025 | BNO-MABU-300-EA-3323-10004_R01.DOCX | 2,27 MB | 15/05/2025 11:24:15 |  | 15/05/2025 17:49:54 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 08/01/2025 | 10/03/2025 | 10/10/2025 |  |  |  | BNO-MABU-SNEPCO-2025-INC-00202 | 5/15/2025 | BNO_EXT_MABU_00576 | 06/02/2025 | CODE 4 - MAJOR COMMENTS |  |  | NR | NA
BNO-MABU-300-EA-3323-10005 |  | TECHNICAL BID EVALUATION REPORT FOR ISOLATORS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 14/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/14/2025 | 9/15/2025 | 9/22/2025 | [10 empty] | NR | NA
BNO-MABU-300-EA-3323-10006 |  | TECHNICAL BID EVALUATION REPORT FOR ELECTRICAL JUNCTION BOXES | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 10/06/2025 | 10/13/2025 | [10 empty] | NR | NA
BNO-MABU-300-EA-3323-10007 |  | TECHNICAL BID EVALUATION REPORT FOR CABLE RACKS_ GLANDS & FITTINGS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 28/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/28/2025 | 9/29/2025 | 10/06/2025 | [10 empty] | NR | NA
BNO-MABU-300-EA-3323-11004 |  | TECHNICAL BID EVALUATION REPORT FOR REMOTE CONTROL STATIONS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0
BNO-MABU-300-EA-4005-10008-001 |  | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR2 LEVEL 4 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 21/05/2025 | 06/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 15/04/2025 | BNO-MABU-300-EA-4005-10008-001_R01.DWG | 2,13 MB | 21/05/2025 03:17:16 |  | 21/05/2025 05:06:18 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 08:02:27 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/15/2025 | 7/18/2025 | 8/29/2025 | BON-DAE-WESTPAQ-2025-TX-00130 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00213 | 5/21/2025 | BNO_EXT_MABU_00587 | 06/04/2025 | CODE 4 - MAJOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-EA-4005-10009-001 |  | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR3 LEVEL 1 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 21/05/2025 | 18/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 15/04/2025 | BNO-MABU-300-EA-4005-10009-001_R01.DWG | 1,75 MB | 21/05/2025 03:19:49 |  | 21/05/2025 05:06:18 | R01 | IFR - ISSUED FOR REVIEW | 18/06/2025 05:29:42 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/15/2025 | 7/18/2025 | 8/29/2025 | BON-DAE-WESTPAQ-2025-TX-00130 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00213 | 5/21/2025 | BNO/EXT/MABU/00612 | 6/18/2025 | CODE 4 - MAJOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-EA-4005-10010-001 |  | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR5 LEVEL 1 | EA - ELECTRICAL | R02 | 3 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 13/07/2025 | 27/07/2025 |  |  | 100 | 25/07/2025 | BNO-MABU-300-EA-4005-10010-001_R02.DWG | 1,87 MB | 13/07/2025 07:25:00 |  | 21/05/2025 05:06:18 | R01 | IFR - ISSUED FOR REVIEW | 18/06/2025 05:29:43 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00358 | R02 | 07/12/2025 |  | 07/13/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10102 | 07/29/2025
BNO-MABU-300-EA-4005-10011-001 |  | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR6 LEVEL 1 | EA - ELECTRICAL | R02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 13/07/2025 | 29/07/2025 |  | ISSUED AS CODE 2 - NO COMMENTS | 100 | 25/07/2025 | BNO-MABU-300-EA-4005-10011-001_R02.DWG | 1,53 MB | 13/07/2025 07:19:42 |  | 21/05/2025 05:06:18 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 08:02:28 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00358 | R02 | 07/12/2025 | BNO/MABU-SNEPCO-2025-INC-00399 | 07/13/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10103 | 07/29/2025 |  | NA
BNO-MABU-300-EA-4005-10012-001 |  | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - SS LEVEL 1 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 21/05/2025 | 06/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 15/04/2025 | BNO-MABU-300-EA-4005-10012-001_R01.DWG | 1,66 MB | 21/05/2025 03:36:55 |  | 21/05/2025 05:06:18 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 08:02:30 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/15/2025 | 7/18/2025 | 8/29/2025 | BON-DAE-WESTPAQ-2025-TX-00130 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00213 | 5/21/2025 | BNO_EXT_MABU_00587 | 06/04/2025 | CODE 4 - MAJOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-EA-4005-10013-001 |  | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - SS LEVEL 2 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 21/05/2025 | 06/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 15/04/2025 | BNO-MABU-300-EA-4005-10013-001_R01.DWG | 1,8 MB | 21/05/2025 03:39:08 |  | 21/05/2025 05:06:18 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 08:02:31 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/15/2025 | 7/18/2025 | 8/29/2025 | BON-DAE-WESTPAQ-2025-TX-00130 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00213 | 5/21/2025 | BNO_EXT_MABU_00587 | 06/04/2025 | CODE 4 - MAJOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-EA-4005-10014-001 |  | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - VR MODULE LEVEL 1 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 21/05/2025 | 06/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 15/04/2025 | BNO-MABU-300-EA-4005-10014-001_R01.DWG | 1,63 MB | 21/05/2025 03:51:23 |  | 21/05/2025 05:06:18 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 08:02:33 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/15/2025 | 7/18/2025 | 8/29/2025 | BON-DAE-WESTPAQ-2025-TX-00130 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00213 | 5/21/2025 | BNO_EXT_MABU_00587 | 06/04/2025 | CODE 4 - MAJOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-EA-4005-10015-001 |  | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR1 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 21/05/2025 | 06/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 15/04/2025 | BNO-MABU-300-EA-4005-10015-001_R01.DWG | 1,53 MB | 21/05/2025 04:00:51 |  | 21/05/2025 09:24:18 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 08:02:34 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/15/2025 | 7/18/2025 | 8/29/2025 | BON-DAE-WESTPAQ-2025-TX-00130 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00215 | 5/21/2025 | BNO_EXT_MABU_00587 | 06/04/2025 | CODE 4 - MAJOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-EA-4005-10016-001 |  | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR2 LEVEL 1 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 21/05/2025 | 06/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 15/04/2025 | BNO-MABU-300-EA-4005-10016-001_R01.DWG | 1,64 MB | 21/05/2025 04:04:37 |  | 21/05/2025 09:24:18 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 08:02:36 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/15/2025 | 7/18/2025 | 8/29/2025 | BON-DAE-WESTPAQ-2025-TX-00130 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00215 | 5/21/2025 | BNO_EXT_MABU_00587 | 06/04/2025 | CODE 4 - MAJOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-EA-4005-10017-001 |  | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - PS LEVEL 1 | EA - ELECTRICAL | R02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 13/07/2025 | 30/07/2025 |  |  | 100 | 25/07/2025 | BNO-MABU-300-EA-4005-10017-001_R02.DWG | 2,21 MB | 13/07/2025 07:14:48 |  | 21/05/2025 09:24:18 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 08:02:37 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00358 | R02 | 07/12/2025 | BNO/MABU-SNEPCO-2025-INC-00399 | 07/13/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10105 | 07/29/2025
BNO-MABU-300-EA-4005-10018-001 |  | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR3 LEVEL 4 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 21/05/2025 | 06/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 15/04/2025 | BNO-MABU-300-EA-4005-10018-001_R01.DWG | 1,47 MB | 21/05/2025 04:09:02 |  | 21/05/2025 09:24:18 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 08:02:39 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/15/2025 | 7/18/2025 | 8/29/2025 | BON-DAE-WESTPAQ-2025-TX-00130 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00215 | 5/21/2025 | BNO_EXT_MABU_00587 | 06/04/2025 | CODE 4 - MAJOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-EA-4005-10019-001 |  | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - MR4 LEVEL 1 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 21/05/2025 | 06/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 15/04/2025 | BNO-MABU-300-EA-4005-10019-001_R01.DWG | 1,54 MB | 21/05/2025 04:13:44 |  | 21/05/2025 09:24:18 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 08:02:40 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/15/2025 | 7/18/2025 | 8/29/2025 | BON-DAE-WESTPAQ-2025-TX-00130 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00215 | 5/21/2025 | BNO_EXT_MABU_00587 | 06/04/2025 | CODE 4 - MAJOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-EA-4005-10020-001 |  | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - CC ELECTRICAL ROOM | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 21/05/2025 | 06/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 02/05/2025 | BNO-MABU-300-EA-4005-10020-001_R01.DWG | 1,58 MB | 21/05/2025 04:15:59 |  | 21/05/2025 09:24:18 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 08:02:42 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 05/02/2025 | 07/03/2025 | 8/14/2025 | BON-DAE-WESTPAQ-2025-TX-00130 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00215 | 5/21/2025 | BNO_EXT_MABU_00587 | 06/04/2025 | CODE 4 - MAJOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-EA-4005-10023-001 |  | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT-WATERFLOOD | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 21/05/2025 | 06/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 02/05/2025 | BNO-MABU-300-EA-4005-10023-001_R01.DWG | 2,82 MB | 21/05/2025 04:18:13 |  | 21/05/2025 09:24:18 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 08:02:43 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 05/02/2025 | 07/03/2025 | 7/22/2025 | BON-DAE-WESTPAQ-2025-TX-00130 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00215 | 5/21/2025 | BNO_EXT_MABU_00587 | 06/04/2025 | CODE 4 - MAJOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-EA-4005-10024-001 |  | CABLE ROUTING AND MAJOR CABLE LADDER LAYOUT - PW ELECTRICAL ROOM | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 21/05/2025 | 06/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 22/04/2025 | BNO-MABU-300-EA-4005-10024-001_R01.DWG | 1,72 MB | 21/05/2025 04:20:20 |  | 21/05/2025 09:24:18 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 08:02:45 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/22/2025 | 6/17/2025 | 6/24/2025 | BON-DAE-WESTPAQ-2025-TX-00130 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00215 | 5/21/2025 | BNO_EXT_MABU_00587 | 06/04/2025 | CODE 4 - MAJOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-EA-4018-10001-001 |  | BONGA MAIN HV SWITCHBOARD SB-7340-D-01 GENERAL ARRANGEMENT UPDATE | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 02/07/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 15/07/2025 | BNO-MABU-300-EA-4018-10001-001_R01.DWG | 965,2 KB | 02/07/2025 09:18:37 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/15/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00293 | R01 | 07/01/2025 | BNO-MABU-SNEPCO-2025-INC-00362 | 07/02/2025 | BNO_EXT_MABU_00693 | 07/17/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | INFO | NA
BNO-MABU-300-EA-4018-10002-001 |  | BONGA MAIN COMPRESSION MODULE SWITCHBOARD SB-7451 GENERAL ARRANGENT UPDATE | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 02/07/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 15/07/2025 | BNO-MABU-300-EA-4018-10002-001_R01.DWG | 1,84 MB | 02/07/2025 09:18:37 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/15/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00293 | R01 | 07/02/2025 | BNO-MABU-SNEPCO-2025-INC-00362 | 07/02/2025 |  |  | OVERDUE | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | INFO | NA
BNO-MABU-300-EA-4024-10001-001 |  | INSTALLATION DRAWINGS - GROUNDING DISTRIBUTION | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 10/07/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 23/07/2025 | BNO-MABU-300-EA-4024-10001-001_R01.DWG | 1,7 MB | 10/07/2025 07:29:24 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/23/2025 | 8/25/2025 | 09/11/2025 | BON-DAE-WESTPAQ-2025-TX-00332 | R01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00387 | 07/09/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | INFO | NA
BNO-MABU-300-EA-4024-10002-001 |  | INSTALLATION DRAWINGS - POWER DISTRIBUTION | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 10/07/2025 | 20/07/2025 |  |  | 100 | 23/07/2025 | BNO-MABU-300-EA-4024-10002-001_R01.DWG | 1,73 MB | 10/07/2025 07:28:51 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/23/2025 | 8/21/2025 | 09/09/2025 | BON-DAE-WESTPAQ-2025-TX-00332 | R01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00387 | 07/09/2025 | [5 empty] | INFO | NA
BNO-MABU-300-EA-4024-10003-001 |  | INSTALLATION DRAWINGS - LIGHTING DISTRIBUTION | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 02/07/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 15/07/2025 | BNO-MABU-300-EA-4024-10003-001_R01.DWG | 1,43 MB | 02/07/2025 08:49:52 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/15/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00292 | R01 | 07/01/2025 | BNO-MABU-SNEPCO-2025-INC-00362 | 07/02/2025 | BNO/EXT/MABU/00700 | 07/22/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10098 | 07/24/2025 | INFO | NA
BNO-MABU-300-EA-4024-10006-001 |  | LIGHTING DISTRIBUTION PLAN - MR LEVELS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 25/06/2025 | 27/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 04/07/2025 | BNO-MABU-300-EA-4024-10006-001_R01.DWG | 2,34 MB | 25/06/2025 06:16:40 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/04/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00245 | R01 | 06/24/2025 | BNO-MABU-SNEPCO-2025-INC-00325 | 06/24/2025 | BNO_EXT_MABU_00678 | 07/16/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10087/99 | 07/28/2025 | R | P2
BNO-MABU-300-EA-4024-10008-001 |  | LIGHTING DISTRIBUTION PLAN - PS LEVEL 1 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 25/06/2025 | 21/07/2025 |  |  | 100 | 04/07/2025 | BNO-MABU-300-EA-4024-10008-001_R01.DWG | 1,38 MB | 25/06/2025 08:58:01 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/04/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00245 | R01 | 06/23/2025 | BNO-MABU-SNEPCO-2025-INC-00325 | 06/24/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10096 | 07/22/2025 | R | P2
BNO-MABU-300-EA-4024-10009-001 |  | LIGHTING DISTRIBUTION PLAN - SSCB EXTERNAL | EA - ELECTRICAL | R01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 30/06/2025 | 09/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 03/07/2025 | BNO-MABU-300-EA-4024-10009-001_R01.DWG | 7,42 MB | 30/06/2025 02:20:06 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/03/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00218 | R01 | 06/18/2025 | BNO-MABU-SNEPCO-2025-INC-00303 | 06/18/2025 | BNO/EXT/MABU/00658 | 07/07/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10089 | 07/09/2025 | R | P2
BNO-MABU-300-EA-4024-10010-001 |  | BONGA MAIN ESSENTIAL SWITCHBOARD - SB-7401A/B-E-01 GENERAL ARRANGEMENT DRAWING UPDATE | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 0 | 24/04/2025 | [7 empty] | 04/06/2025 08:02:46 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/24/2025 | 6/26/2025 | 7/15/2025 | [5 empty] | BNO_EXT_MABU_00587 | 06/04/2025 | CODE 4 - MAJOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-EA-4024-10016-001 |  | GROUNDING DISTRIBUTION PLAN - MR LEVELS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 13/07/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 25/07/2025 | BNO-MABU-300-EA-4024-10016-001_R01.DWG | 4,64 MB | 13/07/2025 07:34:58 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00359 | R01 | 07/12/2025 | BNO/MABU-SNEPCO-2025-INC-00400 | 07/13/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10098 | 07/24/2025 | R | P2
BNO-MABU-300-EA-4024-10017-001 |  | GROUNDING DISTRIBUTION PLAN - PS LEVEL 1 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 11/07/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 24/07/2025 | BNO-MABU-300-EA-4024-10017-001_R01.DWG | 5,98 MB | 11/07/2025 00:14:32 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/24/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00341 | R01 | 07/10/2025 | BNO-MABU-SNEPCO-2025-INC-00390 | 07/10/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | R | P2
BNO-MABU-300-EA-4024-10018-001 |  | GROUNDING DISTRIBUTION PLAN - VR MODULE LEVEL 1 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/25/2025 | 6/27/2025 | 07/04/2025 | [10 empty] | R | P2
BNO-MABU-300-EA-4024-10019-001 |  | LIGHTING DISTRIBUTION PLAN - VR MODULE LEVEL 1 | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 23/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/23/2025 | 7/25/2025 | 08/01/2025 | [10 empty] | R | P2
BNO-MABU-300-EA-4025-10001-001 |  | UPDATE OF EXISTING LIGHTING AND SMALL POWER LAYOUT | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 23/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/23/2025 | 7/25/2025 | 8/15/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-4180-10001-001 |  | CABLE TERMINATION DETAILS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 14/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/14/2025 | 9/15/2025 | 9/22/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-4180-10002-001 |  | LV CABLE ROUTING LAYOUT HULL TO SSCB | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 02/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 05/02/2025 | 07/03/2025 | 07/10/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-4180-10003-001 |  | POWER LAYOUT (FOR OUTDOOR SOCKET) | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/09/2025 | 08/11/2025 | 09/01/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-4180-10004-001 |  | ELECTRICAL SYSTEM REPORT AUTOMATION ARCHITECTURE | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/18/2025 | 9/19/2025 | 9/26/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-4306-10001 |  | ELECTRICAL MTO | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/11/2025 | 10/13/2025 | 10/20/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-4306-10002 |  | BULK MATERIALS MTO | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/16/2025 | 9/17/2025 | 10/08/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-4306-10003 |  | CABLE LADDER RACK ISOMETRICS AND MTO FOR ALL NEW BONGA NORTH CABLE TRAYS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 07/04/2025 | 09/05/2025 | 9/26/2025 | [10 empty] | NR | NA
BNO-MABU-300-EA-4306-10004 |  | SPARE PART LIST | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 9/19/2025 | [10 empty] | NR | NA
BNO-MABU-300-EA-4308-10001 |  | ELECTRICAL CABLE LIST | EA - ELECTRICAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 13/07/2025 | 21/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 24/07/2025 | BNO-MABU-300-EA-4308-10001_A01.XLSX | 419,7 KB | 13/07/2025 06:35:57 | [11 empty] | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00360 | A01 | 07/12/2025 | BNO/MABU-SNEPCO-2025-INC-00398 | 07/13/2025 | BNO/EXT/MABU/00658 | 07/07/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10096 | 07/22/2025
BNO-MABU-300-EA-4308-10002 |  | LIST OF RECOMMENDED VENDORS (FOR COMPANY REVIEW) | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 22/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/22/2025 | 10/24/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-EA-4308-10003 |  | CABLE CUTTING PLAN | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 27/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/27/2025 | 7/29/2025 | 7/25/2025
BNO-MABU-300-EA-4329-10001 |  | ELECTRICAL LOAD LIST | EA - ELECTRICAL | R02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 02/07/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 11/07/2025 | BNO-MABU-300-EA-4329-10001_R02.XLSX | 767,98 KB | 29/06/2025 13:42:19 |  |  |  |  | 16/07/2025 11:02:47 | R02 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00273 | R02 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00353 | 06/29/2025 | BNO_EXT_MABU_00684 | 07/14/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | R | P2
BNO-MABU-300-EA-4380-10004 |  | CABLE TRAY UTILISATION SCHEDULE | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 20/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/20/2025 | 8/22/2025 | 8/29/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-4380-10005 |  | ELECTRICAL CABLE SCHEDULE | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 14/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/14/2025 | 6/16/2025 | 07/03/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-4380-10006 |  | PENETRATION SCHEDULE | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 07/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 05/07/2025 | 07/09/2025 | 8/20/2025 | [10 empty] | R | P2
BNO-MABU-300-EA-4380-10007 |  | PROTECTION SCHEME & RELAY SETTING SCHEDULES | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | R | P2
BNO-MABU-300-EA-4380-10008 |  | DISTRIBUTION BOARD SCHEDULE FOR ALL THE DB | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 12/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/12/2025 | 8/14/2025 | 09/04/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-4380-10009 |  | LV SWITCHGEAR SCHEDULE UPDATE FOR BM | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 23/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/23/2025 | 7/25/2025 | 8/15/2025 | [10 empty] | NR | NA
BNO-MABU-300-EA-4380-10010 |  | HV SWITCHGEAR SCHEDULE UPDATE FOR BM | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 23/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/23/2025 | 7/25/2025 | 8/15/2025 | [10 empty] | NR | NA
BNO-MABU-300-EA-4380-10011 |  | CABLE TRANSIT AND PENTRATION SCHEDULE | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-4380-10012 |  | CONTROL. ALARM AND MONITORING TABLE | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 23/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/23/2025 | 7/25/2025 | 08/01/2025 | [10 empty] | R | P2
BNO-MABU-300-EA-4380-10013 |  | EX REGISTER | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 07/09/2025 | 09/10/2025 | 10/01/2025 | [10 empty] | R | P2
BNO-MABU-300-EA-5680-10001 |  | ELECTRICAL SYSTEM MEMORANDUM | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/15/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-7180-10003 |  | EQUIPMENT VENDOR DOSSIERS (INCLUDING FAT REPORTS) | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/06/2025 | 10/08/2025 | 10/15/2025 | [10 empty] | NR | NA
BNO-MABU-300-EA-7180-10005 |  | SAFOP REPORT | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 21/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/21/2025 | 9/22/2025 | 9/29/2025 | [10 empty] | R | P2
BNO-MABU-300-EA-7180-10006 |  | ARC-FLASH HAZARD REPORT | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 22/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/22/2025 | 9/23/2025 | 9/30/2025 | [10 empty] | R | P2
BNO-MABU-300-EA-7180-10008 |  | POWER SYSTEM ANALYSIS REPORT UPDATE | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/11/2025 | 10/13/2025 | 10/20/2025 | [10 empty] | R | P2
BNO-MABU-300-EA-7180-10009 |  | ESSENTIAL GENERATOR ADEQUACY CHECK REPORT | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | ISSUED | 19/06/2025 | 09/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 03/07/2025 | BNO-MABU-300-EA-7180-10009_R01.DOCX | 909,91 KB | 19/06/2025 09:52:30 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/03/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00224 | R01 | 06/19/2025 | BNO-MABU-SNEPCO-2025-INC-00305 | 06/19/2025 | BNO/EXT/MABU/00663 | 07/07/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10089 | 07/09/2025 | INFO | NA
BNO-MABU-300-EA-7180-10011 |  | FAULT RECOVERY/SYSTEM DYNAMIC STABILITY UNDER 3-PHASE FAULT CONDITIONS REPORT | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 07/09/2025 | 09/10/2025 | 9/17/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-7303-10001 |  | MATERIAL REQUISITION FOR POWER CABLE | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 15/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/15/2025 | 6/17/2025 | 07/04/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-7303-10002 |  | REQUISITION FOR CABLES AND GLANDS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 15/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/15/2025 | 6/17/2025 | 7/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-EA-7303-10003 |  | REQUISITION FOR ELECTRICAL BULK MATERIALS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 20/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/20/2025 | 8/22/2025 | 09/12/2025 | [10 empty] | NR | NA
BNO-MABU-300-EA-7303-10004 |  | REQUISITION FOR CABLE RACK AND FITTINGS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 07/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 05/07/2025 | 07/09/2025 | 8/20/2025 | [10 empty] | NR | NA
BNO-MABU-300-EA-7770-10001 |  | SPECIFICATION FOR ELECTRICAL EQUIPMENT SIZING REVALIDATION | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 26/05/2025 | 17/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 06/06/2025 | BNO-MABU-300-EA-7770-10001_R01.DOCX | 866,86 KB | 26/05/2025 03:08:37 |  | 26/05/2025 04:08:53 | R01 | IFR - ISSUED FOR REVIEW | 18/06/2025 05:21:28 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00145 | R01 | 5/23/2025 | BNO-MABU-SNEPCO-2025-INC-00226 | 05/26/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10102 | 07/29/2025 | R | P2
BNO-MABU-300-EA-7771-10001 |  | SPECIFICATION FOR POWER DISTRIBUTION AND SYSTEM OPERATION PHILOSOPHY | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 14/05/2025 | 20/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 04/04/2025 | BNO-MABU-300-EA-7771-10001_R01.DOCX | 799,8 KB | 14/05/2025 09:19:54 |  | 14/05/2025 12:04:44 | R01 | IFR - ISSUED FOR REVIEW | 03/06/2025 04:16:11 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 04/04/2025 | 06/06/2025 | 7/18/2025 | BON-DAE-WESTPAQ-2025-TX-00105 | R01 | 5/14/2025 | BNO-MABU-SNEPCO-2025-INC-00198 | 5/14/2025 | BNO_EXT_MABU_00579 | 06/02/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10078 | 06/20/2025 | R | P2
BNO-MABU-300-EA-7771-10002 |  | SPECIFICATION FOR ELECTRICAL POWER CABLE | EA - ELECTRICAL | A01 | 3 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 23/07/2025 |  | LUIS.PAMPLIN |  | 50 | 06/08/2025 | BNO-MABU-300-EA-7771-10002_A01.DOCX | 792,13 KB | 23/07/2025 08:43:01 |  | 02/06/2025 08:17:26 | R02 | IFR - ISSUED FOR REVIEW | 18/06/2025 05:21:30 | R02 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00398 | A01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00435 | 07/23/2025 | [5 empty] | R | P2
BNO-MABU-300-EA-7771-10003 |  | SPECIFICATION FOR ELECTRIC MOTOR | EA - ELECTRICAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 02/06/2025 | 11/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-EA-7771-10003_A01.DOCX | 830,74 KB | 02/06/2025 04:33:00 |  | 02/06/2025 08:17:26 | A01 | IFA - ISSUED FOR APPROVAL | 03/06/2025 04:43:45 | A01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00171 | A01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00254 | 06/02/2025 | BNO_EXT_MABU_00580 | 06/03/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-EA-7771-10004 |  | SPECIFICATION FOR ELECTRICAL EQUIPMENT-PACKAGED | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 20/05/2025 | 17/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 15/04/2025 | BNO-MABU-300-EA-7771-10004_R01.DOCX | 824,21 KB | 20/05/2025 10:45:18 |  | 21/05/2025 05:06:18 | R01 | IFR - ISSUED FOR REVIEW | 18/06/2025 05:21:31 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/15/2025 | 6/17/2025 | 7/29/2025 | BON-DAE-WESTPAQ-2025-TX-00124 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00213 | 5/21/2025 | BNO_EXT_MABU_00611 | 06/18/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10100 | 07/28/2025 | R | P2
BNO-MABU-300-EA-7771-10005 |  | SPECIFICATION FOR ELECTRICAL DESIGN PHILOSOPHY | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 14/05/2025 | 17/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 15/04/2025 | BNO-MABU-300-EA-7771-10005_R01.DOCX | 814,97 KB | 14/05/2025 09:25:26 |  | 14/05/2025 12:04:44 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 4/15/2025 | 6/17/2025 | 7/29/2025 | BON-DAE-WESTPAQ-2025-TX-00105 | R01 | 5/14/2025 | BNO-MABU-SNEPCO-2025-INC-00198 | 5/14/2025 | BNO/EXT/MABU/00658 | 07/07/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10075_Reuploaded | 06/24/2025 | R | P2
BNO-MABU-300-EA-7771-10006 |  | CONSTRUCTION AND INSTALLATION SPECIFICATION | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 28/07/2025 |  | LUIS.PAMPLIN |  | 50 | 11/08/2025 | BNO-MABU-300-EA-7771-10006_R01.DOCX | 831,54 KB | 28/07/2025 06:18:16 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/01/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00419 | R01 | 07/28/2025 | BNO/MABU-SNEPCO-2025-INC-00452 | 07/28/2025 | [5 empty] | NR | NA
BNO-MABU-300-EA-7771-10007 |  | SPECIFICATION FOR LV SWITCHGEAR | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 20/05/2025 | 17/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 04/04/2025 | BNO-MABU-300-EA-7771-10007_R01.DOCX | 832,72 KB | 20/05/2025 10:47:48 |  | 21/05/2025 05:06:18 | R01 | IFR - ISSUED FOR REVIEW | 18/06/2025 05:21:33 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 04/04/2025 | 06/06/2025 | 7/18/2025 | BON-DAE-WESTPAQ-2025-TX-00124 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00213 | 5/21/2025 | BNO_EXT_MABU_00611 | 06/18/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10075_Reuploaded | 06/24/2025 | R | P2
BNO-MABU-300-EA-7771-10008 |  | SPECIFICATION FOR HV SWITCHGEAR | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 14/05/2025 | 17/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 17/03/2025 | BNO-MABU-300-EA-7771-10008_R01.DOCX | 828,8 KB | 14/05/2025 09:36:59 |  | 14/05/2025 12:04:44 | R01 | IFR - ISSUED FOR REVIEW | 18/06/2025 05:21:34 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 3/17/2025 | 5/19/2025 | 6/30/2025 | BON-DAE-WESTPAQ-2025-TX-00105 | R01 | 5/14/2025 | BNO-MABU-SNEPCO-2025-INC-00198 | 5/14/2025 | BNO_EXT_MABU_00611 | 06/18/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10075_Reuploaded | 06/24/2025 | R | P2
BNO-MABU-300-EA-7771-10009 |  | SPECIFICATION FOR AC UPS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 20/05/2025 | 17/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 04/04/2025 | BNO-MABU-300-EA-7771-10009_R01.DOCX | 838,41 KB | 20/05/2025 10:50:48 |  | 21/05/2025 05:06:18 | R01 | IFR - ISSUED FOR REVIEW | 18/06/2025 05:21:35 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 04/04/2025 | 06/06/2025 | 7/18/2025 | BON-DAE-WESTPAQ-2025-TX-00124 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00213 | 5/21/2025 | BNO_EXT_MABU_00611 | 06/18/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10075_Reuploaded | 06/24/2025 | R | P2
BNO-MABU-300-EA-7771-10010 |  | SPECIFICATION FOR DC UPS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 24/05/2025 | 17/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 06/06/2025 | BNO-MABU-300-EA-7771-10010_R01.DOCX | 825,84 KB | 24/05/2025 00:34:49 |  | 26/05/2025 04:08:53 | R01 | IFR - ISSUED FOR REVIEW | 18/06/2025 05:21:37 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00139 | R01 | 05/27/2025 | BNO-MABU-SNEPCO-2025-INC-00226 | 05/26/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10075_Reuploaded | 06/24/2025 | R | P2
BNO-MABU-300-EA-7771-10011 |  | SPECIFICATION FOR TRANSFORMER | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 20/06/2025 | 20/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 10/03/2025 | BNO-MABU-300-EA-7771-10011_R01.DOCX | 811,24 KB | 14/05/2025 09:40:58 |  | 14/05/2025 12:04:44 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFA - ISSUED FOR APPROVAL | 03/10/2025 | 05/12/2025 | 6/23/2025 | BON-DAE-WESTPAQ-2025-TX-00105 | R01 | 5/14/2025 | BNO-MABU-SNEPCO-2025-INC-00198 | 5/14/2025 | BNO_EXT_MABU_00585 | 06/04/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10078 | 06/20/2025 | R | P2
BNO-MABU-300-EA-7771-10012 |  | SPECIFICATION FOR LV DISTRIBUTION BOARD PANELS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A0 | 0 | ISSUED | 02/06/2025 | 18/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-EA-7771-10012_R01.DOCX | 815,49 KB | 02/06/2025 02:53:12 |  | 02/06/2025 08:17:26 | R01 | IFR - ISSUED FOR REVIEW | 18/06/2025 05:21:38 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/13/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00164 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00254 | 06/02/2025 | BNO_EXT_MABU_00611 | 06/18/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10078 | 06/20/2025
BNO-MABU-300-EA-8251-10001 |  | SAFOP TERMS OF REFERENCE | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | ISSUED | 17/07/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 02/07/2025 | BNO-MABU-300-EA-8251-10001_R01.DOCX | 1,9 MB | 18/06/2025 04:53:23 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/02/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00211 | R01 | 06/18/2025 | BNO-MABU-SNEPCO-2025-INC-00296 | 06/18/2025 | BNO/EXT/MABU/00658 | 07/07/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | INFO | NA
BNO-MABU-300-EA-8260-10001 |  | ELECTRICAL STUDIES REPORT - LOAD FLOW | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 14/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/14/2025 | 9/15/2025 | 9/22/2025 | [10 empty] | R | P2
BNO-MABU-300-EA-8260-10002 |  | ELECTRICAL STUDIES REPORT - HARMONIC DISTORTION | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/16/2025 | 9/17/2025 | 9/24/2025 | [10 empty] | INFO | NA
BNO-MABU-300-EA-8260-10003 |  | ELECTRICAL STUDIES REPORT - SHORT-CIRCUIT CURRENTS | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 24/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/24/2025 | 9/25/2025 | 10/02/2025 | [10 empty] | R | P2
BNO-MABU-300-EA-8260-10004 |  | ELECTRICAL STUDIES REPORT - PROTECTION COORDINATION | EA - ELECTRICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.06-EA-ELECTRICAL | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 29/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/29/2025 | 9/30/2025 | 10/07/2025 | [10 empty] | R | P2
BNO-MABU-300-EA-8502-10001 |  | DED LIGHTNING PROTECTION CALCULATIONS | EA - ELECTRICAL | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A4 | 0 | ISSUED | 29/06/2025 | 11/07/2025 |  |  | 100 | 11/07/2025 | BNO-MABU-300-EA-8502-10001=A01.DOCX | 172,51 KB | 29/06/2025 10:23:37 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00275 | A01 | 07/11/2025 | N/A |  | N/A |  |  | BNO-MABU-DAE-2025-TN-10090 | 07/10/2025
BNO-MABU-300-EA-8502-10002 |  | DED UPS UTILITY CONSUMPTION LIST | EA - ELECTRICAL | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A4 | 0 | ISSUED | 09/07/2025 | 14/07/2025 |  |  | 100 | 23/07/2025 | BNO-MABU-300-EA-8502-10002=A01.DOCX | 174,44 KB | 09/07/2025 05:36:57 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00329 | A01 | 07/09/2025 | [5 empty] | BNO-MABU-DAE-2025-TN-10091 | 07/14/2025
BNO-MABU-300-HS-7411-10001 |  | DROPPED OBJECT STUDY REPORT | HS - SAFETY | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.11-HS-SAFETY | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 02/07/2025 |  | O.UGWUEGBU |  | 50 | 15/07/2025 | BNO-MABU-300-HS-7411-10001_R01.DOCX | 1,46 MB | 02/07/2025 02:55:53 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/15/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00289 | R01 | 07/01/2025 | BNO-MABU-SNEPCO-2025-INC-00362 | 07/02/2025 | BNO/EXT/MABU/00705/706/712 (OVERDUE) | 07/23/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-HS-7411-10002 |  | BOWTIE REVIEW TERMS OF REFERENCE | HS - SAFETY | A02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.11-HS-SAFETY | A4 | 0 | ENG_IFR COMMENTS - MABU | 12/07/2025 |  | O.UGWUEGBU |  | 85 | 25/07/2025 | BNO-MABU-300-HS-7411-10002_A02.DOCX | 1,78 MB | 12/07/2025 04:46:38 |  | 15/05/2025 04:45:15 | A01 | IFA - ISSUED FOR APPROVAL | 04/04/2025 13:43:26 | R01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED | 04/01/2025 | 5/20/2025 | 07/25/2025 | BON-DAE-WESTPAQ-2025-TX-00344 | A02 | 07/11/2025 | BNO-MABU-SNEPCO-2025-INC-00395 | 07/11/2025 | [5 empty] | INFO | NA
BNO-MABU-300-HS-7411-10003 |  | BOWTIE REVIEW REPORT | HS - SAFETY | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.11-HS-SAFETY | A4 | 0 | ENG_IFR COMMENTS - MABU | 02/07/2025 |  | O.UGWUEGBU |  | 50 | 15/07/2025 | BNO-MABU-300-HS-7411-10003_A01.DOCX | 2,21 MB | 02/07/2025 17:00:24 |  | 05/05/2025 06:52:22 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFA - ISSUED FOR APPROVAL | 4/28/2025 | 07/15/2025 |  | BON-DAE-WESTPAQ-2025-TX-00288 | A01 | 07/01/2025 | BNO-MABU-SNEPCO-2025-INC-00364 | 07/02/2025 | BNO/EXT/MABU/00705/712 (OVERDUE) | 07/23/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-HX-0580-10001 |  | NOISE STUDY REPORT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 05/09/2025 | 6/27/2025 | 7/16/2025 | [10 empty] | INFO | NA
BNO-MABU-300-HX-0704-10002 |  | FIRE AND EXPLOSION ANALYSIS (FEA) REPORT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 05/09/2025 | 6/27/2025 | 7/16/2025 | [10 empty] | R | P2
BNO-MABU-300-HX-0709-10003 |  | QUANTITATIVE RISK ANALYSIS (QRA) REPORT - UPDATE DETAIL PHASE | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/16/2025 | 07/04/2025 | 7/23/2025 | [10 empty] | R | P2
BNO-MABU-300-HX-0780-10005 |  | SIMOPS REPORT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 03/11/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 11/03/2025 | 12/15/2025 | 12/29/2025 | [10 empty] | R | P2
BNO-MABU-300-HX-1212-10001 |  | FIRE WATER DEMAND VERIFICATION - CALCULATION NOTES | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 26/05/2025 |  | O.UGWUEGBU | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 06/06/2025 | BNO-MABU-300-HX-1212-10001_R01.DOC | 2,22 MB | 26/05/2025 02:32:35 |  | 27/05/2025 09:45:07 | R01 | IFR - ISSUED FOR REVIEW | 17/06/2025 10:03:37 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00143 | R01 | 5/23/2025 | BNO-MABU-SNEPCO-2025-INC-00235 | 5/27/2025 | BNO/EXT/MABU/00597 | 06/10/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-HX-1222-10001 |  | DELUGE SYSTEM HYDRAULIC CALCULATION NOTES | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 29/07/2025 |  | O.UGWUEGBU |  | 50 | 12/08/2025 | BNO-MABU-300-HX-1222-10001_R01.DOCX | 1,18 MB | 29/07/2025 08:23:01 | [11 empty] | IFR - ISSUED FOR REVIEW | 06/09/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00421 | R01 | 07/29/2025 | BNO/MABU-SNEPCO-2025-INC-00460 | 07/29/2025 | [5 empty] | R | P2
BNO-MABU-300-HX-1601-10005 |  | HAZARDOUS AREA CLASSIFICATION SCHEDULE | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ISSUED | 13/06/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 27/06/2025 | BNO-MABU-300-HX-1601-10005_R01.DOCX | 840,35 KB | 13/06/2025 09:25:19 | [11 empty] | IFR - ISSUED FOR REVIEW | 06/27/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00205 | R01 | 06/13/2025 | BNO/MABU-SNEPCO-2025-INC-00301 | 06/18/2025 | BNO/EXT/MABU/00658 | 07/07/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10097 | 07/24/2025 | R | P2
BNO-MABU-300-HX-2318-10001 |  | EMERGENCY EVACUATION RESCUE ANALYSIS (EERA) REPORT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ISSUED | 03/06/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 17/06/2025 | BNO-MABU-300-HX-2318-10001_R01.DOC | 2,25 MB | 03/06/2025 03:36:34 |  | 03/06/2025 09:42:33 | R01 | IFR - ISSUED FOR REVIEW | 02/07/2025 06:07:29 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00180 | R01 | 06/03/2025 | BNO-MABU-SNEPCO-2025-INC-00259 | 06/03/2025 | BNO/EXT/MABU/00649 | 07/01/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10094 | 07/18/2025 | R | P2
BNO-MABU-300-HX-2334-10001-001 |  | HAZARDOUS AREA CLASSIFICATION MAIN DECK | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/16/2025 | 07/04/2025 | 7/23/2025 | [10 empty] | R | P2
BNO-MABU-300-HX-2334-10002-001 |  | HAZARDOUS AREA CLASSIFICATION UPPER DECK | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/16/2025 | 07/04/2025 | 7/23/2025 | [10 empty] | R | P2
BNO-MABU-300-HX-2334-10003-001 |  | HAZARDOUS AREA CLASSIFICATION UPPER DECK - AFT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 10/07/2025 |  | O.UGWUEGBU |  | 50 | 23/07/2025 | BNO-MABU-300-HX-2334-10003-001_R01.DWG | 3,66 MB | 10/07/2025 08:40:07 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/23/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00331 | R01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00387 | 07/09/2025 | [5 empty] | R | P2
BNO-MABU-300-HX-2334-10004-001 |  | HAZARDOUS AREA CLASSIFICATION UPPER DECK - MID AFT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 10/07/2025 |  | O.UGWUEGBU |  | 50 | 23/07/2025 | BNO-MABU-300-HX-2334-10004-001_R01.DWG | 5,17 MB | 10/07/2025 08:40:15 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/23/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00331 | R01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00387 | 07/09/2025 | [5 empty] | R | P2
BNO-MABU-300-HX-2334-10004-002 |  | HAZARDOUS AREA CLASSIFICATION UPPER DECK - MID AFT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 10/07/2025 |  | O.UGWUEGBU |  | 50 | 23/07/2025 | BNO-MABU-300-HX-2334-10004-002_R01.DWG | 4,83 MB | 10/07/2025 08:40:26 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/23/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00331 | R01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00387 | 07/09/2025
BNO-MABU-300-HX-2334-10006-001 |  | HAZARDOUS AREA CLASSIFICATION MAIN DECK - MID AFT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 10/07/2025 |  | O.UGWUEGBU |  | 50 | 23/07/2025 | BNO-MABU-300-HX-2334-10006-001_R01.DWG | 3,98 MB | 10/07/2025 08:40:30 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/23/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00331 | R01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00387 | 07/09/2025 | [5 empty] | R | P2
BNO-MABU-300-HX-2334-10006-002 |  | HAZARDOUS AREA CLASSIFICATION MAIN DECK - MID AFT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 10/07/2025 |  | O.UGWUEGBU |  | 50 | 23/07/2025 | BNO-MABU-300-HX-2334-10006-002_R01.DWG | 3,59 MB | 10/07/2025 08:40:21 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/23/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00331 | R01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00387 | 07/09/2025
BNO-MABU-300-HX-2334-10007-001 |  | HAZARDOUS AREA CLASSIFICATION DRAWING MAIN DECK - MID AFT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/16/2025 | 07/04/2025 | 7/23/2025 | [10 empty] | R | P2
BNO-MABU-300-HX-2334-10008-001 |  | HAZARDOUS AREA CLASSIFICATION DRAWING - UPPER DECK | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/16/2025 | 07/04/2025 | 7/23/2025 | [10 empty] | R | P2
BNO-MABU-300-HX-3323-10001 |  | TBE FOR SAFETY ITEMS | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | NR | NA
BNO-MABU-300-HX-4180-10004-001 |  | SAFETY PLAN - SSCB LAYOUT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/16/2025 | 07/04/2025 | 7/23/2025 | [10 empty] | NR | NA
BNO-MABU-300-HX-4180-10006-001 |  | ESCAPE ROUTE & SAFETY EQUIPMENT LAYOUT - CARGO DECK (EL.100000) AFT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A3 | 0 | ENG_IFR CONSOLIDATION | 17/07/2025 |  | O.UGWUEGBU |  | 50 | 04/07/2025 | BNO-MABU-300-HX-4180-10006-001_R01.DWG | 676,06 KB | 25/06/2025 09:15:14 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/04/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00246 | R01 | 06/23/2025 | BNO-MABU-SNEPCO-2025-INC-00325 | 06/24/2025 | BNO/EXT/MABU/00670 | 07/10/2025 | OVERDUE |  |  | R | P1
BNO-MABU-300-HX-4180-10007-001 |  | ESCAPE ROUTE & SAFETY EQUIPMENT LAYOUT- CARGO DECK (EL.100000) FORWARD | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/16/2025 | 07/04/2025 | 7/23/2025 | [10 empty] | R | P1
BNO-MABU-300-HX-4180-10008-001 |  | ESCAPE ROUTE & SAFETY EQUIPMENT LAYOUT- MAIN DECK (EL.105182) AFT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 25/06/2025 |  | O.UGWUEGBU |  | 50 | 04/07/2025 | BNO-MABU-300-HX-4180-10008-001_R01.DWG | 1,06 MB | 25/06/2025 09:28:00 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/04/2025 |  |  |  | BON-DAE-WESTPAQ-2025-TX-00246 | 06/23/2025 | BNO-MABU-SNEPCO-2025-INC-00325_24-06-2025 | 06/24/2025 | BNO/EXT/MABU/00670 | 07/10/2025 | OVERDUE |  |  | R | P1
BNO-MABU-300-HX-4180-10009-001 |  | ESCAPE ROUTE & SAFETY EQUIPMENT LAYOUT- MAIN DECK (EL.105182) FORWARD | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/16/2025 | 07/04/2025 | 7/23/2025 | [10 empty] | R | P1
BNO-MABU-300-HX-4180-10010-001 |  | ESCAPE ROUTE & SAFETY EQUIPMENT LAYOUT- UPPER DECK (EL. 112802) AFT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A3 | 0 | ENG_IFR COMMENTS - MABU | 25/06/2025 |  | O.UGWUEGBU |  | 50 | 04/07/2025 | BNO-MABU-300-HX-4180-10010-001_R01.DWG | 1,86 MB | 25/06/2025 09:31:59 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/04/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00246 | R01 | 06/23/2025 | BNO-MABU-SNEPCO-2025-INC-00325 | 06/24/2025 | BNO_EXT_MABU_00682 | 07/15/2025 | OVERDUE |  |  | R | P1
BNO-MABU-300-HX-4180-10011-001 |  | ESCAPE ROUTE & SAFETY EQUIPMENT LAYOUT- UPPER DECK (EL. 112802) FORWARD | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/16/2025 | 07/04/2025 | 7/23/2025 | [10 empty] | R | P1
BNO-MABU-300-HX-4301-10001 |  | ASSUMPTION REGISTER | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ENG_IFR CONSOLIDATION | 20/06/2025 |  | O.UGWUEGBU |  | 50 | 03/07/2025 | BNO-MABU-300-HX-4301-10001_R01.DOC | 2,32 MB | 20/06/2025 04:27:56 | [11 empty] | IFR - ISSUED FOR REVIEW | 06/19/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00222 | R01 | 06/19/2025 | BNO-MABU-SNEPCO-2025-INC-00304 | 06/19/2025 | BNO/EXT/MABU/00664 | 07/07/2025 | OVERDUE |  |  | INFO | NA
BNO-MABU-300-HX-5798-10001 |  | HAZARD EVALUATION AND RISK MANAGEMENT PLAN | HX - HSE | A02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 22/07/2025 |  | THEODORE_EBUNOHA |  | 85 | 04/08/2025 | BNO-MABU-300-HX-5798-10001_A02.DOCX | 1,32 MB | 22/07/2025 02:42:10 |  | 28/03/2025 09:55:56 | R01 | IFR - ISSUED FOR REVIEW | 14/05/2025 05:14:33 | A01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED | 04/01/2025 | 06/03/2025 | 6/24/2025 | BON-DAE-WESTPAQ-2025-TX-00394 | A02 | 07/22/2025 | BNO/MABU-SNEPCO-2025-INC-00430 | 07/22/2025 | [5 empty] | R | P2
BNO-MABU-300-HX-5880-10001 |  | HEALTH SAFETY SECURITY ENVIRONMENT PLAN | HX - HSE | A02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 22/07/2025 |  | K.AKPABIO |  | 85 | 04/08/2025 | BNO-MABU-300-HX-5880-10001_A02.DOCX | 1,58 MB | 22/07/2025 02:44:54 |  | 31/03/2025 14:35:37 | R01 | IFR - ISSUED FOR REVIEW | 20/05/2025 03:36:09 | A01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED | 2/28/2025 | 05/02/2025 | 5/23/2025 | BON-DAE-WESTPAQ-2025-TX-00394 | A02 | 07/22/2025 | BNO-MABU-SNEPCO-2025-INC-00430 | 07/22/2025 | [5 empty] | R | P2
BNO-MABU-300-HX-6613-10002 |  | ACTION TRACKING REGISTER | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 9/22/2025 | 10/09/2025 | [10 empty] | NR | NA
BNO-MABU-300-HX-6873-10003 |  | HAZID REPORT (DED) | HX - HSE | A01 | 3 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 29/06/2025 |  | O.UGWUEGBU |  | 50 | 11/07/2025 | BNO-MABU-300-HX-6873-10003_A01.DOCX | 2,72 MB | 29/06/2025 16:43:16 |  | 05/05/2025 06:52:22 | R01 | IFR - ISSUED FOR REVIEW | 20/05/2025 03:36:10 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 4/25/2025 | 07/11/2025 |  | BON-DAE-WESTPAQ-2025-TX-00264 | A01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00355 | 06/27/2025 | BNO_EXT_MABU_00687 | 07/16/2025 | OVERDUE |  |  | R | P1
BNO-MABU-300-HX-6873-10004 |  | HAZID CLOSE OUT REPORT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ISSUED | 29/05/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 12/06/2025 | BNO-MABU-300-HX-6873-10004_R01.DOCX | 876,01 KB | 29/05/2025 10:23:19 |  | 29/05/2025 16:10:31 | R01 | IFR - ISSUED FOR REVIEW | 24/06/2025 09:27:38 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00159 | R01 | 05/29/2025 | BNO-MABU-SNEPCO-2025-INC-00244 | 5/29/2025 | BNO/EXT/MABU/00638 | 6/24/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10094 | 07/18/2025
BNO-MABU-300-HX-6874-10001 |  | GAS DISPERSION MODELLING STUDY REPORT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 05/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/05/2025 | 9/23/2025 | 10/10/2025 | [10 empty] | R | P2
BNO-MABU-300-HX-6875-10001 |  | SAFOP CLOSE-OUT REPORT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | CANCELADO |  |  |  |  | 0 | 16/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS
BNO-MABU-300-HX-6875-10005 |  | INTEGRATED HAZOP CLOSEOUT REPORT - UPDATE | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 23/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/23/2025 | 07/11/2025 | 7/30/2025 | [10 empty] | R | P1
BNO-MABU-300-HX-6875-10006 |  | HAZOP - TERMS OF REFERENCE | HX - HSE | A02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 12/07/2025 |  | O.UGWUEGBU |  | 50 | 25/07/2025 | BNO-MABU-300-HX-6875-10006_A02.DOCX | 1,54 MB | 12/07/2025 04:57:07 |  | 22/05/2025 05:42:37 | A01 | IFA - ISSUED FOR APPROVAL | [7 empty] | AFC/AFU - APPROVED | 04/08/2025 | 5/27/2025 | 07/25/2025 | BON-DAE-WESTPAQ-2025-TX-00344 | A02 | 07/11/2025 | BNO-MABU-SNEPCO-2025-INC-00395 | 07/11/2025 | [5 empty] | R | P2
BNO-MABU-300-HX-6875-10007 |  | HAZOP REPORT (DED) | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 10/07/2025 |  | O.UGWUEGBU |  | 50 | 23/07/2025 | BNO-MABU-300-HX-6875-10007_R01.DOCX | 5,28 MB | 10/07/2025 07:19:56 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/09/2025 | 8/27/2025 | 9/15/2025 | BON-DAE-WESTPAQ-2025-TX-00333 | R01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00387 | 07/09/2025 | [5 empty] | R | P1
BNO-MABU-300-HX-6875-10008 |  | HAZOP CLOSEOUT REPORT ((DED) | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 27/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/27/2025 | 7/15/2025 | 08/01/2025 | [10 empty] | R | P1
BNO-MABU-300-HX-6881-10001 |  | SPECIFICATIONS FOR SAFETY SYSTEM DESCRIPTION | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/04/2025 | 7/23/2025 | 08/11/2025 | [10 empty] | R | P2
BNO-MABU-300-HX-6881-10002 |  | DESIGN SAFETY CASE REPORT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 21/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/21/2025 | 10/13/2025 | 10/30/2025 | [10 empty] | R | P1
BNO-MABU-300-HX-7303-10001 |  | PASSIVE FIRE PROTECTION LIST | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ISSUED | 03/06/2025 | 18/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 17/06/2025 | BNO-MABU-300-HX-7303-10001_R01.DOC | 2,21 MB | 03/06/2025 03:42:33 |  | 03/06/2025 09:42:33 | R01 | IFR - ISSUED FOR REVIEW | 23/06/2025 09:09:51 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00180 | R01 | 06/03/2025 | BNO-MABU-SNEPCO-2025-INC-00263 | 06/04/2025 | BNO/EXT/MABU/00629 | 6/23/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10094 | 07/18/2025 | R | P2
BNO-MABU-300-HX-7303-10002 |  | MATERIAL REQUISITION FOR SAFETY ITEMS | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 9/22/2025 | 10/09/2025 | [10 empty] | NR | NA
BNO-MABU-300-HX-7303-10003 |  | BILL OF MATERIALS (FIRE & SAFETY) | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/18/2025 | 09/10/2025 | 9/29/2025 | [10 empty] | INFO | NA
BNO-MABU-300-HX-7739-10001 |  | SAFETY CONCEPT & PHILOSOPHIES | HX - HSE | R02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 25/07/2025 |  | O.UGWUEGBU |  | 50 | 08/08/2025 | BNO-MABU-300-HX-7739-10001_R02.DOC | 2,99 MB | 25/07/2025 10:12:24 |  | 22/05/2025 05:42:37 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 3/21/2025 | 5/30/2025 | 6/18/2025 | BON-DAE-WESTPAQ-2025-TX-00408 | R02 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00446 | 07/25/2025 | BNO/EXT/MABU/00581 | 06/03/2025 | CODE 4 - MAJOR COMMENTS |  |  | R | P1
BNO-MABU-300-HX-7739-10002 |  | SAFETY SIGNS LAYOUT | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 15/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/15/2025 | 07/03/2025 | 7/22/2025 | [10 empty] | INFO | NA
BNO-MABU-300-HX-7739-10003 |  | SAFETY EQUIPMENT SPECIFICATION | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ENG_IFR COMMENTS - MABU | 30/06/2025 |  | O.UGWUEGBU |  | 50 | 14/07/2025 | BNO-MABU-300-HX-7739-10003_R01.DOCX | 851,61 KB | 30/06/2025 10:07:00 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/14/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00281 | R01 | 06/30/2025 | BNO-MABU-SNEPCO-2025-INC-00359 | 06/30/2025 | BNO/EXT/MABU/00688 (OVERDUE RCVD LATE FROM CPY.) | 07/25/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-HX-7739-10004 |  | SAFETY EQUIPMENT MTO | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/18/2025 | 09/10/2025 | 9/29/2025 | [10 empty] | INFO | NA
BNO-MABU-300-HX-7739-10005 |  | SAFETY EQUIPMENT DATASHEET | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 25/07/2025 |  | O.UGWUEGBU |  | 50 | 08/08/2025 | BNO-MABU-300-HX-7739-10005_R01.XLSX | 183,05 KB | 25/07/2025 10:28:05 | [11 empty] | IFR - ISSUED FOR REVIEW | 7/18/2025 | 09/10/2025 | 9/29/2025 | BON-DAE-WESTPAQ-2025-TX-00412 | R01 | 07/25/2025 |  | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00446 |  |  |  |  | R | P2
BNO-MABU-300-HX-7753-10003 |  | HAZID - TERMS OF REFERENCE | HX - HSE | A02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 12/07/2025 |  | O.UGWUEGBU |  | 85 | 25/07/2025 | BNO-MABU-300-HX-7753-10003_A02.DOCX | 1,41 MB | 12/07/2025 05:13:59 |  | 15/05/2025 04:45:15 | A01 | IFA - ISSUED FOR APPROVAL | 04/04/2025 13:43:25 | R01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED | 03/07/2025 | 4/25/2025 | 07/25/2025 | BON-DAE-WESTPAQ-2025-TX-00344 | A02 | 07/11/2025 | BNO-MABU-SNEPCO-2025-INC-00395 | 07/11/2025 | [5 empty] | R | P2
BNO-MABU-300-HX-7753-10005 |  | SIMOPS TERMS OF REFERENCE | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-HX-7753-10006 |  | DESIGN SAFETY CASE TERMS OF REFERENCE | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 27/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/27/2025 | 7/15/2025 | 08/01/2025 | [10 empty] | INFO | NA
BNO-MABU-300-HX-7876-10001 |  | SAFETY EQUIPMENT LIST | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 25/07/2025 |  | O.UGWUEGBU |  | 50 | 08/08/2025 | BNO-MABU-300-HX-7876-10001_R01.DOCX | 829,27 KB | 25/07/2025 10:45:20 | [11 empty] | IFR - ISSUED FOR REVIEW | 7/18/2025 | 09/05/2025 | 9/24/2025 | BON-DAE-WESTPAQ-2025-TX-00412 | R01 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00446 | 07/25/2025 | [5 empty] | R | P2
BNO-MABU-300-HX-7880-10002 |  | SPECIFICATIONS FOR SUB-CONTRACTED SAFETY STUDIES REQUIREMENTS | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 25/07/2025 |  | O.UGWUEGBU |  | 50 | 08/08/2025 | BNO-MABU-300-HX-7880-10002_R01.DOCX | 857,09 KB | 25/07/2025 10:31:21 | [11 empty] | IFR - ISSUED FOR REVIEW | 06/04/2025 | 7/23/2025 | 08/11/2025 | BON-DAE-WESTPAQ-2025-TX-00412 | R01 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00446 | 07/25/2025 | [5 empty] | NR | NA
BNO-MABU-300-HX-7880-10003 |  | SPECIFICATIONS FOR SAFETY SHOWER SPECIFICATION | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 29/06/2025 |  | O.UGWUEGBU |  | 50 | 11/07/2025 | BNO-MABU-300-HX-7880-10003_R01.DOCX | 846,51 KB | 29/06/2025 13:11:54 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00274 | R01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00353 | 06/29/2025 | BNO/EXT/MABU/00705/712(OVERDUE) | 07/23/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-HX-7880-10004 |  | SPECIFICATIONS FOR PASSIVE FIRE PROTECTION (PFP) FLEXIBLE JACKET | HX - HSE | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.12-HX-HSE | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 27/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/27/2025 | 7/15/2025 | 08/01/2025 | [10 empty] | R | P2
BNO-MABU-300-HX-8502-10001 |  | REQUEST FOR SAFETY SIGNS LAYOUT | HX - HSE | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A0 | 0 | ENGINEERING CONSOLIDATION | 02/07/2025 |  | K.AKPABIO |  | 0 | 14/07/2025 | BNO-MABU-300-HX-8502-10001=A01.DOCX | 170,77 KB | 02/07/2025 17:15:34 | [15 empty] | BON-DAE-WESTPAQ-2025-TX-00290 | A01 | 07/01/2025 | BNO-MABU-SNEPCO-2025-INC-00362 | 07/02/2025
BNO-MABU-300-HX-8502-10002 |  | REQUEST FOR COMPANY PREFERRED SOFTWARE FOR NOISE STUDY ASSESSMENT | HX - HSE | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A0 | 0 | ENGINEERING CONSOLIDATION | 07/07/2025 |  | K.AKPABIO |  | 50 | 21/07/2025 | BNO-MABU-300-HX-8502-10002=A01.DOCX | 167,31 KB | 07/07/2025 05:00:26 | [11 empty] | IFI - ISSUED FOR INFORMATION | 07/21/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00308 | A01 | 07/07/2025 | N/A
BNO-MABU-300-HX-8502-10003 |  | DEP REFERENCES LATEST | HX - HSE | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A0 | 0 | ENGINEERING CONSOLIDATION | 16/07/2025 |  | K.AKPABIO |  | 0 | 30/07/2025 | BNO-MABU-300-HX-8502-10003=A01.DOCX | 170,42 KB | 16/07/2025 01:27:00 | [15 empty] | BON-DAE-WESTPAQ-2025-TX-00369 | A01 | 07/16/2025 | N/A
BNO-MABU-300-HX-8502-10004 |  | REQUEST FOR CPY RESOLUTION ON IMPAIRMENT OF HPU PANEL DOORS ON ESCAPE ROUTE_A01 | HX - HSE | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A0 | 0 | ENGINEERING CONSOLIDATION | 27/07/2025 |  | O.UGWUEGBU |  | 0 | 08/08/2025 | BNO-MABU-300-HX-8502-10004_A01.DOCX | 168,01 KB | 27/07/2025 06:31:53 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00417 | A01 | 07/28/2025
BNO-MABU-300-IN-0780-10001 |  | SIL DETERMINATION REPORT | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 24/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/24/2025 | 9/25/2025 | 10/16/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-0780-10002 |  | OSI PI PROCESS HISTORIAN POINT CONFIGURATION REPORT. | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/25/2025 | 8/27/2025 | 9/17/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-0780-10004 |  | SIF DESIGN VERIFICATION (AS PER IEC 61511) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-0780-10005 |  | FUNCTIONAL SAFETY ASSESSMENT - STAGE 2 TOR | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-0780-10006 |  | FUNCTIONAL SAFETY ASSESSMENT - STAGE 2 REPORT | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-0780-10007 |  | FUNCTIONAL SAFETY ASSESSMENT - STAGE 3 TOR | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-0780-10008 |  | FUNCTIONAL SAFETY ASSESSMENT - STAGE 3 REPORT | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-0780-10009 |  | ALARM RATIONALISATION WORKSHOP - TOR | IN - INSTRUMENTATION | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 18/07/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 30/07/2025 | BNO-MABU-300-IN-0780-10009_A01.DOCX | 837,7 KB | 16/07/2025 02:05:28 | [11 empty] | IFA - ISSUED FOR APPROVAL |  | 07/30/2025 |  | BON-DAE-WESTPAQ-2025-TX-00370 | A01 | 07/16/2025 | BNO/MABU-SNEPCO-2025-INC-00407 | 07/16/2025 | BNO/EXT/MABU/00663 | 07/14/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | NR | NA
BNO-MABU-300-IN-0980-10001-001 |  | VIBRATION MONITORING SYSTEMS BLOCK DIAGRAMS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 08/07/2025 | 24/07/2025 |  |  | 100 | 22/07/2025 | BNO-MABU-300-IN-0980-10001-001_R01.DWG | 428,02 KB | 08/07/2025 13:58:37 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/22/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00320 | R01 | 07/08/2025 | BNO-MABU-SNEPCO-2025-INC-00380 | 07/08/2025 | BNO/EXT/MABU/00674 | 07/11/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025 | R | P2
BNO-MABU-300-IN-0980-10001-002 |  | VIBRATION_MONITORING_SYSTEMS_BLOCK_DIAGRAMS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | ISSUED | 08/07/2025 | 24/07/2025 |  |  | 100 | 22/07/2025 | BNO-MABU-300-IN-0980-10001-002_R01.DWG | 429,22 KB | 08/07/2025 14:09:16 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/22/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00321 | R01 | 07/08/2025 | BNO-MABU-SNEPCO-2025-INC-00380 | 07/08/2025 | BNO/EXT/MABU/00674 | 07/11/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025
BNO-MABU-300-IN-0980-10002-001 |  | HYDRAULIC AND CHEMICAL SYSTEMS BLOCK DIAGRAM BOARDING VALVE HYDRAULIC DISTRIBUTION | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | INFO | NA
BNO-MABU-300-IN-0980-10003 |  | ICSS NETWORK ARCHITECTURE DETAILED DRAWINGS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 30/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/30/2025 | 07/02/2025 | 7/23/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-0980-10005-001 |  | BPCS BLOCK DIAGRAM | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/25/2025 | 8/27/2025 | 9/17/2025 | [10 empty] | INFO | NA
BNO-MABU-300-IN-0980-10006-001 |  | ICSS NETWORK ARCHITECTURE BLOCK DIAGRAMS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 05/06/2025 | 07/08/2025 | 7/29/2025 | [10 empty] | INFO | NA
BNO-MABU-300-IN-0980-10007-001 |  | CABLE BLOCK DIAGRAM | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 26/06/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 08/07/2025 | BNO-MABU-300-IN-0980-10007-001_R01.DWG | 1,77 MB | 26/06/2025 05:17:15 | [11 empty] | IFR - ISSUED FOR REVIEW | 06/06/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00253 | R01 | 06/24/2025 | BNO-MABU-SNEPCO-2025-INC-00334 | 06/26/2025 | BNO/EXT/MABU/00675 | 07/11/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | NR | NA
BNO-MABU-300-IN-0980-10008-001 |  | CHEMICAL INJECTION HYDRAULIC TUBING BLOCK DIAGRAM | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 03/07/2025 | 24/07/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 100 | 16/07/2025 | BNO-MABU-300-IN-0980-10008-001_R01.DWG | 191,4 KB | 03/07/2025 13:19:30 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00297 | R01 | 07/02/2025 | BNO-MABU-SNEPCO-2025-INC-00368 | 07/03/2025 | BNO/EXT/MABU/00703 | 07/22/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10098 | 07/24/2025 | NR | NA
BNO-MABU-300-IN-0980-10008-002 |  | CHEMICAL INJECTION HYDRAULIC TUBING BLOCK DIAGRAM | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 03/07/2025 | 24/07/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 100 | 16/07/2025 | BNO-MABU-300-IN-0980-10008-002_R01.DWG | 206,59 KB | 03/07/2025 13:07:30 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00297 | R01 | 07/02/2025 | BNO-MABU-SNEPCO-2025-INC-00368 | 07/03/2025 | BNO/EXT/MABU/00703 (OVERDUE) | 07/22/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10098 | 07/24/2025
BNO-MABU-300-IN-1214-10001 |  | CONTROL VALVES SIZING CALCULATION | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 03/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/03/2025 | 08/05/2025 | 8/26/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-1214-10002 |  | PRESSURE RELIEF VALVES SIZING CALCULATION | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 03/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 04/03/2025 | 06/05/2025 | 6/26/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-1214-10003 |  | RESTRICTION ORIFICE SIZING CALCULATION - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 03/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 04/03/2025 | 06/05/2025 | 6/26/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-1214-10004 |  | THERMOWELLS SIZING CALCULATION | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 03/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 04/03/2025 | 06/05/2025 | 6/26/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-1214-10006 |  | MC CONTROL VALVES - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-1214-10008 |  | MC PRESSURE SAFETY VALVES - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-1214-10009 |  | INSTRUMENT AIR CONSUMPTION CALCULATION | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-1214-10010 |  | INSTRUMENT POWER CONSUMPTION CALCULATION | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-1214-10011 |  | SIL CALCULATION NOTES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 23/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/23/2025 | 9/16/2025 | 10/07/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-1979-10001 |  | I/O MAPPING AND DATABASE - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 30/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/30/2025 | 07/02/2025 | 7/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-IN-1979-10002 |  | MASTER ALARM DATABASE (VARIABLE TABLE) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ENG_IFR COMMENTS - MABU | 14/07/2025 |  | JOSE.SARAIVA |  | 50 | 28/07/2025 | BNO-MABU-300-IN-1979-10002_R01.XLSX | 486,03 KB | 14/07/2025 06:16:56 | [11 empty] | IFR - ISSUED FOR REVIEW | 5/29/2025 | 7/23/2025 | 8/13/2025 | BON-DAE-WESTPAQ-2025-TX-00357 | R01 | 07/14/2025 | BNO-MABU-SNEPCO-2025-INC-00404 | 07/14/2025 | [5 empty] | R | P2
BNO-MABU-300-IN-1979-10003 |  | ESD TRIP SCHEDULE (INPUT ONLY) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 20/06/2025 | 24/07/2025 |  |  | 100 | 04/07/2025 | BNO-MABU-300-IN-1979-10003_R01.XLSX | 468,97 KB | 20/06/2025 03:53:05 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00228 | R01 | 06/20/2025 | BNO/MABU-SNEPCO-2025-INC-00346 | 06/27/2025 | BNO/EXT/MABU/00674 | 07/11/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10097 | 07/24/2025 | INFO | NA
BNO-MABU-300-IN-2105-10001 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR PIG SIGNALER - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA | 15/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 06/06/2025 | BNO-MABU-300-IN-2105-10001_R01.XLSX | 220,82 KB | 15/05/2025 09:32:30 |  | 15/05/2025 17:33:01 | R01 | IFR - ISSUED FOR REVIEW | 30/05/2025 07:14:18 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/06/2025 | 08/08/2025 | 8/29/2025 | BON-DAE-WESTPAQ-2025-TX-00112 | R01 | 5/16/2025 | BNO-MABU-SNEPCO-2025-INC-00201 | 5/15/2025 | BNO/EXT/MABU/00571 | 5/30/2025 | 3 |  |  | INFO | NA
BNO-MABU-300-IN-2105-10002 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR SAND DETECTOR - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | INFO | NA
BNO-MABU-300-IN-2105-10003 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR SMART CHOKE VALVE - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 11/07/2025 |  | ARY.CARVALHO |  | 50 | 24/07/2025 | BNO-MABU-300-IN-2105-10003_R01.XLSX | 218,59 KB | 11/07/2025 00:19:14 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/24/2025 | 08/08/2025 | 8/29/2025 | BON-DAE-WESTPAQ-2025-TX-00342 | R01 | 07/10/2025 | BNO-MABU-SNEPCO-2025-INC-00390 | 07/10/2025 | [5 empty] | INFO | NA
BNO-MABU-300-IN-2105-10004 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR HYDRAULIC MOTOR OPERATED VALVE - FINAL | IN - INSTRUMENTATION | R02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 17/07/2025 |  | ARY.CARVALHO |  | 50 | 31/07/2025 | BNO-MABU-300-IN-2105-10004_R02.XLSX | 289,83 KB | 17/07/2025 09:47:31 |  | 30/05/2025 09:49:21 | R01 | IFR - ISSUED FOR REVIEW | 24/06/2025 04:06:23 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  | 07/31/2025 |  | BON-DAE-WESTPAQ-2025-TX-00373 | A01 | 07/17/2025 | BNO-MABU-SNEPCO-2025-INC-00412 | 07/17/2025 | [5 empty] | NR | NA
BNO-MABU-300-IN-2105-10005 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR PNEUMATIC ACTUATED ON-OFF_ BLOWDOWN AND SHUTDOWN VALVES - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 05/06/2025 | 07/07/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 20/06/2025 | BNO-MABU-300-IN-2105-10005_R01.XLSX | 757,18 KB | 05/06/2025 05:29:00 |  |  |  |  | 30/06/2025 06:18:36 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/20/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00189 | R01 | 06/05/2025 | BNO-MABU-SNEPCO-2025-INC-00268 | 06/05/2025 | BNO_EXT_MABU_00646 | 06/30/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10087 | 07/07/2025 | NR | NA
BNO-MABU-300-IN-2105-10006 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR CORIOLIS FLOWMETER - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 29/04/2025 | 26/05/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 04/06/2025 | BNO-MABU-300-IN-2105-10006_R01.XLSX | 172,8 KB | 29/04/2025 05:33:41 |  | 02/05/2025 07:48:27 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 08:16:52 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/04/2025 | 08/06/2025 | 8/27/2025 | BON-DAE-WESTPAQ-2025-TX-00084 | R01 | 4/28/2025 | BNO-MABU-SNEPCO-2025-INC-00176 | 05/02/2025 | BNO_EXT_MABU_00589 | 06/04/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-IN-2105-10007 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR CORROSION DETECTOR - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 18/07/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 11/07/2025 | BNO-MABU-300-IN-2105-10007_R01.XLSX | 237,37 KB | 27/06/2025 06:50:45 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00262 | R01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00348 | 06/27/2025 | BNO/EXT/MABU/00673 | 07/11/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10098 | 07/24/2025 | NR | NA
BNO-MABU-300-IN-2105-10008 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR DIFFERENTIAL PRESSURE INDICATING TRANSMITTER - FINAL | IN - INSTRUMENTATION | R01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA | 15/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 04/06/2025 | BNO-MABU-300-IN-2105-10008_R01.XLSX | 159,78 KB | 15/05/2025 08:10:48 |  | 15/05/2025 17:33:01 | R01 | IFR - ISSUED FOR REVIEW | 30/05/2025 07:14:19 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/04/2025 | 08/06/2025 | 8/27/2025 | BON-DAE-WESTPAQ-2025-TX-00108 | R01 | 5/15/2025 | BNO-MABU-SNEPCO-2025-INC-00201 | 5/15/2025 | BNO/EXT/MABU/00571 | 5/30/2025 | 3 |  |  | NR | NA
BNO-MABU-300-IN-2105-10009 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR RESTRICTION ORIFICE - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/04/2025 | 08/06/2025 | 8/27/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-2105-10010 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR TEMPERATURE INDICATING TRANSMITTER - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 22/05/2025 | 23/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 04/06/2025 | BNO-MABU-300-IN-2105-10010=R01.XLSX | 399,54 KB | 22/05/2025 02:14:45 |  | 22/05/2025 09:56:37 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 06/04/2025 | 08/06/2025 | 8/27/2025 | BON-DAE-WESTPAQ-2025-TX-00135 | R01 | 5/21/2025 | BNO-MABU-SNEPCO-2025-INC-00221 | 5/22/2025 | BNO/EXT/MABU/00615 | 6/19/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025 | NR | NA
BNO-MABU-300-IN-2105-10011 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR ULTRASONIC FLOWMETER - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ENG_IFR CONSOLIDATION | 02/07/2025 |  | ARY.CARVALHO |  | 50 | 15/07/2025 | BNO-MABU-300-IN-2105-10011_R01.XLSX | 229,84 KB | 02/07/2025 05:11:25 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/15/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00285 | R01 | 07/01/2025 | BNO-MABU-SNEPCO-2025-INC-00362 | 07/02/2025 | BNO/EXT/MABU/00700 | 07/22/2025 | OVERDUE |  |  | NR | NA
BNO-MABU-300-IN-2105-10012 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR PRESSURE GAUGE - FINAL | IN - INSTRUMENTATION | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 50 | 08/08/2025 | BNO-MABU-300-IN-2105-10012_A01.XLSX | 453,07 KB | 25/07/2025 07:45:25 |  | 15/05/2025 17:33:01 | R01 | IFR - ISSUED FOR REVIEW | 30/05/2025 07:14:21 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 06/04/2025 | 08/06/2025 | 8/27/2025 | BON-DAE-WESTPAQ-2025-TX-00107 | A01 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00447 | 07/25/2025 | BNO/EXT/MABU/00571 | 5/30/2025 |  |  |  | NR | NA
BNO-MABU-300-IN-2105-10013 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR PRESSURE INDICATING TRANSMITTER - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 26/05/2025 | 23/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 06/06/2025 | BNO-MABU-300-IN-2105-10013_R01.XLSX | 545,36 KB | 26/05/2025 02:18:24 |  | 27/05/2025 10:10:15 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00142 | R01 | 5/23/2025 | BNO-MABU-SNEPCO-2025-INC-00236 | 5/27/2025 | BNO/EXT/MABU/00615 | 6/19/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025 | NR | NA
BNO-MABU-300-IN-2105-10014 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR TEMPERATURE GAUGE - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 15/05/2025 | 02/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 28/05/2025 | BNO-MABU-300-IN-2105-10014_R01.XLSX | 173,98 KB | 15/05/2025 04:27:37 |  | 15/05/2025 17:33:01 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 06/04/2025 | 08/06/2025 | 8/27/2025 | BON-DAE-WESTPAQ-2025-TX-00107 | R01 | 5/15/2025 | BNO-MABU-SNEPCO-2025-INC-00201 | 5/15/2025 | BNO/EXT/MABU/00572 | 5/30/2025 | 4 |  |  | NR | NA
BNO-MABU-300-IN-2105-10015 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR PRESSURE RELIEF VALVE - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/04/2025 | 08/06/2025 | 8/27/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-2105-10016 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR CONTROL VALVES - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | DCC_IFR RECEIVED FROM ASSAI | 23/07/2025 |  | F.NEVES |  | 50 | 06/08/2025 | BNO-MABU-300-IN-2105-10016_R01.XLSX | 389,42 KB | 23/07/2025 15:52:30 | [11 empty] | IFR - ISSUED FOR REVIEW | 06/04/2025 | 08/06/2025 | 8/27/2025 | BON-DAE-WESTPAQ-2025-TX-00406 | R01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00444 | 07/23/2025 | [5 empty] | NR | NA
BNO-MABU-300-IN-2105-10017 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR HEAT AND SMOKE DETECTORS - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/04/2025 | 08/06/2025 | 8/27/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-2105-10018 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR HYDRAULIC HAND VALVE AND SHUTDOWN VALVE - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 18/06/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 03/07/2025 | BNO-MABU-300-IN-2105-10018_R01.XLSX | 407,97 KB | 18/06/2025 16:15:42 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/03/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00219 | R01 | 06/18/2025 | BNO-MABU-SNEPCO-2025-INC-00303 | 06/18/2025 | BNO/EXT/MABU/00665 | 07/09/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | R | P2
BNO-MABU-300-IN-2105-10019 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR HYDRAULIC BOARDING SHUTDOWN VALVE - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/04/2025 | 08/06/2025 | 8/27/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-2105-10020 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR POINT TYPE GAS DETECTOR - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 23/07/2025 | 27/07/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 100 | 11/07/2025 | BNO-MABU-300-IN-2105-10020_R01.XLSX | 544,35 KB | 29/06/2025 12:54:31 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00270 | R01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00353 | 06/29/2025 | BNO/EXT/MABU/00703 (CODE 4) | 07/22/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10099 | 07/27/2025 | R | P2
BNO-MABU-300-IN-2105-10021 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR OPEN PATH GAS DETECTOR | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 08/07/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 22/07/2025 | BNO-MABU-300-IN-2105-10021_R01.XLSX | 549,1 KB | 08/07/2025 13:29:54 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/22/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00317 | R01 | 07/08/2025 | BNO-MABU-SNEPCO-2025-INC-00380 | 07/08/2025 | BNO/EXT/MABU/00700 | 07/22/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10102 | 07/29/2025 | R | P2
BNO-MABU-300-IN-2105-10022 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR IR FLAME DETECTOR - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 22/07/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 09/07/2025 | BNO-MABU-300-IN-2105-10022_R01.XLSX | 819,21 KB | 26/06/2025 06:14:46 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/09/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00254 | R01 | 06/25/2025 | BNO-MABU-SNEPCO-2025-INC-00335 | 06/26/2025 | BNO/EXT/MABU/00700 | 07/22/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10097 | 07/24/2025 | R | P2
BNO-MABU-300-IN-2105-10023 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR MANUAL ALARM CALL POINT - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 02/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/02/2025 | 08/04/2025 | 8/25/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-2105-10024 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR SOUNDER AND BEACON ALARMS - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 02/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/02/2025 | 08/04/2025 | 8/25/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-2105-10025 |  | INSTRUMENTATION & AUTOMATION DATASHEET FOR JUNCTION BOXES - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | INFO | NA
BNO-MABU-300-IN-2312-10001-001 |  | SUBSEA CONTROL SYSTEM TOPSIDE INTERFACE SCHEMATIC | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | INFO | NA
BNO-MABU-300-IN-2335-10001-001 |  | PROCESS HOOK UP DRAWING | IN - INSTRUMENTATION | R02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 26/06/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 09/07/2025 | BNO-MABU-300-IN-2335-10001-001_R02.DWG | 1,17 MB | 26/06/2025 06:17:47 |  | 28/03/2025 11:22:25 | R01 | IFR - ISSUED FOR REVIEW | 09/04/2025 04:52:32 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 07/09/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00254 | R02 | 06/25/2025 | BNO-MABU-SNEPCO-2025-INC-00335 | 06/26/2025 | BNO/EXT/MABU/00673 | 07/11/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | NR | NA
BNO-MABU-300-IN-2335-10002-001 |  | SUPPORT HOOK UP DRAWING | IN - INSTRUMENTATION | R02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 27/06/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 11/07/2025 | BNO-MABU-300-IN-2335-10002-001_R02.DWG | 1,11 MB | 27/06/2025 09:03:05 |  | 28/03/2025 11:02:46 | R01 | IFR - ISSUED FOR REVIEW | 09/04/2025 05:00:04 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00263 | R02 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00349 | 06/27/2025 | BNO/EXT/MABU/00673 | 07/11/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | NR | NA
BNO-MABU-300-IN-2335-10003-001 |  | ELECTRICAL HOOK UP DRAWING - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 08/05/2025 | 20/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 03/04/2025 | BNO-MABU-300-IN-2335-10003-001_R01.DWG | 587,02 KB | 08/05/2025 03:43:47 |  | 09/05/2025 04:38:41 | R01 | IFR - ISSUED FOR REVIEW | 22/05/2025 06:05:27 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 04/03/2025 | 06/05/2025 | 6/26/2025 | BON-DAE-WESTPAQ-2025-TX-00097 | R01 | 05/08/2025 | BNO-MABU-SNEPCO-2025-INC-00185 | 05/09/2025 | BNO_EXT_MABU_00558 | 06/05/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10077 | 06/20/2025 | NR | NA
BNO-MABU-300-IN-2335-10004-001 |  | PNEUMATIC/HYDRALIC HOOK UP DRAWING | IN - INSTRUMENTATION | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 26/05/2025 | 20/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 09/06/2025 | BNO-MABU-300-IN-2335-10004-001_A01.DWG | 484,12 KB | 26/05/2025 03:47:23 |  | 27/05/2025 10:10:15 | A01 | IFA - ISSUED FOR APPROVAL | [7 empty] | IFA - ISSUED FOR APPROVAL | 04/03/2025 | 06/09/2025 | 6/26/2025 | BON-DAE-WESTPAQ-2025-TX-00146 | A01 | 5/26/2025 | BNO-MABU-SNEPCO-2025-INC-00236 | 05/27/2025 |  |  | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10078 | 06/20/2025 | NR | NA
BNO-MABU-300-IN-2335-10006-001 |  | PNEUMATIC/HYDRAULIC HOOK-UP DRAWINGS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/25/2025 | 6/27/2025 | 7/18/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-2341-10003-001 |  | HPU/HCU INTERFACE HOOKUP DRAWINGS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-2341-10004-001 |  | PRODUCTION UMBILICAL INTERFACE HOOKUP DRAWINGS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-2341-10005-001 |  | GASLIFT UMBILICAL HOOKUP DRAWING | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-2341-10007-001 |  | CORROSION INHIBITOR & METHANOL SYSTEM TO TUPA INTERFACE HOOKUP DRAWINGS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-2341-10008-001 |  | BUNDLE GASLIFT UMBILICAL( BGLU) TO GASLIFT TUPA HOOKUP DRAWINGS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-2341-10012-001 |  | CONTROL SYSTEMS INTERFACE HOOKUP DRAWINGS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-2347-10001-001 |  | INSTRUMENT LOOP DIAGRAMS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-2373-10001 |  | CHEMICAL INJECTION HYDRAULIC TUBING ROUTING DRAWINGS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 31/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/31/2025 | 10/02/2025 | 10/21/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-2389-10001 |  | RIO TERMINATION DRAWINGS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-2389-10002 |  | RIO PANEL TERMINATION DRAWINGS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3309-10001 |  | INSTRUMENT SUMMARY - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 07/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 05/07/2025 | 07/09/2025 | 7/30/2025 | [10 empty] | INFO | NA
BNO-MABU-300-IN-3323-10001 |  | TBE FOR SAND DETECTOR ELEMENT_ SAND DETECTOR TRANSMITTER | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 24/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/24/2025 | 8/26/2025 | 9/16/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10002 |  | TBE FOR SMART CHOKE VALVE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 24/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/24/2025 | 8/26/2025 | 9/16/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10003 |  | TBE FOR PIG SIGNALER | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10004 |  | TBE FOR TUBING & BULK MATERIAL MTO | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10005 |  | TBE FOR SUPPORT | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10006 | PRJ2501-BNO-06-INS-PT-004 | TBE FOR BOARDING VALVES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ENG_IFR CONSOLIDATION | 15/05/2025 |  | ARY.CARVALHO | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 23/05/2025 | BNO-MABU-300-IN-3323-10006_R01.ZIP | 2,4 MB | 15/05/2025 11:30:13 |  | 15/05/2025 17:33:01 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 04/02/2025 | 06/04/2025 | 6/25/2025 |  |  |  | BNO-MABU-SNEPCO-2025-INC-00201 | 5/15/2025 | BNO_EXT_MABU_00576 | 06/02/2025 | CODE 4 - MAJOR COMMENTS |  |  | NR | NA
BNO-MABU-300-IN-3323-10007 |  | TBE FOR CABLE TRAYS AND ACCESSORIES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10008 |  | TBE FOR CHANNELS AND ACCESSORIES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/11/2025 | 8/13/2025 | 09/03/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10009 |  | TBE FOR CORIOLIS FLOWMETERS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/11/2025 | 8/13/2025 | 09/03/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10010 |  | TBE FOR BLOWDOWN VALVE_ PNEUMATIC ACTUATED ON/OFF VALVE AND SHUTDOWN VALVE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/11/2025 | 8/13/2025 | 09/03/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10011 |  | TBE FOR CABLE GLANDS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/11/2025 | 8/13/2025 | 09/03/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10012 |  | TBE FOR CABLES AND MULTICABLES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/11/2025 | 8/13/2025 | 09/03/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10013 | PRJ2501-BNO-06-INS-PT-008_01R | TBE FOR CONTROL VALVES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ENG_IFR COMMENTS - MABU | 15/05/2025 |  | ARY.CARVALHO | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 21/05/2025 | BNO-MABU-300-IN-3323-10013_R01.ZIP | 3,81 MB | 15/05/2025 11:13:58 |  | 15/05/2025 17:33:01 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 06/06/2025 | 08/08/2025 | 8/29/2025 |  |  |  | BNO-MABU-SNEPCO-2025-INC-00201 | 5/15/2025 | BNO/EXT/MABU/00567 | 5/28/2025 | 3 |  |  | NR | NA
BNO-MABU-300-IN-3323-10014 |  | TBE FOR HYDRAULIC MOTOR OPERATED VALVE (ON/OFF VALVE)_ HYDRAULIC HAND VALVE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10015 |  | TBE FOR JUNCTION BOXES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10016 |  | TBE FOR MISCELLANEOUS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10017 |  | TBE FOR PIPING AND PIPING CONNECTIONS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10018 |  | TBE FOR PRESSURE RELIEF VALVE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10019 |  | TBE FOR TEMPERATURE INDICATING TRANSMITTER | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10020 |  | TBE FOR PRESSURE AND DIFFERENTIAL PRESSURE INDICATING TRANSMITTERS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10021 |  | TBE FOR TEMPERATURE GAUGES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 20/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/20/2025 | 8/22/2025 | 09/12/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10022 |  | TBE FOR PRESSURE GAUGES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 20/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/20/2025 | 8/22/2025 | 09/12/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10023 |  | TBE FOR FIRE & GAS DETECTORS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 20/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/20/2025 | 8/22/2025 | 09/12/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-3323-10024 |  | TBE FOR ULTRASONIC FLOWMETER | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 20/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/20/2025 | 8/22/2025 | 09/12/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10025 |  | TBE FOR CORROSION TRANSMITTER | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 20/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/20/2025 | 8/22/2025 | 09/12/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10026 |  | TBE FOR BEACON | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 24/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/24/2025 | 8/26/2025 | 9/16/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10027 |  | TBE FOR MANUAL CALL POINT | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 24/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/24/2025 | 8/26/2025 | 9/16/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-3323-10028 |  | TBE FOR CHEMICAL INJECTION HYDRAULIC TUBING | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 0 | 24/06/2025 | [7 empty] | 24/06/2025 04:06:24 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 6/24/2025 | 8/26/2025 | 7/23/2025 | [5 empty] | BNO/EXT/MABU/00614 | 6/19/2025 | CODE 4 - MAJOR COMMENTS |  |  | NR | NA
BNO-MABU-300-IN-3323-10029 | PRJ2403-BNO-06-INS-RM-001 | MATERIAL REQUISITION FOR TUBING AND FITTINGS (TAM 26) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | ISSUED | 23/06/2025 | 30/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 |  | BNO-MABU-300-IN-3323-10029_R01.XLSX | 177,77 KB | 23/06/2025 12:11:01 | [11 empty] | IFR - ISSUED FOR REVIEW | [6 empty] | BNO-MABU-SNEPCO-2025-INC-00230 | 05/26/2025 | BNO_EXT_MABU_00615 | 06/20/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025
BNO-MABU-300-IN-3323-10030 | PRJ2403-BNO-06-INS-RM-002 | MATERIAL REQUISITION FOR INSTRUMENTATION CABLE TRAY (TAM 26) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | ISSUED | 23/06/2025 | 30/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 |  | BNO-MABU-300-IN-3323-10030_R01.XLSX | 188,4 KB | 23/06/2025 12:20:34 | [11 empty] | IFR - ISSUED FOR REVIEW | [6 empty] | BNO-MABU-SNEPCO-2025-INC-00230 | 05/26/2025 | BNO_EXT_MABU_00615 | 06/20/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 07/29/2025
BNO-MABU-300-IN-3323-10031 | PRJ2403-BNO-06-INS-RM-003 | MATERIAL REQUISITION FOR INSTRUMENTATION SUPPORT (TAM 26) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | ISSUED | 23/06/2025 | 30/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 |  | BNO-MABU-300-IN-3323-10031_R01.XLSX | 177,13 KB | 23/06/2025 12:21:05 | [11 empty] | IFR - ISSUED FOR REVIEW | [6 empty] | BNO-MABU-SNEPCO-2025-INC-00230 | 05/26/2025 | BNO_EXT_MABU_00615 | 06/20/2025 | CODE 3 - MINOR COMMENTS
BNO-MABU-300-IN-3323-10032 | PRJ2403-BNO-06-INS-RM-004 | MATERIAL REQUISITION - CLAMPS FOR TUBING (TAM 26) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | ISSUED | 23/06/2025 | 30/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 |  | BNO-MABU-300-IN-3323-10032_R01.XLSX | 180,67 KB | 23/06/2025 12:21:26 | [11 empty] | IFR - ISSUED FOR REVIEW | [6 empty] | BNO-MABU-SNEPCO-2025-INC-00230 | 05/26/2025 | BNO_EXT_MABU_00615 | 06/20/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025
BNO-MABU-300-IN-4018-10001-001 |  | INSTRUMENT CABLES ROUTING DRAWINGS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/25/2025 | 6/27/2025 | 7/18/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4018-10002-001 |  | INSTRUMENT TUBING ROUTING DRAWINGS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4018-10003-001 |  | PCD NETWORK ARCHITECTURE DRAWING(PHYSICAL LOGICAL) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 23/07/2025 |  | ARY.CARVALHO |  | 50 | 06/08/2025 | BNO-MABU-300-IN-4018-10003-001_R01.DWG | 6,67 MB | 23/07/2025 06:10:20 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00400 | R01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00437 | 07/23/2025
BNO-MABU-300-IN-4018-10005-001 |  | PCD NETWORK CABLE (BLOCK DIAGRAM) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 23/07/2025 |  | ARY.CARVALHO |  | 50 | 06/08/2025 | BNO-MABU-300-IN-4018-10005-001_R01.DWG | 396,22 KB | 23/07/2025 06:10:18 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00400 | R01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00437 | 07/23/2025 |  | 07/23/2025
BNO-MABU-300-IN-4024-10002-001 |  | FIRE AND GAS LOCATION LAYOUT AND LOCATION PLAN - SSCB CONTROL ROOM SHT 1 | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 02/06/2025 | 27/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-IN-4024-10002-001_R01.DWG | 4,5 MB | 02/06/2025 09:06:32 |  | 02/06/2025 15:55:22 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00174 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00256 | 06/02/2025 | BNO/EXT/MABU/00615 | 6/20/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10082 | 06/27/2025 | R | P2
BNO-MABU-300-IN-4024-10002-002 |  | FIRE AND GAS LOCATION LAYOUT AND LOCATION PLAN - SSCB CONTROL ROOM SHT 2 | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | ISSUED | 18/06/2025 | 30/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-IN-4024-10002-002_R01.DWG | 4,51 MB | 02/06/2025 09:11:08 |  | 02/06/2025 15:55:22 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00174 | R01 | 06/02/2025 | BNO/MABU-SNEPCO-2025-INC-00256 | 06/02/2025 | BNO/EXT/MABU/00615 | 6/20/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025
BNO-MABU-300-IN-4024-10003-001 |  | F&G LOCATION LAYOUT & PLAN SSCB (BATTERY ROOM) - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 02/06/2025 | 29/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-IN-4024-10003-001_R01.DWG | 2,39 MB | 02/06/2025 09:13:01 | [11 empty] | IFR - ISSUED FOR REVIEW | 06/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00174 | R01 | 06/02/2025 |  |  |  |  | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025 | R | P2
BNO-MABU-300-IN-4024-10004-001 |  | F&G LOCATION LAYOUT & PLAN FLOWLINE CORROSION INHIBITOR SKID - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 02/06/2025 | 27/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-IN-4024-10004-001_R01.DWG | 2,18 MB | 02/06/2025 09:28:08 |  | 02/06/2025 15:55:22 | R01 | IFA - ISSUED FOR APPROVAL | 20/06/2025 14:29:29 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 06/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00174 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00256 | 06/02/2025 | BNO/EXT/MABU/00623 | 6/20/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10082 | 06/27/2025 | R | P2
BNO-MABU-300-IN-4024-10005-001 |  | F&G LOCATION LAYOUT & PLAN SUBSEA WELL LAUNCHER AND RECEIVER - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ENG_IFR CONSOLIDATION | 02/06/2025 |  | ARY.CARVALHO | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-IN-4024-10005-001_R01.DWG | 2,46 MB | 02/06/2025 10:21:55 |  | 02/06/2025 15:55:22 | R01 | IFR - ISSUED FOR REVIEW | 20/06/2025 14:29:31 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00174 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00256 | 06/02/2025 | BNO/EXT/MABU/00623 | 6/20/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-IN-4024-10005-002 |  | FIRE AND GAS LOCATION LAYOUT & PLAN SUBSEA WELL LAUNCHE AND RECEIVER | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | ISSUED | 02/06/2025 | 23/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-IN-4024-10005-002_R01.DWG | 3,82 MB | 02/06/2025 10:23:44 |  | 02/06/2025 15:55:22 | R01 | IFR - ISSUED FOR REVIEW | 20/06/2025 14:29:33 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00174 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00256 | 06/02/2025 | BNO/EXT/MABU/00623 | 6/20/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025
BNO-MABU-300-IN-4024-10006-001 |  | F&G LOCATION LAYOUT & PLAN METHANOL INJECTION PACKAGE - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 02/06/2025 | 27/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-IN-4024-10006-001_R01.DWG | 6,61 MB | 02/06/2025 10:25:29 |  | 02/06/2025 15:55:22 | R01 | IFR - ISSUED FOR REVIEW | 20/06/2025 15:37:08 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 07/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00174 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00256 | 06/02/2025 | BNO/EXT/MABU/00621 | 6/20/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10082 | 06/27/2025 | R | P2
BNO-MABU-300-IN-4024-10007-001 |  | F&G LOCATION LAYOUT & PLAN WATERFLOOD INJECTION PACKAGE - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 02/06/2025 | 27/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-IN-4024-10007-001_R01.DWG | 5,61 MB | 02/06/2025 10:27:13 |  | 02/06/2025 15:55:22 | R01 | IFR - ISSUED FOR REVIEW | 20/06/2025 15:37:09 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00174 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00256 | 06/20/2025 | BNO/EXT/MABU/00621 | 6/20/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10082 | 06/27/2025 | R | P2
BNO-MABU-300-IN-4024-10007-002 |  | FIRE & GAS LOCATION LAYOUT WATERFLOOD INJECTION PUMP TURBINE PLAN AT LEVEL 2 SHT 2 | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | ISSUED | 23/06/2025 | 27/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-IN-4024-10007-002_R01.DWG | 5,46 MB | 02/06/2025 09:53:37 |  | 02/06/2025 15:55:22 | R01 | IFR - ISSUED FOR REVIEW | 20/06/2025 15:37:10 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00174 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00256 | 06/02/2025 | BNO/EXT/MABU/00621 | 6/20/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025
BNO-MABU-300-IN-4024-10008-001 |  | PNEUMATIC & HYDRAULIC INSTRUMENTATION PLAN & LOCATION WATERFLOOD INJECTION PACKAGE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 03/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 04/03/2025 | 06/05/2025 | 6/26/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4024-10009-001 |  | F&G LOCATION LAYOUT & PLAN BOARDING VALVE PANEL AND TERMINATION UNBILICAL PANEL - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 04/06/2025 | 27/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-IN-4024-10009-001_R01.DWG | 4,19 MB | 02/06/2025 09:57:03 |  |  |  |  | 20/06/2025 15:37:12 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00174 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00266 | 06/04/2025 | BNO/EXT/MABU/00621 | 6/20/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10082 | 06/27/2025 | R | P2
BNO-MABU-300-IN-4024-10010-001 |  | PNEUMATIC & HYDRAULIC INSTRUMENTATION PLAN & LOCATION LAYOUT SUBSEA WELL LAUNCHER AND RECEIVER AND GAS LIFT - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 02/06/2025 | 27/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-IN-4024-10010-001_R01.DWG | 14,03 MB | 02/06/2025 07:56:21 |  | 02/06/2025 08:25:47 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00173 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00255 | 06/02/2025 | BNO_EXT_MABU_00621 | 06/20/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10082 | 06/27/2025 | NR | NA
BNO-MABU-300-IN-4024-10011-001 |  | PNEUMATIC & HYDRAULIC INSTRUMENTATION PLAN & LOCATION PRODUCTION MANIFOLD | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 02/06/2025 | 27/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-IN-4024-10011-001_R01.DWG | 2,75 MB | 02/06/2025 08:00:08 |  | 02/06/2025 08:25:47 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00173 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00255 | 06/02/2025 | BNO_EXT_MABU_00621 | 06/20/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025 | NR | NA
BNO-MABU-300-IN-4024-10012-001 |  | PNEUMATIC & HYDRAULIC INSTRUMENTATION PLAN & LOCATION GAS RISER LIFT METERS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 26/06/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 04/07/2025 | BNO-MABU-300-IN-4024-10012-001_R01.DWG | 4,46 MB | 26/06/2025 15:13:55 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/04/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00193 | R01 | 06/23/2025 | BNO-MABU-SNEPCO-2025-INC-00343 | 06/26/2025 | BNO/EXT/MABU/00675 | 07/11/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | NR | NA
BNO-MABU-300-IN-4024-10013-001 |  | PNEUMATIC & HYDRAULIC INSTRUMENTATION PLAN & LOCATION FLOWLINE CORROSION INHIBITOR SYSTEM PACKAGE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 26/06/2025 | 17/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 04/07/2025 | BNO-MABU-300-IN-4024-10013-001_R01.DWG | 6,01 MB | 26/06/2025 15:24:36 |  |  |  |  | 16/07/2025 11:02:49 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 07/04/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00193 | R01 | 06/23/2025 | BNO-MABU-SNEPCO-2025-INC-00343 | 06/26/2025 | BNO_EXT_MABU_00684 | 07/14/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10093 | 07/17/2025 | NR | NA
BNO-MABU-300-IN-4024-10014-001 |  | PNEUMATIC & HYDRAULIC INSTRUMENTATION PLAN & LOCATION METHANOL INJECTION PACKAGE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 02/06/2025 | 27/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-IN-4024-10014-001_R01.DWG | 4,83 MB | 02/06/2025 08:02:58 |  | 02/06/2025 08:25:47 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 06/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00173 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00255 | 06/02/2025 | BNO_EXT_MABU_00621 | 06/20/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10082 | 06/27/2025 | NR | NA
BNO-MABU-300-IN-4024-10020-001 |  | ELECTRICAL & I NSTRUMENTATION PLAN & LOCATION PRODUCTION MANIFOLD | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 30/06/2025 | 02/07/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 25/06/2025 | BNO-MABU-300-IN-4024-10020-001_R01.DWG | 4,39 MB | 10/06/2025 10:05:18 |  | 11/06/2025 05:04:20 | R01 | IFR - ISSUED FOR REVIEW | 30/06/2025 06:18:37 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/25/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00197 | R01 | 06/11/2025 | BNO-MABU-SNEPCO-2025-INC-00271 | 06/11/2025 | BNO_EXT_MABU_00646 | 06/30/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10084 | 07/02/2025 | NR | NA
BNO-MABU-300-IN-4024-10021-001 |  | ELECTRICAL & INSTRUMENTATION PLAN & LOCATION BOARDING VALVE PANEL-HPU | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 11/06/2025 | 30/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 25/06/2025 | BNO-MABU-300-IN-4024-10021-001_R01.DWG | 1,9 MB | 10/06/2025 10:00:38 |  | 11/06/2025 05:04:20 | R01 | IFR - ISSUED FOR REVIEW | 30/06/2025 06:18:40 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/25/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00197 | R01 | 06/10/2025 | BNO-MABU-SNEPCO-2025-INC-00271 | 06/11/2025 |  |  | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025 | NR | NA
BNO-MABU-300-IN-4024-10022-001 |  | ELECTRICAL INSTRUMENTATION PLAN & SSCB - BATTERY ROOM - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 30/06/2025 | 02/07/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 25/06/2025 | BNO-MABU-300-IN-4024-10022-001_R01.DWG | 1,92 MB | 10/06/2025 09:58:12 |  | 11/06/2025 05:04:20 | R01 | IFR - ISSUED FOR REVIEW | 30/06/2025 06:18:41 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/25/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00197 | R01 | 06/11/2025 | BNO-MABU-SNEPCO-2025-INC-00271 | 06/11/2025 | BNO_EXT_MABU_00646 | 06/30/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025 | NR | NA
BNO-MABU-300-IN-4024-10023-001 |  | F&G LOCATION LAYOUT COVER SHEET | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 02/06/2025 | 27/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-IN-4024-10023-001_R01.DWG | 5,34 MB | 02/06/2025 09:58:52 |  | 02/06/2025 15:55:22 | R01 | IFR - ISSUED FOR REVIEW | 20/06/2025 14:29:34 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00174 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00256 | 06/02/2025 | BNO/EXT/MABU/00623 | 6/20/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10082 | 06/27/2025 | INFO | NA
BNO-MABU-300-IN-4024-10024-001 |  | F&G LOCATION LAYOUT INDEX SHEET | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 02/06/2025 | 27/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-IN-4024-10024-001_R01.DWG | 385,73 KB | 02/06/2025 10:00:51 |  | 02/06/2025 15:55:22 | R01 | IFR - ISSUED FOR REVIEW | 20/06/2025 15:37:13 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00174 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00255 | 06/02/2025 | BNO/EXT/MABU/00621 | 6/20/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10082 | 06/27/2025 | INFO | NA
BNO-MABU-300-IN-4024-10025-001 |  | F&G LOCATION LAYOUT LEGEND SHEET | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 02/06/2025 | 27/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 16/06/2025 | BNO-MABU-300-IN-4024-10025-001_R01.DWG | 5,31 MB | 02/06/2025 10:02:43 |  | 02/06/2025 15:55:22 | R01 | IFR - ISSUED FOR REVIEW | 20/06/2025 14:29:36 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00174 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00255 | 06/02/2025 | BNO/EXT/MABU/00623 | 6/20/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10082 | 06/27/2025 | INFO | NA
BNO-MABU-300-IN-4024-10028-001 |  | F&G LOCATION LAYOUT SSCB (OUTDOOR) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/25/2025 | 6/27/2025 | 7/18/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-4024-10029-001 |  | F&G DEVICES AND JUNCTION BOX LOCATION LAYOUT - SSCB | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/25/2025 | 6/27/2025 | 7/18/2025 | [10 empty] | INFO | NA
BNO-MABU-300-IN-4024-10031-001 |  | F&G DEVICES AND JUNCTION BOX LOCATION LAYOUT - FLOWLINE CORROSION INHIBITOR SKID | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/25/2025 | 6/27/2025 | 7/18/2025 | [10 empty] | INFO | NA
BNO-MABU-300-IN-4024-10033-001 |  | PNEUMATIC & HYDRAULIC INSTRUMENTATION & AUTOMATION LOCATION LAYOUT - WATERFLOOD INJECTION PACKAGE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/25/2025 | 6/27/2025 | 7/18/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4024-10034-001 |  | PNEUMATIC & HYDRAULIC INSTRUMENTATION & AUTOMATION LOCATION LAYOUT SUBSEA WELL LAUNCHER AND RECEIVER | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/25/2025 | 6/27/2025 | 7/18/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4024-10035-001 |  | PNEUMATIC & HYDRAULIC INSTRUMENTATION & AUTOMATION LOCATION LAYOUT - PRODUCTION MANIFOLD | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/25/2025 | 6/27/2025 | 7/18/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4024-10036-001 |  | PNEUMATIC & HYDRAULIC INSTRUMENTATION & AUTOMATION LOCATION LAYOUT - WI TURBINE DIESEL DAY TANK SYSTEM | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/25/2025 | 6/27/2025 | 7/18/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4024-10037-001 |  | PNEUMATIC & HYDRAULIC INSTRUMENTATION & AUTOMATION LOCATION LAYOUT - GAS RISER LIFT METERS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/25/2025 | 6/27/2025 | 7/18/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4024-10038-001 |  | PNEUMATIC & HYDRAULIC INSTRUMENTATION & AUTOMATION LOCATION LAYOUT - FLOWLINE CORROSION INHIBITOR SYSTEM PACKAGE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/25/2025 | 6/27/2025 | 7/18/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4024-10039-001 |  | CONTROL AND EQUIPMENT ROOM LAYOUT | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4024-10042-001 |  | INSTRUMENT AND JUNCTION BOX / LOCAL CONTROL PANELS LOCATION PLAN | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | INFO | NA
BNO-MABU-300-IN-4024-10056-001 |  | ELECTRICAL & INSTRUMENTATION PLAN & LOCATION SSCB | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 30/06/2025 | 02/07/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 25/06/2025 | BNO-MABU-300-IN-4024-10056-001_R01.DWG | 1,81 MB | 10/06/2025 07:51:58 |  | 11/06/2025 04:59:39 | R01 | IFR - ISSUED FOR REVIEW | 30/06/2025 06:18:43 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/25/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00197 | R01 | 06/10/2025 | BNO-MABU-SNEPCO-2025-INC-00269 | 06/11/2025 | BNO_EXT_MABU_00646 | 06/30/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025 | NR | NA
BNO-MABU-300-IN-4024-10057-001 |  | ELECTRICAL & INSTRUMENTATION PLAN & LOCATION METHANOL LAYOUT INJECTION PACKAGE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 30/06/2025 | 02/07/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 25/06/2025 | BNO-MABU-300-IN-4024-10057-001_R01.DWG | 3,96 MB | 10/06/2025 07:51:18 |  | 11/06/2025 04:59:39 | R01 | IFR - ISSUED FOR REVIEW | 30/06/2025 06:18:44 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/25/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00197 | R01 | 06/10/2025 | BNO-MABU-SNEPCO-2025-INC-00269 | 06/11/2025 | BNO_EXT_MABU_00646 | 06/30/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025 | NR | NA
BNO-MABU-300-IN-4024-10060-001 |  | JUNCTION BOX TERMINATION LAYOUT | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4024-10070-001 |  | F&G DETECTION SYSTEM - FIRE ZONE COVER SHEET | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 20/05/2025 | 30/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 07/05/2025 | BNO-MABU-300-IN-4024-10070-001_R01.DWG | 5,17 MB | 20/05/2025 03:43:43 |  | 20/05/2025 07:17:08 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 05/07/2025 | 07/09/2025 | 7/30/2025 | BON-DAE-WESTPAQ-2025-TX-00119 | R01 | 5/17/2025 | BNO-MABU-SNEPCO-2025-INC-00208 | 5/20/2025 | BNO/EXT/MABU/00615 | 6/20/2025 | CODE 3 - MINOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-IN-4024-10071-001 |  | F&G DETECTION SYSTEM - FIRE ZONE LEGEND SHEET | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 20/05/2025 | 30/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 07/05/2025 | BNO-MABU-300-IN-4024-10071-001_R01.DWG | 5,19 MB | 20/05/2025 03:48:22 |  | 20/05/2025 07:17:08 | R01 | IFR - ISSUED FOR REVIEW | 24/06/2025 04:06:26 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 05/07/2025 | 07/09/2025 | 7/30/2025 | BON-DAE-WESTPAQ-2025-TX-00119 | R01 | 5/17/2025 | BNO-MABU-SNEPCO-2025-INC-00208 | 5/20/2025 | BNO/EXT/MABU/00614 | 6/19/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025 | INFO | NA
BNO-MABU-300-IN-4024-10072-001 |  | F&G DETECTION SYSTEM - FIRE ZONE WATERFLOOD INJECTION PUMP TURBINE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 20/05/2025 | 30/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 07/05/2025 | BNO-MABU-300-IN-4024-10072-001_R01.DWG | 4,94 MB | 20/05/2025 05:32:21 |  | 21/05/2025 11:30:08 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 05/07/2025 | 07/09/2025 | 7/30/2025 | BON-DAE-WESTPAQ-2025-TX-00119 | R01 | 5/17/2025 | BNO-MABU-SNEPCO-2025-INC-00217 | 5/21/2025 | BNO_EXT_MABU_00584 | 06/04/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025 | R | P2
BNO-MABU-300-IN-4024-10072-002 |  | FIRE AND GAS LOCATION LAYOUT WATERFLOOD INJECTION PUMP TURBINE PLAN AT LEVEL 2 | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | ISSUED | 20/05/2025 | 29/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 31/05/2025 | BNO-MABU-300-IN-4024-10072-002_R01.PDF | 825,28 KB | 20/05/2025 09:25:41 |  | 21/05/2025 11:30:08 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00119 | R01 | 5/20/2025 | BNO-MABU-SNEPCO-2025-INC-00217 | 5/21/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025
BNO-MABU-300-IN-4024-10073-001 |  | F&G DETECTION SYSTEM - FIRE ZONE METHANOL INJECTION PACKAGE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 20/05/2025 | 29/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 07/05/2025 | BNO-MABU-300-IN-4024-10073-001_R01.DWG | 6,88 MB | 20/05/2025 03:53:44 |  | 21/05/2025 05:12:43 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 05/07/2025 | 07/09/2025 | 7/30/2025 | BON-DAE-WESTPAQ-2025-TX-00119 | R01 | 5/17/2025 | BNO-MABU-SNEPCO-2025-INC-00211 | 5/21/2025 | BNO_EXT_MABU_00584 | 06/04/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025 | R | P2
BNO-MABU-300-IN-4024-10074-001 |  | F&G DETECTION SYSTEM - FIRE ZONE FLOWLINE CORROSION INHIBITOR SKID - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 20/05/2025 | 29/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 07/05/2025 | BNO-MABU-300-IN-4024-10074-001_R01.DWG | 2,15 MB | 20/05/2025 05:15:28 |  | 21/05/2025 05:12:43 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 05/07/2025 | 07/09/2025 | 7/30/2025 | BON-DAE-WESTPAQ-2025-TX-00119 | R01 | 5/17/2025 | BNO-MABU-SNEPCO-2025-INC-00211 | 5/21/2025 | [5 empty] | R | P2
BNO-MABU-300-IN-4024-10075-001 |  | F&G DETECTION SYSTEM - FIRE ZONE SWITCHGEAR & SUBSEA CONTROL BUILDING | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 20/05/2025 | 29/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 07/05/2025 | BNO-MABU-300-IN-4024-10075-001_R01.DWG | 2,94 MB | 20/05/2025 05:19:09 |  | 21/05/2025 05:12:43 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 10:39:36 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 05/07/2025 | 07/09/2025 | 7/30/2025 | BON-DAE-WESTPAQ-2025-TX-00119 | R01 | 5/17/2025 | BNO-MABU-SNEPCO-2025-INC-00211 | 5/21/2025 | BNO_EXT_MABU_00590 | 06/04/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025 | R | P2
BNO-MABU-300-IN-4024-10076-001 |  | F&G DETECTION SYSTEM - FIRE ZONE SSCB (BATTERY ROOM) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 20/05/2025 | 29/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 07/05/2025 | BNO-MABU-300-IN-4024-10076-001_R01.DWG | 2,85 MB | 20/05/2025 05:26:53 |  | 21/05/2025 05:12:43 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 10:39:38 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 05/07/2025 | 07/09/2025 | 7/30/2025 | BON-DAE-WESTPAQ-2025-TX-00119 | R01 | 5/17/2025 | BNO-MABU-SNEPCO-2025-INC-00211 | 5/21/2025 | BNO_EXT_MABU_00590 | 06/04/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025 | R | P2
BNO-MABU-300-IN-4024-10077-001 |  | F&G DETECTION SYSTEM - FIRE ZONE SUBSEA WELL LAUNCHER AND RECEIVER - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 20/05/2025 | 29/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 07/05/2025 | BNO-MABU-300-IN-4024-10077-001_R01.DWG | 4,51 MB | 20/05/2025 09:32:56 |  | 21/05/2025 11:30:08 | R01 | IFR - ISSUED FOR REVIEW | 17/06/2025 10:15:27 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 05/07/2025 | 07/09/2025 | 7/30/2025 | BON-DAE-WESTPAQ-2025-TX-00119 | R01 | 5/17/2025 | BNO-MABU-SNEPCO-2025-INC-00217 | 5/21/2025 | BNO/EXT/MABU/00598 | 06/10/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025 | R | P2
BNO-MABU-300-IN-4024-10077-002 |  | FIRE AND GAS LOCATION LAYOUT & PLAN SUBSEA WELL LAUNCHER AND RECEIVER | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | NÃO SE APLICA | 20/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 31/05/2025 | BNO-MABU-300-IN-4024-10077-002_R01.DWG | 3,83 MB | 20/05/2025 09:40:43 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00119 | R01 | 5/20/2025 |  |  |  |  | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10084 | 07/02/2025
BNO-MABU-300-IN-4024-10078-001 |  | F&G DETECTION SYSTEM - FIRE ZONE BOARDING VALVE PANEL AND TUPA | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 20/05/2025 | 29/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 07/05/2025 | BNO-MABU-300-IN-4024-10078-001_R01.DWG | 1,79 MB | 20/05/2025 09:47:55 |  | 21/05/2025 11:30:08 | R01 | IFR - ISSUED FOR REVIEW | 17/06/2025 10:15:29 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 05/07/2025 | 07/09/2025 | 7/30/2025 | BON-DAE-WESTPAQ-2025-TX-00119 | R01 | 5/17/2025 | BNO-MABU-SNEPCO-2025-INC-00217 | 5/21/2025 | BNO/EXT/MABU/00598 | 06/10/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025 | R | P2
BNO-MABU-300-IN-4024-10078-002 |  | FIRE AND GAS LOCATION LAYOUT & PLAN BOARDING VALV PANEL & TERMINATION UMBLICAL PANEL ASSEMBLY SHT 2 | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | ISSUED | 20/05/2025 | 29/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 31/05/2025 | BNO-MABU-300-IN-4024-10078-002_R01.DWG | 1,79 MB | 20/05/2025 09:50:49 | [11 empty] | IFR - ISSUED FOR REVIEW | 05/31/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00119 | R01 | 5/17/2025 | BNO-MABU-SNEPCO-2025-INC-00323 | 06/23/2025 | BNO/EXT/MABU/00667 | 07/09/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/29/2025
BNO-MABU-300-IN-4024-10079-001 |  | FIRE AND GAS DETECTION SYSTEM FIRE ZONE INDEX SHEET | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 19/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/19/2025 | 06/09/2025 | 6/23/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4024-10080-001 |  | FIRE AND GAS DETECTION SYSTEM FIRE ZONE - WATERFLOOD INJECTION PUMP STACK LEVEL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 19/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/19/2025 | 06/09/2025 | 6/23/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4024-10081-001 |  | SAFETY PLAN - SSCB - SHEET 1 | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 19/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/19/2025 | 06/09/2025 | 6/23/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4024-10082-001 |  | SAFETY PLAN - SSCB - SHEET 2 | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 19/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/19/2025 | 06/09/2025 | 6/23/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4024-10083-001 |  | FIRE AND GAS DETECTION SYSTEM FIRE ZONE - PRODUCTION MANIFLOD | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 19/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/19/2025 | 06/09/2025 | 6/23/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4180-10003-001 |  | STANDARD INSTALLATION DRAWINGS (INSTRUMENT_ JB_ CABLE TRAY SUPPORT DRAWINGS_ EARTHING DRAWINGS ETC.) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 05/06/2025 | 07/08/2025 | 7/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4180-10004-001 |  | INSTRUMENT AND JUNCTION BOXES INSTALLATION DRAWING | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4180-10005 |  | ALARM & TRIP SCHEDULE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 25/06/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 04/07/2025 | BNO-MABU-300-IN-4180-10005_R01.XLSX | 485,43 KB | 25/06/2025 03:59:47 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/04/2025 |  |  |  | BON-DAE-WESTPAQ-2025-TX-00241 | 06/23/2025 | BNO-MABU-SNEPCO-2025-INC-00325 | 06/24/2025 | BNO/EXT/MABU/00665 | 07/09/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | R | P2
BNO-MABU-300-IN-4180-10006 |  | INSTRUMENT JUNCTION BOX SCHEDULE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4306-10002 |  | MATERIAL LIST FOR PNEUMATIC & HYDRAULIC L INSTRUMENTATION PLAN | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 03/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 04/03/2025 | 06/05/2025 | 6/26/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4306-10005 |  | MATERIAL LIST FOR PNEUMATIC & HYDRALIC HOOK UP DRAWING | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 03/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 04/03/2025 | 06/05/2025 | 6/26/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4306-10006 |  | MATERIAL LIST FOR INSTRUMENT & JUNCTION BOX SUPPORT HOOK UP ITEMS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 03/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/03/2025 | 08/05/2025 | 8/26/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4306-10009 |  | INSTRUMENTATION MTO - MISCELLANEOUS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4306-10010 |  | MATERIAL LIST FOR INSTRUMENT & JUNCTION BOX SUPPORT ITEMS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4306-10011 |  | MATERIAL LIST FOR F&G INSTRUMENTS - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4306-10012 |  | INSTRUMENT TUBING & BULK MATERIAL MTO | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4306-10015 |  | MATERIAL LIST FOR ELECTRICAL INSTRUMENTATION PLAN - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 03/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/03/2025 | 08/05/2025 | 8/26/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4306-10016 |  | MATERIAL LIST FOR PROCESS HOOK UP DRAWING | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 03/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/03/2025 | 08/05/2025 | 8/26/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4306-10017 |  | MATERIAL LIST FOR ELECTRICAL HOOK UP DRAWING - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 03/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/03/2025 | 08/05/2025 | 8/26/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4306-10018 |  | CHEMICAL INJECTION HYDRAULIC TUBING MTO | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 22/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/22/2025 | 9/23/2025 | 10/10/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4308-10001 |  | INSTRUMENTATION CABLE SCHEDULE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 07/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 05/07/2025 | 6/25/2025 | 7/16/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-4327-10001 |  | I/O LIST | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 03/06/2025 | 29/06/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 17/06/2025 | BNO-MABU-300-IN-4327-10001_R01.XLSX | 219,05 KB | 03/06/2025 06:59:22 | [11 empty] | IFR - ISSUED FOR REVIEW | 06/17/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00184 | R01 | 06/03/2025 | BNO-MABU-SNEPCO-2025-INC-00258 | 06/03/2025 | BNO/EXT/MABU/00653 | 7/3/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10083 | 06/30/2025 | INFO | NA
BNO-MABU-300-IN-4327-10002 |  | I/O MAPPING LIST (FOR PACKAGES) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 30/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/30/2025 | 07/02/2025 | 7/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-IN-4380-10001 |  | MASTER CONTROL PANEL LIST | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | INFO | NA
BNO-MABU-300-IN-4380-10002 |  | ALARM AND SET POINT LIST | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 20/06/2025 | 20/07/2025 |  | ISSUED AS CODE 4 - MAJOR COMMENTS | 100 | 04/07/2025 | BNO-MABU-300-IN-4380-10002_R01.XLSX | 161 KB | 20/06/2025 03:56:02 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00228 | R01 | 06/20/2025 | BNO/MABU-SNEPCO-2025-INC-00307 | 06/20/2025 | BNO/EXT/MABU/00667 | 07/09/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | R | P2
BNO-MABU-300-IN-4380-10003 |  | INSTRUMENT LIST | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA | 02/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 06/06/2025 | BNO-MABU-300-IN-4380-10003_R01.XLSX | 2,87 MB | 07/04/2025 02:17:14 |  | 07/04/2025 05:49:56 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 06/06/2025 | 08/08/2025 | 8/29/2025 | BON-DAE-WESTPAQ-2025-TX-00057 | R01 | 04/06/2025 | BNO-MABU-SNEPCO-2025-INC-00137 | 04/07/2025 | BNO/EXT/MABU/00521 | 4/29/2025 | 4 | BNO-MABU-DAE-2025-TN-10032 | 4/23/2025 | INFO | NA
BNO-MABU-300-IN-5505-10001 |  | CONTROL NARRATIVES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | INFO | NA
BNO-MABU-300-IN-5505-10002-001 |  | CONTROL SYSTEM BLOCK DIAGRAM | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 03/07/2025 | 27/07/2025 |  |  | 100 | 16/07/2025 | BNO-MABU-300-IN-5505-10002-001_R01.DWG | 280,76 KB | 03/07/2025 14:09:30 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00302 | R01 | 07/03/2025 | BNO-MABU-SNEPCO-2025-INC-00368 | 07/03/2025 | BNO/EXT/MABU/00703 | 07/22/2025 | CODE 4 - MAJOR COMMENTS | BNO-MABU-DAE-2025-TN-10099 | 07/27/2025 | R | P2
BNO-MABU-300-IN-5507-10001 |  | ICSS NETWORK DESIGN SPECIFICATION (FDS) - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 30/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/30/2025 | 07/02/2025 | 7/23/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-5507-10002 |  | ICSS SECURITY DESIGN SPECIFICATION (FDS) - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA | 14/03/2025 |  |  |  | 0 | 30/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/30/2025 | 07/02/2025 | 7/23/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-5507-10003 |  | ICSS NETWORK MANAGEMENT DESIGN SPECIFICATION (FDS) - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA | 14/03/2025 |  |  |  | 0 | 30/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/30/2025 | 07/02/2025 | 7/23/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-5680-10001 |  | IP(F) NARRATIVES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ENG_IFR COMMENTS - MABU | 14/07/2025 |  | EDNO.MAGALHAES |  | 50 | 28/07/2025 | BNO-MABU-300-IN-5680-10001_R01.DOCX | 837,8 KB | 14/07/2025 06:22:33 | [11 empty] | IFR - ISSUED FOR REVIEW | 5/28/2025 | 7/30/2025 | 8/20/2025 | BON-DAE-WESTPAQ-2025-TX-00357 | R01 | 07/14/2025 | BNO-MABU-SNEPCO-2025-INC-00404 | 07/14/2025 | [5 empty] | INFO | NA
BNO-MABU-300-IN-5880-10002 |  | FUNCTIONAL SAFETY MANAGEMENT PLAN | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 07/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 05/07/2025 | 6/25/2025 | 7/16/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-6067-10001 |  | FAT_ SAT TESTING PROCEDURES FOR PROCESS AUTOMATION SYSTEMS (HARDWARE_ SOFTWARE) AND PCD SECURITY | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/25/2025 | 8/27/2025 | 9/17/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-6067-10002 |  | FAT_ SAT TESTING PROCEDURES FOR SAFEGUARDING SYSTEMS (HARDWARE_ SOFTWARE) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/25/2025 | 8/27/2025 | 9/17/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-6067-10003 |  | FAT_ SAT TESTING PROCEDURES FOR FIRE & GAS CONTROL SYSTEMS (HARDWARE_ SOFTWARE) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/25/2025 | 8/27/2025 | 9/17/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-6067-10004 |  | FAT_ SAT TESTING PROCEDURES FOR ALARM MANAGEMENT SYSTEMS (HARDWARE_ SOFTWARE) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/25/2025 | 8/27/2025 | 9/17/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-6067-10005 |  | THIRD PARTY PACKAGE INTEGRATED FAT TESTING PROCEDURES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/25/2025 | 8/27/2025 | 9/17/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-6180-10001 |  | COMMISSIONING PROCEDURES FOR PROCESS AUTOMATION SYSTEMS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/25/2025 | 8/27/2025 | 9/17/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-6180-10002 |  | COMMISSIONING PROCEDURES FOR SAFEGUARDING SYSTEM | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/25/2025 | 8/27/2025 | 9/17/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-6180-10003 |  | OPERATIONS/MAINTENANCE PROCEEDURES FOR PROCESS AUTOMATION AND PCD IT SECURITY SYSTEMS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/25/2025 | 8/27/2025 | 9/17/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-6180-10004 |  | OPERATION / MAINTENANCE PROCEDURES FOR SAFETY SYSTEMS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/25/2025 | 8/27/2025 | 9/17/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-6180-10005 |  | FINAL SIF TEST PROCEDURES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | INFO | NA
BNO-MABU-300-IN-6604-10001-001 |  | PROCESS AND ESS CAUSE AND EFFECT DIAGRAMS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | ISSUED | 29/06/2025 | 22/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 11/07/2025 | BNO-MABU-300-IN-6604-10001-001_R01.XLSX | 1,4 MB | 29/06/2025 12:45:06 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00270 | R01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00353 | 06/29/2025 | BNO/EXT/MABU/00703 (OVERDUE) | 07/22/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10097 | 07/22/2025 | R | P2
BNO-MABU-300-IN-6604-10003-001 |  | F&G CAUSE AND EFFECT DIAGRAMS - DETAIL PHASE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 07/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 05/07/2025 | 07/09/2025 | 7/30/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-6612-10001 |  | ICSS ASSET REGISTER | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 30/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/30/2025 | 07/02/2025 | 7/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-IN-7180-10003 |  | ALARM RATIONALISATION WORKSHOP - REPORT | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/25/2025 | 9/26/2025 | 10/17/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7180-10004 |  | GAS LIFT MANIFOLD DOCUMENTS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 13/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/13/2025 | 10/15/2025 | 9/22/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7180-10005 |  | CONTROL VALVES SIZING CALCULATION | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 12/07/2025 |  | ARY.CARVALHO |  | 50 | 25/07/2025 | BNO-MABU-300-IN-7180-10005_R01.DOCX | 1,08 MB | 12/07/2025 05:25:35 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/25/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00345 | R01 | 07/11/2025 | BNO-MABU-SNEPCO-2025-INC-00392 | 07/11/2025
BNO-MABU-300-IN-7180-10007 |  | INSTRUMENT POWER CONSUMPTION CALCULATION | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | DCC_IFR RECEIVED FROM ASSAI | 12/07/2025 |  | F.NEVES |  | 50 | 04/08/2025 | BNO-MABU-300-IN-7180-10007_R01.DOCX | 799,67 KB | 12/07/2025 05:38:36 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/25/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00391 | R01 | 07/22/2025 | BNO-MABU-SNEPCO-2025-INC-00429 | 07/22/2025 | BNO/EXT/MABU/00720 | 07/28/2025 | CODE 3 - MINOR COMMENTS
BNO-MABU-300-IN-7180-10010 |  | PRESSURE RELIEF VALVES SIZING CALCULATION | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 12/07/2025 |  | ARY.CARVALHO |  | 50 | 25/07/2025 | BNO-MABU-300-IN-7180-10010_R01.DOCX | 1 MB | 12/07/2025 05:25:40 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/25/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00345 | R01 | 07/11/2025 | BNO-MABU-SNEPCO-2025-INC-00392 | 07/11/2025
BNO-MABU-300-IN-7180-10011 |  | RESTRICTION ORIFICE SIZING CALCULATION - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A0 | 0 | ENG_IFR COMMENTS - MABU | 19/07/2025 |  | EDNO.MAGALHAES,FLAVIAMORAES.FRM |  | 50 | 01/08/2025 | BNO-MABU-300-IN-7180-10011_R01.DOCX | 952,33 KB | 19/07/2025 04:40:39 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/19/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00386 | R01 | 07/19/2025 | BNO-MABU-SNEPCO-2025-INC-00421 | 07/19/2025
BNO-MABU-300-IN-7180-10013 | THIS SUPERSEDES WITH UPDATED DOCTYPE. | THERMOWELLS SIZING CALCULATION | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 11/07/2025 |  | ARY.CARVALHO |  | 50 | 25/07/2025 | BNO-MABU-300-IN-7180-10013_R01.DOCX | 2,02 MB | 11/07/2025 05:22:16 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/25/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00346 | R01 | 07/11/2025 | BNO-MABU-SNEPCO-2025-INC-00391 | 07/11/2025 | BNO/EXT/MABU/00720 (OVERDUE) | 07/28/2025 | CODE 3 - MINOR COMMENTS
BNO-MABU-300-IN-7303-10001 |  | MATERIAL REQUISITION FOR PIG SIGNALER | IN - INSTRUMENTATION | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 22/07/2025 |  | ARY.CARVALHO |  | 100 | 04/08/2025 | BNO-MABU-300-IN-7303-10001_A01.DOCX | 810,11 KB | 22/07/2025 03:14:46 | [11 empty] | IFA - ISSUED FOR APPROVAL | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00391 | A01 | 07/22/2025 | BNO-MABU-SNEPCO-2025-INC-00429 | 07/22/2025 |  |  |  |  | 07/17/2025 | NR | NA
BNO-MABU-300-IN-7303-10002 |  | MATERIAL REQUISITION SAND DETECTOR | IN - INSTRUMENTATION | A01 | 3 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 22/07/2025 |  | ARY.CARVALHO |  | 100 | 04/08/2025 | BNO-MABU-300-IN-7303-10002_A01.DOCX | 809,78 KB | 22/07/2025 03:30:28 | [11 empty] | IFA - ISSUED FOR APPROVAL | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00391 | A01 | 07/22/2025 | BNO-MABU-SNEPCO-2025-INC-00429 | 07/22/2025 | BNO/EXT/MABU/00673 | 07/11/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-IN-7303-10004 |  | MATERIAL REQUISITION MAIN AUTOMATION CONTRACTOR | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/07/2025 | BNO-MABU-300-IN-7303-10004_R01.DOCX | 880,2 KB | 12/07/2025 06:01:43 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/25/2025 | 08/06/2025 | 8/27/2025 | BON-DAE-WESTPAQ-2025-TX-00352 | R01 | 07/11/2025 | BNO-MABU-SNEPCO-2025-INC-00394 | 07/11/2025 | BNO/EXT/MABU/00720 (OVERDUE) | 07/28/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-IN-7303-10005 |  | MATERIAL REQUISITION FOR HEAT AND SMOKE DETECTORS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/04/2025 | 08/06/2025 | 8/27/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7303-10006 |  | MATERIAL REQUISITION BOARDING VALVES PANEL | IN - INSTRUMENTATION | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | DCC_IFR RECEIVED FROM ASSAI | 25/07/2025 |  | F.NEVES |  | 100 | 08/08/2025 | BNO-MABU-300-IN-7303-10006_A01.DOCX | 811,4 KB | 25/07/2025 07:49:24 | [11 empty] | IFA - ISSUED FOR APPROVAL | 07/18/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00411 | A01 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00447 | 07/25/2025 | BNO/EXT/MABU/00700 | 07/22/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | NR | NA
BNO-MABU-300-IN-7303-10007 |  | MATERIAL REQUISITION FOR HYDRAULIC MOTOR OPERATED VALVE | IN - INSTRUMENTATION | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | DCC_IFR RECEIVED FROM ASSAI | 23/07/2025 |  | F.NEVES |  | 100 | 04/08/2025 | BNO-MABU-300-IN-7303-10007_A01.DOCX | 812,45 KB | 22/07/2025 03:36:07 | [11 empty] | IFA - ISSUED FOR APPROVAL | 07/08/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00391 | A01 | 07/22/2025 | BNO-MABU-SNEPCO-2025-INC-00429 | 07/22/2025 | BNO/EXT/MABU/00671 | 07/10/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-IN-7303-10008 |  | MATERIAL REQUISITION FOR ULTRASONIC FLOWMETER | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 29/06/2025 | 17/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 11/07/2025 | BNO-MABU-300-IN-7303-10008_R01.DOCX | 815,49 KB | 29/06/2025 12:34:34 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00270 | R01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00353 | 06/29/2025 | BNO/EXT/MABU/00672 | 07/11/2025 | CODE 2 - NO COMMENTS | BNO-MABU-DAE-2025-TN-10103 | 07/29/2025 | NR | NA
BNO-MABU-300-IN-7303-10009 |  | MATERIAL REQUISITION FOR PNEUMATIC ACTUATED ON-OFF_ BLOWDOWN AND SHUTDOWN VALVES | IN - INSTRUMENTATION | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 22/07/2025 |  | ARY.CARVALHO |  | 100 | 04/08/2025 | BNO-MABU-300-IN-7303-10009_A01.DOCX | 815,86 KB | 22/07/2025 02:51:21 | [11 empty] | IFA - ISSUED FOR APPROVAL | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00395 | A01 | 07/22/2025 | BNO-MABU-SNEPCO-2025-INC-00429 | 07/22/2025 | [5 empty] | NR | NA
BNO-MABU-300-IN-7303-10010 |  | MATERIAL REQUISITION FOR PRESSURE INDICATING TRANSMITTER AND DIFFERENTIAL PRESSURE INDICATING TRANSMITTER | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/04/2025 | 08/06/2025 | 8/27/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7303-10011 |  | MATERIAL REQUISITION FOR CONTROL VALVE | IN - INSTRUMENTATION | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | DCC_IFR RECEIVED FROM ASSAI | 12/07/2025 |  | F.NEVES |  | 50 | 25/07/2025 | BNO-MABU-300-IN-7303-10011_A01.DOCX | 811,97 KB | 12/07/2025 06:14:40 | [11 empty] | IFA - ISSUED FOR APPROVAL | 07/18/2025 | 07/25/2025 |  | BON-DAE-WESTPAQ-2025-TX-00353 | A01 | 07/11/2025 | BNO-MABU-SNEPCO-2025-INC-00396 | 07/11/2025 | [5 empty] | NR | NA
BNO-MABU-300-IN-7303-10012 |  | MATERIAL REQUISITION FOR PRESSURE RELIEF VALVE | IN - INSTRUMENTATION | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 22/07/2025 |  | ARY.CARVALHO |  | 100 | 04/08/2025 | BNO-MABU-300-IN-7303-10012_A01.DOCX | 813,68 KB | 22/07/2025 02:57:43 | [11 empty] | IFA - ISSUED FOR APPROVAL | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00395 | A01 | 07/22/2025 | BNO-MABU-SNEPCO-2025-INC-00429 | 07/22/2025 | [5 empty] | NR | NA
BNO-MABU-300-IN-7303-10013 |  | MATERIAL REQUISITION TEMPERATURE INDICATING TRANSMITTER | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 26/06/2025 | 17/07/2025 |  | ISSUED AS CODE 2 - NO COMMENTS | 100 | 07/07/2025 | BNO-MABU-300-IN-7303-10013_R01.DOCX | 810,1 KB | 26/06/2025 01:52:15 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/07/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00248 | R01 | 06/23/2025 | BNO-MABU-SNEPCO-2025-INC-00325 | 06/24/2025 | BNO/EXT/MABU/00671 (OVERDUE) | 07/10/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10093 | 07/17/2025 | NR | NA
BNO-MABU-300-IN-7303-10014 |  | MATERIAL REQUISITION FOR CORROSION DETECTOR | IN - INSTRUMENTATION | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 100 | 04/08/2025 | BNO-MABU-300-IN-7303-10014_A01.DOCX | 813,56 KB | 22/07/2025 03:46:49 | [11 empty] | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00391 | A01 | 07/22/2025 | BNO/MABU-SNEPCO-2025-INC-00429 | 07/22/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-IN-7303-10015 |  | MATERIAL REQUISITION FOR PRESSURE GAUGE | IN - INSTRUMENTATION | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 100 | 04/08/2025 | BNO-MABU-300-IN-7303-10015_A01.DOCX | 812,07 KB | 22/07/2025 03:48:06 | [11 empty] | IFA - ISSUED FOR APPROVAL | 07/09/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00391 | A01 | 07/22/2025 | BNO-MABU-SNEPCO-2025-INC-00429 | 07/22/2025 | BNO/EXT/MABU/00682 | 07/14/2025 | CODE 2 - NO COMMENTS |  |  | NR | NA
BNO-MABU-300-IN-7303-10016 |  | MATERIAL REQUISITION FOR TEMPERATURE GAUGE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 27/06/2025 | 17/07/2025 |  | ISSUED AS CODE 2 - NO COMMENTS | 100 | 11/07/2025 | BNO-MABU-300-IN-7303-10016_R01.DOCX | 811,11 KB | 27/06/2025 06:22:41 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00268 | R01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00348 | 06/27/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10093 | 07/17/2025 | NR | NA
BNO-MABU-300-IN-7303-10017 |  | MATERIAL REQUISITION FOR RESTRICTION ORIFICE | IN - INSTRUMENTATION | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | DCC_IFR RECEIVED FROM ASSAI | 23/07/2025 |  | F.NEVES |  | 100 | 06/08/2025 | BNO-MABU-300-IN-7303-10017_A01.DOCX | 810,04 KB | 23/07/2025 05:51:30 | [11 empty] | IFA - ISSUED FOR APPROVAL | 06/26/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00402 | A01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00435 | 07/23/2025 | [5 empty] | NR | NA
BNO-MABU-300-IN-7303-10018 |  | MATERIAL REQUISITION FOR CORIOLIS FLOWMETER | IN - INSTRUMENTATION | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 28/07/2025 |  | ARY.CARVALHO |  | 100 | 11/08/2025 | BNO-MABU-300-IN-7303-10018_A01.DOCX | 811,65 KB | 28/07/2025 06:37:09 | [11 empty] | IFA - ISSUED FOR APPROVAL | 07/09/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00418 | A01 | 07/28/2025 | BNO/MABU-SNEPCO-2025-INC-00454 | 07/28/2025 | BNO/EXT/MABU/00672 | 07/11/2025 | CODE 2 - NO COMMENTS | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | NR | NA
BNO-MABU-300-IN-7303-10019 |  | MATERIAL REQUISITION FOR HYDRAULIC HAND VALVE AND SHUTDOWN VALVE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 27/06/2025 | 17/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 11/07/2025 | BNO-MABU-300-IN-7303-10019_R01.DOCX | 815,2 KB | 27/06/2025 06:26:43 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00268 | R01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00348 | 06/27/2025 | BNO/EXT/MABU/00671 (OVERDUE) | 07/10/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10093 | 07/17/2025 | NR | NA
BNO-MABU-300-IN-7303-10020 |  | MATERIAL REQUISITION FOR HYDRAULIC BOARDING SHUTDOWN VALVE | IN - INSTRUMENTATION | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | DCC_IFR RECEIVED FROM ASSAI | 23/07/2025 |  | F.NEVES |  | 100 | 06/08/2025 | BNO-MABU-300-IN-7303-10020_A01.DOCX | 811,41 KB | 23/07/2025 05:59:14 | [11 empty] | IFA - ISSUED FOR APPROVAL | 07/09/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00435 | A01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00402 | 07/23/2025 | [5 empty] | NR | NA
BNO-MABU-300-IN-7303-10021 |  | MATERIAL REQUISITION FOR POINT TYPE GAS DETECTOR | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 02/07/2025 | 17/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 15/07/2025 | BNO-MABU-300-IN-7303-10021_R01.DOCX | 812,85 KB | 02/07/2025 07:44:29 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/15/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00291 | R01 | 07/01/2025 | BNO-MABU-SNEPCO-2025-INC-00362 | 07/02/2025 | BNO/EXT/MABU/00705 (OVERDUE) | 07/23/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10093 | 07/17/2025 | NR | NA
BNO-MABU-300-IN-7303-10022 |  | MATERIAL REQUISITION FOR OPEN PATH GAS DETECTOR | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 03/07/2025 | 17/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 16/07/2025 | BNO-MABU-300-IN-7303-10022_R01.DOCX | 813,9 KB | 03/07/2025 12:22:52 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00296 | R01 | 07/02/2025 | BNO-MABU-SNEPCO-2025-INC-00368 | 07/03/2025 | BNO/EXT/MABU/00705 (OVERDUE) | 07/23/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10093 | 07/17/2025 | NR | NA
BNO-MABU-300-IN-7303-10023 |  | MATERIAL REQUISITION FOR IR FLAME DETECTOR | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 03/07/2025 | 17/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 16/07/2025 | BNO-MABU-300-IN-7303-10023_R01.DOCX | 815,41 KB | 03/07/2025 13:29:51 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00298 | R01 | 07/16/2025 | BNO-MABU-SNEPCO-2025-INC-00368 | 07/03/2025 | BNO/EXT/MABU/00705 (OVERDUE) | 07/23/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10093 | 07/17/2025 | NR | NA
BNO-MABU-300-IN-7303-10024 |  | MATERIAL REQUISITION FOR MANUAL ALARM CALL POINT | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 17/06/2025 | 20/07/2025 |  | ISSUED AS CODE 2 - NO COMMENTS | 100 | 30/06/2025 | BNO-MABU-300-IN-7303-10024_R01.DOCX | 807,98 KB | 17/06/2025 02:21:18 | [11 empty] | IFR - ISSUED FOR REVIEW | 06/30/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00214 | R01 | 06/17/2025 | BNO-MABU-SNEPCO-2025-INC-00293 | 06/17/2025 | BNO/EXT/MABU/00665 | 07/09/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | NR | NA
BNO-MABU-300-IN-7303-10025 |  | MATERIAL REQUISITION FOR SOUNDER AND BEACON ALARMS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 02/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/02/2025 | 08/04/2025 | 8/25/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7303-10026 |  | MATERIAL REQUISITION FOR INSTRUMENTATION CABLES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 10/07/2025 | 29/07/2025 |  |  | 100 | 23/07/2025 | BNO-MABU-300-IN-7303-10026_R01.DOCX | 825,48 KB | 10/07/2025 07:05:56 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/23/2025 | 08/04/2025 | 8/25/2025 | BON-DAE-WESTPAQ-2025-TX-00335 | R01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00387 | 07/09/2025 | BNO/EXT/MABU/00720 (OVERDUE) | 07/28/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025 | NR | NA
BNO-MABU-300-IN-7303-10027 |  | MATERIAL REQUISITION FOR SUPPORT | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7303-10028 |  | MATERIAL REQUISITION FOR TUBINGS AND COMPRESSION CONNSECTIONS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7303-10030 |  | MATERIAL REQUISITION FOR CABLE GLANDS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7303-10031 |  | MATERIAL REQUISITION FOR CABLES AND MULTICABLES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7303-10033 |  | MATERIAL REQUISITION FOR TUBING & BULK MATERIAL MTO | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7303-10034 |  | MATERIAL REQUISITION FOR CABLE TRAYS AND ACCESSORIES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7303-10035 |  | MATERIAL REQUISITION FOR CABLE TRAYS_ CHANNELS AND ACCESSORIES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7303-10037 |  | MATERIAL REQUISITION FOR HYDRAULIC ACTUATED_ BOARDING_ HAND AND HYDRAULIC MOTOR OPERATED VALVE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7303-10038 |  | MATERIAL REQUISITION FOR JUNCTION BOXES | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7303-10039 |  | MATERIAL REQUISITION FOR BULK & MISCELLANEOUS MATERIALS (TUBES_ FITTINGS_ AIR MANIFOLDS) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 06/06/2025 | 08/08/2025 | 8/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7303-10040 |  | MATERIAL REQUISITION FOR SMART CHOKE VALVE | IN - INSTRUMENTATION | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | DCC_IFR RECEIVED FROM ASSAI | 23/07/2025 |  | F.NEVES |  | 100 | 06/08/2025 | BNO-MABU-300-IN-7303-10040_A01.DOCX | 811,27 KB | 23/07/2025 15:59:24 | [11 empty] | IFA - ISSUED FOR APPROVAL | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00404 | A01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00443 | 07/23/2025 | [5 empty] | NR | NA
BNO-MABU-300-IN-7303-10041 |  | MATERIAL REQUISITION FOR CHEMICAL INJECTION HYDRAULIC TUBING | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 13/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/13/2025 | 8/15/2025 | 7/23/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7709-10001 |  | DESIGN SPECIFICATION FOR CONTROL_ AUTOMATION AND SAFETY SYSTEM | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA | 08/04/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 03/04/2025 | BNO-MABU-300-IN-7709-10001_R01.DOCX | 849,25 KB | 08/04/2025 08:03:31 |  | 08/04/2025 08:47:34 | R01 | IFR - ISSUED FOR REVIEW | 02/05/2025 07:57:06 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 04/03/2025 | 06/05/2025 | 6/26/2025 | BON-DAE-WESTPAQ-2025-TX-00059 | R01 | 04/08/2025 | BNO-MABU-SNEPCO-2025-INC-00139 | 04/08/2025 | BNO/EXT/MABU/00531 | 05/02/2025 | 3 | BNO-MABU-DAE-2025-TN-10034 | 05/08/2025 | R | P2
BNO-MABU-300-IN-7739-10002 |  | PACO LIFE CYCLE MANAGEMENT PLAN | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 30/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/30/2025 | 07/02/2025 | 7/23/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-7739-10004 | PRJ2501-BNO-06-INS-PT-020 | TBE FOR MAIN AUTOMATION CONTRACTOR | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ENG_IFR CONSOLIDATION | 15/05/2025 |  | ARY.CARVALHO | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 28/05/2025 | BNO-MABU-300-IN-7739-10004_R01.XLSX | 730,35 KB | 15/05/2025 11:36:36 |  | 15/05/2025 17:33:01 | R01 | IFR - ISSUED FOR REVIEW | 30/05/2025 07:14:22 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 6/16/2025 | 8/18/2025 | 09/08/2025 |  |  |  | BNO-MABU-SNEPCO-2025-INC-00201 | 5/15/2025 | BNO_EXT_MABU_00571 | 05/30/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-IN-7770-10001 |  | F&G DESIGN SPECIFICATION | IN - INSTRUMENTATION | A02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 19/07/2025 |  | ARY.CARVALHO |  | 50 | 01/08/2025 | BNO-MABU-300-IN-7770-10001_A02.DOCX | 832,83 KB | 19/07/2025 03:05:38 |  | 10/04/2025 07:20:08 | R01 | IFR - ISSUED FOR REVIEW | 08/05/2025 01:50:56 | R01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  |  |  | BON-DAE-WESTPAQ-2025-TX-00383 | A02 | 07/19/2025 | BNO-MABU-SNEPCO-2025-INC-00420 | 07/19/2025 | [5 empty] | R | P2
BNO-MABU-300-IN-7770-10002 |  | DESIGN SPECIFICATION FOR FIELD INSTRUMENTATION | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA | 05/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 03/04/2025 | BNO-MABU-300-IN-7770-10002_R01.DOCX | 894,67 KB | 27/03/2025 16:49:03 |  | 28/03/2025 11:15:19 | R01 | IFR - ISSUED FOR REVIEW | 09/04/2025 05:08:50 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 04/03/2025 | 06/05/2025 | 6/26/2025 | BON-DAE-WESTPAQ-2025-TX-00034 | R01 | 3/21/2025 | BNO-MABU-SNEPCO-2025-INC-00117 | 3/24/2025 | BNO/EXT/MABU/00495 | 04/09/2025 | 3 | BNO-MABU-DAE-2025-TN-10029 | 4/23/2025 | NR | NA
BNO-MABU-300-IN-7770-10003 |  | BOARDING VALVES PANEL SPECIFICATION | IN - INSTRUMENTATION | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 18/07/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 11/07/2025 | BNO-MABU-300-IN-7770-10003_A01.DOCX | 1,12 MB | 27/06/2025 08:44:49 |  | 10/04/2025 07:20:08 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFA - ISSUED FOR APPROVAL | 04/03/2025 | 07/11/2025 |  | BON-DAE-WESTPAQ-2025-TX-00267 | A01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00350 | 06/27/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10097 | 07/24/2025 | NR | NA
BNO-MABU-300-IN-7770-10004 |  | VENDOR SUPPLIED PACKAGES INTEGRATION DESIGN SPECIFICATION | IN - INSTRUMENTATION | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 29/06/2025 | 24/07/2025 |  |  | 100 | 11/07/2025 | BNO-MABU-300-IN-7770-10004_A01.DOCX | 1,77 MB | 29/06/2025 16:21:06 |  | 31/03/2025 12:20:18 | R01 | IDC - INTERNAL COMMENTS | [7 empty] | IFR - ISSUED FOR REVIEW | 07/25/2025 | 07/11/2025 |  | BON-DAE-WESTPAQ-2025-TX-00272 | R01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00355 | 06/29/2025 | BNO/EXT/MABU/00673 | 07/11/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10102 | 07/29/2025 | INFO | NA
BNO-MABU-300-IN-7770-10005 |  | SPECIFICATIONS FOR SIL ASSESSMENT TERMS OF REFERENCE - DETAIL PHASE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 03/07/2025 | 27/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 16/07/2025 | BNO-MABU-300-IN-7770-10005_R01.DOCX | 927,41 KB | 03/07/2025 14:20:16 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00300 | R01 | 07/03/2025 | BNO-MABU-SNEPCO-2025-INC-00368 | 07/03/2025 | BNO/EXT/MABU/00705 (OVERDUE) | 07/23/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10099 | 07/25/2025 | R | P2
BNO-MABU-300-IN-7770-10009 |  | SIF REQUIREMENT SPECIFICATION (SRS) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | R | P2
BNO-MABU-300-IN-7770-10010 |  | ALARM SYSTEM REQUIREMENTS SPECIFICATION - FINAL | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ISSUED | 18/07/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 04/07/2025 | BNO-MABU-300-IN-7770-10010_R01.DOCX | 813,87 KB | 20/06/2025 06:51:10 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/04/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00235 | R01 | 06/20/2025 | BNO/MABU-SNEPCO-2025-INC-00313 | 06/20/2025 | BNO/EXT/MABU/00665 | 07/09/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10095 | 07/20/2025 | R | P2
BNO-MABU-300-IN-7771-10001 | PRJ2501-BNO-06-INS-PT-022 | TECHNICAL BID EVALUATION FOR HYDRAULIC HAND VALVE AND SHUTDOWN VALVE | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | ENG_IFR CONSOLIDATION | 15/05/2025 |  | ARY.CARVALHO | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 23/05/2025 | BNO-MABU-300-IN-7771-10001_R01.ZIP | 7,1 MB | 15/05/2025 11:33:13 |  | 15/05/2025 17:33:01 | R01 | IFR - ISSUED FOR REVIEW | 29/05/2025 09:48:21 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 6/16/2025 | 8/18/2025 | 09/08/2025 |  |  |  | BNO-MABU-SNEPCO-2025-INC-00201 | 5/15/2025 | BNO/EXT/MABU/00569 | 5/29/2025 | 3 |  |  | INFO | NA
BNO-MABU-300-IN-8380-10001 |  | PANEL THERMAL DISPERSION (INTERNAL DOCUMENT) | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/16/2025 | 8/18/2025 | 09/08/2025 | [10 empty] | NR | NA
BNO-MABU-300-IN-8502-10001 |  | RFI (CONTROL NARATIVES) | IN - INSTRUMENTATION | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A0 | 0 | ENGINEERING CONSOLIDATION | 10/07/2025 |  | ARY.CARVALHO |  | 0 | 24/07/2025 | BNO-MABU-300-IN-8502-10001=A01.DOCX | 170,43 KB | 10/07/2025 15:52:15 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00339 | A01 | 07/10/2025 | N/A
BNO-MABU-300-IN-8880-10001-001 |  | INSTRUMENT WIRING DIAGRAMS | IN - INSTRUMENTATION | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.13-IN-INSTRUMENTATION | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 25/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 4/25/2025 | 6/27/2025 | 7/18/2025 | [10 empty] | NR | NA
BNO-MABU-300-JA-3375-10002-001 |  | 3D MODEL REVIEW FILE | JA - IM | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.14-JA-INFORMATION MNGM | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 28/05/2025 |  | GABRIEL.SILVA |  | 50 | 11/06/2025 | BNO-MABU-300-JA-3375-10002-001_R01.XLSM | 8,24 MB | 28/05/2025 09:34:07 |  |  |  |  | 21/06/2025 05:05:21 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/11/2025 |  |  | IPMT DELIVERABLE FROM ENGR GABRIEL SILVA | N/A | N/A | BNO-MABU-SNEPCO-2025-INC-00238 | 5/28/2025
BNO-MABU-300-JA-5798-10001 |  | E3D MODELING EXECUTION PLAN | JA - IM | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.14-JA-INFORMATION MNGM | A4 | 0 | ISSUED | 13/06/2025 | 30/07/2025 |  |  | 100 | 27/06/2025 | BNO-MABU-300-JA-5798-10001_A01.DOCX | 2,93 MB | 13/06/2025 06:31:38 |  |  |  |  | 04/06/2025 08:16:54 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00201 | A01 | 06/13/2025 | BNO-MABU-SNEPCO-2025-INC-00290 | 06/16/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10102 | 07/29/2025 | NR | NA
BNO-MABU-300-JA-5798-10002 |  | SMARTPLANT P&ID DESIGN EXECUTION PLAN | JA - IM | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.14-JA-INFORMATION MNGM | A4 | 0 | ISSUED | 17/06/2025 | 30/07/2025 |  |  | 100 | 01/07/2025 | BNO-MABU-300-JA-5798-10002_A01.DOCX | 1,34 MB | 17/06/2025 15:15:18 |  | 22/05/2025 09:56:37 | R01 | IFR - ISSUED FOR REVIEW | 21/06/2025 05:05:22 | A01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  | 06/17/2025 |  | BON-DAE-WESTPAQ-2025-TX-00213 | A01 | 06/17/2025 | BNO-MABU-SNEPCO-2025-INC-00294 | 06/17/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10102 | 07/29/2025 | NR | NA
BNO-MABU-300-JA-5798-10002-002 |  | 3D MODEL | JA - IM | R02 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.29-3D MODEL / 02.29.01-DAE MODELS | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | BNO-MABU-300-JA-5798-10002-002_R02.ZIP | 109,62 MB | 22/05/2025 10:50:21 | [11 empty] | IFR - ISSUED FOR REVIEW | [6 empty] | BNO-MABU-SNEPCO-2025-INC-00207 | 5/22/2025
BNO-MABU-300-JA-5798-10003 |  | SMARTPLANT INSTRUMENTATION DESIGN EXECUTION PLAN | JA - IM | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.14-JA-INFORMATION MNGM | A4 | 0 | ENG_IFR COMMENTS - MABU | 25/06/2025 |  | GABRIEL.SILVA |  | 50 | 08/07/2025 | BNO-MABU-300-JA-5798-10003_A01.DOCX | 1,47 MB | 25/06/2025 09:55:23 |  | 22/05/2025 09:56:37 | R01 | IFR - ISSUED FOR REVIEW | 24/06/2025 09:11:59 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 04/08/2025 | 07/08/2025 |  | BON-DAE-WESTPAQ-2025-TX-00247 | A01 | 06/24/2025 | BNO-MABU-SNEPCO-2025-INC-00324 | 06/24/2025 | [5 empty] | NR | NA
BNO-MABU-300-JA-6017-10001 |  | INFORMATION QUALITY MANAGEMENT SYSTEM (IQMS) | JA - IM | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.14-JA-INFORMATION MNGM | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 08/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 04/08/2025 | 5/27/2025 | 6/17/2025 | [10 empty] | NR | NA
BNO-MABU-300-JA-6611-10002 | BNO-MABU-300-JA-6611-10001 (DAE) | DAE MASTER DOCUMENT REGISTER | JA - IM | R05 | 3 | BNO - BONGA NORTH | BNO / 02-DED / 02.14-JA-INFORMATION MNGM | A4 | 0 | ENG_IFR CONSOLIDATION |  |  | F.NEVES |  | 85 | 01/04/2025 | BNO-MABU-300-JA-6611-10002_R05.XLSX | 588,35 KB | 29/07/2025 08:28:26 |  | 17/06/2025 08:07:45 | A01 | IFA - ISSUED FOR APPROVAL | 17/04/2025 14:26:03 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFI - ISSUED FOR INFORMATION | 03/11/2025 | 07/31/2025 | 08/21/2025 | BON-DAE-WESTPAQ-2025-TX-0389 | R05 |  | NOT TO BE ISSUED ON ASSAI
BNO-MABU-300-KA-5798-10002-001 |  | PCD NETWORK ARCHITECTURE DRAWING (PHYSICAL & LOGICAL) | KA - IT | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.15-KA-IT | A3 | 0 | ISSUED | 09/07/2025 | 30/07/2025 |  |  | 100 | 23/07/2025 | BNO-MABU-300-KA-5798-10002-001_R01.DWG | 6,19 MB | 09/07/2025 02:36:50 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/23/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00326 | R01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00381 | 07/09/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025 | INFO | NA
BNO-MABU-300-KA-5798-10003-001 |  | PCD PI NETWORK ARCHITECTURE DRAWING | KA - IT | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.15-KA-IT | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 17/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/17/2025 | 08/05/2025 | 8/22/2025 | [10 empty] | INFO | NA
BNO-MABU-300-KA-5798-10004 |  | INFORMATION TECHNOLOGY (IT) PLAN | KA - IT | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.15-KA-IT | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 15/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/15/2025 | 07/03/2025 | 7/22/2025 | [10 empty] | NR | NA
BNO-MABU-300-KA-5980-10001 |  | PCD ASSET REGISTER | KA - IT | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.15-KA-IT | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 07/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 05/07/2025 | 6/25/2025 | 7/14/2025 | [10 empty] | INFO | NA
BNO-MABU-300-KA-7739-10001 |  | PCD NETWORK CABLE SCHEDULE | KA - IT | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.15-KA-IT | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 14/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/14/2025 | 07/02/2025 | 7/21/2025 | [10 empty] | NR | NA
BNO-MABU-300-KA-7739-10003 |  | BONGA NORTH PCD NETWORK DESIGN SPECIFICATION - FINAL | KA - IT | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.15-KA-IT | A4 | 0 | ISSUED | 26/05/2025 | 21/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 06/06/2025 | BNO-MABU-300-KA-7739-10003_R01.DOCX | 1,84 MB | 26/05/2025 01:45:25 |  | 27/05/2025 09:45:07 | R01 | IFR - ISSUED FOR REVIEW | 17/06/2025 09:50:49 | R01 | 2-NO COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/06/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00141 | R01 | 5/23/2025 | BNO-MABU-SNEPCO-2025-INC-00235 | 5/27/2025 | BNO/EXT/MABU/00596 | 06/10/2025 | CODE 2 - NO COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025 | R | P2
BNO-MABU-300-KA-7739-10004 |  | BONGA NORTH PCD - IT SECURITY DESIGN SPECIFICATION - FINAL | KA - IT | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.15-KA-IT | A4 | 0 | ISSUED | 29/06/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 11/07/2025 | BNO-MABU-300-KA-7739-10004_R01.DOCX | 1,15 MB | 29/06/2025 10:26:55 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00270 | R01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00353 | 06/29/2025 | BNO_EXT_MABU_00695 | 07/17/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10084 | 07/02/2025 | R | P2
BNO-MABU-300-KA-7739-10005 |  | PCD 3RD PARTY NETWORK INTEGRATION DESIGN SPECIFICATION - FINAL | KA - IT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.15-KA-IT | A4 | 0 | ISSUED | 21/07/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 25/07/2025 | BNO-MABU-300-KA-7739-10005_A01.DOCX | 1,48 MB | 12/07/2025 06:20:10 |  |  |  |  | 05/06/2025 09:51:35 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 4/30/2025 | 07/25/2025 |  | BON-DAE-WESTPAQ-2025-TX-00354 | A01 | 07/11/2025 | BNO-MABU-SNEPCO-2025-INC-00396 | 07/11/2025 | BNO/EXT/MABU/00728 (OVERDUE) | 07/28/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10098 | 07/24/2025 | INFO | NA
BNO-MABU-300-KA-7739-10006 |  | PCD NETWORK MANAGEMENT DESIGN SPECIFICATION - FINAL | KA - IT | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.15-KA-IT | A4 | 0 | ISSUED | 21/07/2025 | 30/07/2025 |  |  | 100 | 25/07/2025 | BNO-MABU-300-KA-7739-10006_A01.DOCX | 1,79 MB | 12/07/2025 06:34:27 |  |  |  |  | 05/06/2025 09:51:36 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 05/05/2025 | 07/25/2025 |  | BON-DAE-WESTPAQ-2025-TX-00354 | A01 | 07/11/2025 | BNO-MABU-SNEPCO-2025-INC-00396 | 07/11/2025 | BNO/EXT/MABU/00728 (OVERDUE) | 07/28/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025 | INFO | NA
BNO-MABU-300-KA-7739-10007 |  | PCD DMZ (SECUREPCD) INTEGRATION AND CONFIGURATION DETAILS | KA - IT | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.15-KA-IT | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 12/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 05/12/2025 | 6/30/2025 | 7/17/2025 | [10 empty] | INFO | NA
BNO-MABU-300-KA-7880-10001 |  | PCD HANDOVER PLAN | KA - IT | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.15-KA-IT | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 03/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 07/03/2025 | 8/21/2025 | 09/09/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-1206-10002 |  | SPRING SUPPORTS SCHEDULE | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 19/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/19/2025 | 10/07/2025 | 10/24/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-1206-10004 |  | API 10000 PRESSURE RATING WALL THICKNESS CALCULATION REPORT | MP - PIPING | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 29/07/2025 |  | ANDREA.SANTOS |  | 50 | 12/08/2025 | BNO-MABU-300-MP-1206-10004_A01.DOCX | 1,18 MB | 29/07/2025 09:05:01 |  | 01/04/2025 05:46:19 | R01 | IFR - ISSUED FOR REVIEW | 07/05/2025 20:46:55 | R01 | 3-MINOR COMMENTS | 01/01/1900 |  |  |  | IFA - ISSUED FOR APPROVAL | 04/01/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00424 | A01 | 07/29/2025 | BNO/MABU-SNEPCO-2025-INC-00462 | 07/29/2025 | BNO/EXT/MABU/00497 | 04/10/2025 |  | BNO-MABU-DAE-2025-TN-10087 | 07/07/2025 | R | P2
BNO-MABU-300-MP-2105-10001 |  | PIPING DATASHEETS FOR LARGE BORE BALL VALVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ENG_IFR CONSOLIDATION | 17/06/2025 |  | ANDREA.SANTOS |  | 50 | 01/07/2025 | BNO-MABU-300-MP-2105-10001_R01.XLSX | 208,83 KB | 17/06/2025 07:33:50 | [11 empty] | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00210 | R01 | 06/17/2025 | BNO-MABU-SNEPCO-2025-INC-00286 | 06/17/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-MP-2105-10002 |  | PIPING DATASHEETS FOR DOUBLE BLOCK AND BLEED VALVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ENG_IFR CONSOLIDATION | 17/06/2025 |  | ANDREA.SANTOS | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 01/07/2025 | BNO-MABU-300-MP-2105-10002_R01.XLSX | 286,99 KB | 17/06/2025 17:03:16 | [11 empty] | IFA - ISSUED FOR APPROVAL | 07/01/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00212 | R01 | 06/17/2025 | BNO-MABU-SNEPCO-2025-INC-00295 | 06/17/2025 | BNO/EXT/MABU/00678 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-MP-2105-10003 |  | PIPING DATASHEETS FOR QUICK CONNECT - DISCONNECT COUPLING | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 19/06/2025 |  | ANDREA.SANTOS |  | 50 | 04/07/2025 | BNO-MABU-300-MP-2105-10003_R01.XLSX | 111,07 KB | 19/06/2025 09:58:26 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/04/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00226? | R01 | 06/19/2025 | BNO/MABU-SNEPCO-2025-INC-00304 | 06/19/2025 | [5 empty] | R | P2
BNO-MABU-300-MP-2105-10004 |  | PIPING DATASHEETS FOR LARGE BORE CHECK VALVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ENG_IFR CONSOLIDATION | 17/06/2025 |  | ANDREA.SANTOS |  | 50 | 01/07/2025 | BNO-MABU-300-MP-2105-10004_R01.XLSX | 146,68 KB | 17/06/2025 07:35:28 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00210 | R01 | 06/17/2025 | BNO-MABU-SNEPCO-2025-INC-00286 | 06/17/2025 | BNO/EXT/MABU/00678 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-MP-2105-10005 |  | PIPING DATASHEETS FOR GLOBE VALVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 17/06/2025 |  | ANDREA.SANTOS |  | 50 | 01/07/2025 | BNO-MABU-300-MP-2105-10005_R01.XLSX | 145,59 KB | 17/06/2025 07:37:04 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00210 | R01 | 06/17/2025 | BNO-MABU-SNEPCO-2025-INC-00286 | 06/17/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-MP-2105-10006 |  | PIPING DATASHEETS FOR SMALL BORE BALL VALVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 17/06/2025 |  | ANDREA.SANTOS |  | 50 | 01/07/2025 | BNO-MABU-300-MP-2105-10006_R01.XLSX | 154,88 KB | 17/06/2025 07:38:43 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00210 | R01 | 06/17/2025 | BNO-MABU-SNEPCO-2025-INC-00286 | 06/17/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-MP-2105-10007 |  | PIPING DATASHEETS FOR BUTTERFLY VALVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 17/06/2025 |  | ANDREA.SANTOS |  | 50 | 01/07/2025 | BNO-MABU-300-MP-2105-10007_R01.XLSX | 113,6 KB | 17/06/2025 17:08:33 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/01/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00212 | R01 | 06/17/2025 | BON-DAE-WESTPAQ-2025-TX-00212 | 06/17/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-MP-2105-10008 |  | PIPING DATASHEETS FOR SMALL BORE CHECK VALVE | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 17/06/2025 |  | ANDREA.SANTOS,EDSON.BARBOSA |  | 50 | 01/07/2025 | BNO-MABU-300-MP-2105-10008_R01.XLSX | 113,97 KB | 17/06/2025 07:40:10 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00210 | R01 | 06/17/2025 | BNO-MABU-SNEPCO-2025-INC-00286 | 06/17/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-MP-2105-10009 |  | PIPING DATASHEETS FOR INSULATING GASKET SET | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ISSUED | 20/06/2025 | 27/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 04/07/2025 | BNO-MABU-300-MP-2105-10009_R01.XLSX | 191,64 KB | 20/06/2025 04:18:47 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00229 | R01 | 06/20/2025 | BNO/MABU-SNEPCO-2025-INC-00308 | 06/20/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10102 | 07/29/2025 | R | P2
BNO-MABU-300-MP-2105-10010 |  | PIPING DATASHEETS FOR BARRED TEE | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ENG_IFR CONSOLIDATION | 30/05/2025 |  | ANDREA.SANTOS | ISSUED AS CODE 2 - NO COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-MP-2105-10010_R01.XLSX | 122,58 KB | 30/05/2025 05:39:42 |  | 30/05/2025 09:49:21 | R01 | IFR - ISSUED FOR REVIEW | 23/06/2025 10:09:43 | R01 | 2-NO COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00162 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00250 | 5/30/2025 | BNO_EXT_MABU_00619 | 06/20/2025 | CODE 2 - NO COMMENTS |  |  | R | P2
BNO-MABU-300-MP-2105-10011 |  | PIPING DATASHEETS FOR GATE VALVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 19/06/2025 |  | ANDREA.SANTOS |  | 50 | 03/07/2025 | BNO-MABU-300-MP-2105-10011_R01.XLSX | 126,14 KB | 19/06/2025 14:12:29 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/03/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00221 | R01 | 06/19/2025 | BNO-MABU-SNEPCO-2025-INC-00304 | 06/19/2025 | [5 empty] | R | P2
BNO-MABU-300-MP-2105-10012 |  | PIPING DATASHEETS FOR NEEDLE VALVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 19/06/2025 |  | ANDREA.SANTOS |  | 50 | 03/07/2025 | BNO-MABU-300-MP-2105-10012_R01.XLSX | 124,54 KB | 19/06/2025 14:39:05 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/03/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00221 | R01 | 06/19/2025 | BNO-MABU-SNEPCO-2025-INC-00304 | 06/19/2025 | [5 empty] | R | P2
BNO-MABU-300-MP-2105-10013 |  | PIPING DATASHEET FOR VALVE & DOOR INTERLOCK SYSTEM FOR PIG LAUNCHING AND RECEIVING | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ISSUED | 19/06/2025 | 07/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 03/07/2025 | BNO-MABU-300-MP-2105-10013_R01.XLSX | 189,05 KB | 19/06/2025 14:39:50 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/03/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00221 | R01 | 06/19/2025 | BNO-MABU-SNEPCO-2025-INC-00304 | 06/19/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10087 | 07/07/2025 | NR | NA
BNO-MABU-300-MP-2105-10014 |  | DATASHEET FOR KENMAC OR OLIVER DBB WITH NRV (CHECK VALVE) 2" FLANGED * 1/2" THREADED | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 26/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/26/2025 | 6/14/2025 | 6/26/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2105-10015 |  | PIPING DATA SHEET FOR SLIPSTREAM SAND SAMPLING SYSTEM | MP - PIPING | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 50 | 04/08/2025 | BNO-MABU-300-MP-2105-10015_A01.XLSX | 1,2 MB | 22/07/2025 09:01:17 |  | 30/05/2025 09:49:21 | R01 | IFR - ISSUED FOR REVIEW | 23/06/2025 10:16:15 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 06/13/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00393 | A01 | 07/22/2025 | BNO-MABU-SNEPCO-2025-INC-00429 | 07/22/2025
BNO-MABU-300-MP-2105-10016 |  | DATASHEET FOR STRAINERS | MP - PIPING | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 50 | 04/08/2025 | BNO-MABU-300-MP-2105-10016_A01.XLSX | 116,21 KB | 22/07/2025 09:06:55 |  | 30/05/2025 06:04:37 | R01 | IFR - ISSUED FOR REVIEW | 23/06/2025 10:09:45 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00393 | A01 | 07/22/2025 | BNO-MABU-SNEPCO-2025-INC-00429 | 07/22/2025
BNO-MABU-300-MP-2105-10017 |  | DATASHEET FOR AIR RELEASE VALVE (AIR ELIMINATOR) | MP - PIPING | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 50 | 04/08/2025 | BNO-MABU-300-MP-2105-10017_A01.XLSX | 112,48 KB | 22/07/2025 09:11:22 |  | 30/05/2025 06:04:37 | R01 | IFR - ISSUED FOR REVIEW | 23/06/2025 10:16:16 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00393 | A01 | 07/22/2025 | BNO-MABU-SNEPCO-2025-INC-00429 | 07/22/2025
BNO-MABU-300-MP-2105-10018 |  | DATASHEET FOR CORROSION MONITOR (ACCESS FITTING ASSEMBLIES) | MP - PIPING | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 22/07/2025 |  | ANDREA.SANTOS |  | 50 | 04/08/2025 | BNO-MABU-300-MP-2105-10018_A01.XLSX | 111,37 KB | 22/07/2025 08:46:06 |  | 30/05/2025 06:04:37 | R01 | IFR - ISSUED FOR REVIEW | 23/06/2025 10:16:18 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00392 | A01 | 07/22/2025 | BNO-MABU-SNEPCO-2025-INC-00429 | 07/22/2025
BNO-MABU-300-MP-2105-10019 |  | DATASHEET FOR FLAME ARRESTOR | MP - PIPING | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 50 | 04/08/2025 | BNO-MABU-300-MP-2105-10019_A01.XLSX | 113,37 KB | 22/07/2025 08:57:36 |  | 30/05/2025 06:04:37 | R01 | IFR - ISSUED FOR REVIEW | 23/06/2025 10:09:46 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00392 | A01 | 07/22/2025 | BNO-MABU-SNEPCO-2025-INC-00429 | 07/22/2025
BNO-MABU-300-MP-2105-10020 |  | DATASHEET FOR BIRD SCREEN | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ISSUED | 30/05/2025 | 27/07/2025 |  | ISSUED AS CODE 2 - NO COMMENTS | 100 | 13/06/2025 | BNO-MABU-300-MP-2105-10020_R01.XLSX | 111,87 KB | 30/05/2025 05:03:44 |  | 30/05/2025 06:04:37 | R01 | IFR - ISSUED FOR REVIEW | 24/06/2025 05:52:52 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00161 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-0024 | 05/30/2025 | BNO_EXT_MABU_00635 | 06/24/2025 | CODE 2 - NO COMMENTS | BNO-MABU-DAE-2025-TN-10099 | 07/27/2025
BNO-MABU-300-MP-2343-10001-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-CC-423005-40S-SS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10002-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-CC-423005-40S-SS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10003-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DC-483015-80-A | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10004-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PM-033030-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10005-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-PM-033030-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10006-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-033030-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10007-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-033030-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10008-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-033030-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10009-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PM-033031-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10010-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-PM-033031-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10011-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-033031-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10012-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-033031-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10013-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-UW-513033-80-G | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10014-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-DN-473034-STD-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10015-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-CC-423040-40S-SS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10016-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-CC-423040-40S-SS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10017-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-CC-423041-40S-SS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10018-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PG-313045-"750"-F1-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10019-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-CM-423045-XXS-J3 | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10020-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PG-313045-"750"-F1-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10021-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-CM-423045-XXS-J3 | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10022-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-PG-313045-"750"-F1-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10023-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PG-313045-"750"-F1-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10024-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PG-313046-"750"-FLT-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10025-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-CM-423046-XXS-J3 | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10026-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-PG-313046-"750"-FLT-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10027-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-PG-313046-"750"-FLT-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10028-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PG-313046-"750"-FLT-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10029-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PG-313047-"750"-FFLT-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10030-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-CM-423047-XXS-J3 | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10031-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-PG-313047-"750"-FFLT-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10032-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PG-313047-"750"-FFLT-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10033-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PG-313048-"750"-F1-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10034-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PG-313048-"750"-F1-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10035-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-PG-313048-"750"-F1-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10036-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PG-313048-"750"-FFLT-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10037-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PG-313049-"750"-FLT-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10038-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-PG-313049-"750"-FLT-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10039-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-PG-313049-"750"-FLT-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10040-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PG-313049-"750"-FLT-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10041-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PG-313050-"750"-FFLT-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10042-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-PG-313050-"750"-FFLT-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10043-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PG-313050-"750"-FFLT-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10044-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-WI-403065-STD-AW | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10045-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 16"-WI-403071-"1900"-F | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10046-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 16"-WI-403076-"1900"-F | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10047-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-FG-443083-40S-SSB-E | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10048-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083090-XXS-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10049-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043090-"1800"-JJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10050-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043090-"1800"-JJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/09/2025 | 10/17/2025 | 10/29/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10051-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083091-XXS-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10052-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043091-"1125"-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10053-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043091-"1125"-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10054-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043092-100-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10055-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PM-083092-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10056-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043092-100-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10057-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043092-100-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10058-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083093-XXS-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10059-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PM-043093-"1125"-JJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10060-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-PM-043093-"1125"-JJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10061-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-PM-083094-XXS-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10062-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083094-XXS-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10063-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043094-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10064-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PM-043094-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10065-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-PM-043094-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10066-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-PM-043095-"1800"-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10067-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083095-XXS-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10068-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-PM-043095-"1800"-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10069-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043095-"1800"-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10070-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-PM-083096-XXS-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10071-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-463096-80-ALT | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10072-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083096-XXS-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10073-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-PM-043096-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10074-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-PM-043096-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10075-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083097-XXS-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10076-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043097-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10077-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043097-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10078-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043097-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10079-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-PM-083098-XXS-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10080-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043098-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10081-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-DN-473098-STD-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10082-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083098-XXS-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10083-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043098-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10084-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-PM-043099-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10085-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043099-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10086-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083099-XXS-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10087-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PM-043099-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10088-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043099-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10089-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043099-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10090-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-FG-443100-40S-SSB-E | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10091-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-FG-443100-40S-SSB-T | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10092-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043100-"1562"-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10093-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083100-XXS-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10094-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 3"-FG-443100-40S-SSB-E | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10095-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-FG-443100-40S-SSB-T | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10096-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-PM-043100-"1562"-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10097-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043101-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10098-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-FG-443101-80-B-P | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10099-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PM-083101-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10100-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-PM-043101-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 10/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/10/2025 | 10/20/2025 | 10/30/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10101-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043101-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10102-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083102-XXS-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10103-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043102-"1800"-JJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10104-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043102-"1800"-JJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10105-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-PM-083103-XXS-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10106-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043103-"1125"-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10107-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083103-XXS-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10108-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-463103-80-A | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10109-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043103-"1125"-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10110-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-WI-403103-30-63861 | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10111-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043104-100-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10112-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083104-XXS-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10113-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-DN-483104-STD-H | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10114-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043104-100-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10115-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043104-100-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10116-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-PM-083105-XXS-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10117-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083105-XXS-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10118-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043105-"1125"-JJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10119-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PM-043105-"1125"-JJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10120-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-PM-043105-"1125"-JJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10121-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083106-XXS-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10122-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PM-043106-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10123-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-PM-043106-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10124-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1"-PM-043107-"1800"-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10125-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1-1/2"-PM-083107-XXS-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10126-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-083107-XXS-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10127-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-PM-043107-"1800"-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10128-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043107-"1800"-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10129-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 6"-PM-043108-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10130-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-PM-043108-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10131-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043109-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10132-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-433109-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10133-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043109-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10134-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-433109-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10135-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043109-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10136-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043110-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10137-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043110-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10138-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-PM-043111-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10139-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-433111-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10140-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 4"-PM-043111-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10141-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043111-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10142-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-433111-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10143-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 14"-PM-043111-100-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10144-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043112-"1562"-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10145-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 10"-PM-043112-"1562"-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10146-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 2"-PM-043113-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10147-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 8"-PM-043113-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10148-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 12"-PM-043113-120-IFJ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10149-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 1/2"-PM-043114-0.31-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10150-001 |  | PIPING CONSTRUCT ISOMETRIC DRAWING: 3/4"-PM-043114-0.31-CC | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/11/2025 | 10/21/2025 | 10/31/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-2343-10193-001 |  | PIPING ISOMETRIC A02-L1-038675 | MP - PIPING | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 27/07/2025 |  | ANDREA.SANTOS |  | 100 | 08/08/2025 | BNO-MABU-300-MP-2343-10193-001-A01.DWG | 709,7 KB | 27/07/2025 09:05:43 | [11 empty] | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00416 | A01 | 08/08/2025 | BNO/MABU-SNEPCO-2025-INC-00449 | 08/08/2025
BNO-MABU-300-MP-2343-10194-001 |  | PIPING ISOMETRIC A02.L1-033031 | MP - PIPING | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 27/07/2025 |  | ANDREA.SANTOS |  | 100 | 08/08/2025 | BNO-MABU-300-MP-2343-10194-001-A01.DWG | 639,61 KB | 27/07/2025 09:06:05 | [11 empty] | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00416 | A01 | 07/27/2025 | BNO/MABU-SNEPCO-2025-INC-00449 | 07/27/2025
BNO-MABU-300-MP-2343-10195-001 |  | PIPING ISOMETRIC A02.L1-033031 | MP - PIPING | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 27/07/2025 |  | ANDREA.SANTOS |  | 100 | 08/08/2025 | BNO-MABU-300-MP-2343-10195-001-A01.DWG | 637,41 KB | 27/07/2025 09:06:32 | [11 empty] | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00378 | A01 | 07/27/2025 | BNO/MABU-SNEPCO-2025-INC-00449 | 07/27/2025
BNO-MABU-300-MP-2343-10196-001 |  | PIPING ISOMETRIC A02.L1-038674 | MP - PIPING | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 27/07/2025 |  | ANDREA.SANTOS |  | 100 | 08/08/2025 | BNO-MABU-300-MP-2343-10196-001-A01.DWG | 702,31 KB | 27/07/2025 09:06:49 | [11 empty] | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00416 | A01 | 07/17/2025 | BNO/MABU-SNEPCO-2025-INC-00449 | 07/27/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10096 | 07/22/2025
BNO-MABU-300-MP-2343-10197-001 |  | PIPING ISOMETRIC A02.L1.043119 | MP - PIPING | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 27/07/2025 |  | ANDREA.SANTOS |  | 100 | 08/08/2025 | BNO-MABU-300-MP-2343-10197-001-A01.DWG | 683,76 KB | 27/07/2025 09:07:10 | [11 empty] | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00378 | A01 | 07/27/2025 | BNO/MABU-SNEPCO-2025-INC-00416 | 07/27/2025
BNO-MABU-300-MP-2343-10198-001 |  | PIPING ISOMETRIC A02.L1-043118 | MP - PIPING | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 27/07/2025 |  | ANDREA.SANTOS |  | 100 | 08/08/2025 | BNO-MABU-300-MP-2343-10198-001-A01.DWG | 658,46 KB | 27/07/2025 09:08:08 | [11 empty] | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00416 | A01 | 07/27/2025 | BNO/MABU-SNEPCO-2025-INC-00449 | 07/27/2025
BNO-MABU-300-MP-2343-10199-001 |  | PIPING ISOMETRIC A02.L1-313045 | MP - PIPING | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 27/07/2025 |  | ANDREA.SANTOS |  | 100 | 08/08/2025 | BNO-MABU-300-MP-2343-10199-001-A01.DWG | 633,72 KB | 27/07/2025 09:12:03 | [11 empty] | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00416 | A01 | 07/27/2025 | BNO/MABU-SNEPCO-2025-INC-00449 | 07/27/2025
BNO-MABU-300-MP-2343-10200-001 |  | PIPING ISOMETRIC A02.MZ/L1-313048 | MP - PIPING | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 27/07/2025 |  | ANDREA.SANTOS |  | 100 | 08/08/2025 | BNO-MABU-300-MP-2343-10200-001-A01.DWG | 634,51 KB | 27/07/2025 09:13:03 | [11 empty] | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00416 | A01 | 07/27/2025 | BNO/MABU-SNEPCO-2025-INC-00449 | 07/27/2025
BNO-MABU-300-MP-2343-10201-001 |  | PIPING ISOMETRIC A07.L2-423005 | MP - PIPING | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 27/07/2025 |  | ANDREA.SANTOS |  | 100 | 08/08/2025 | BNO-MABU-300-MP-2343-10201-001-A01.DWG | 665,79 KB | 27/07/2025 09:14:01 | [11 empty] | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00416 | A01 | 07/17/2025 | BNO/MABU-SNEPCO-2025-INC-00449 | 07/27/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10096 | 07/22/2025
BNO-MABU-300-MP-2343-10201-002 |  | PIPING ISOMETRIC A07.L2-423005 | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | CANCELADO | 18/07/2025 |  |  |  | 50 | 31/07/2025 | BNO-MABU-300-MP-2343-10201-002-R01.DWG | 644,66 KB | 18/07/2025 04:49:35 | [11 empty] | SUPERSEDED |  |  |  | BON-DAE-WESTPAQ-2025-TX-00378 | R01 | 07/17/2025 | BNO/MABU-SNEPCO-2025-INC-00417 | 07/18/2025 | SUPERSEDED! SEE EMAIL ATTACHED! |  |  | SUPERSEDED! SEE EMAIL ATTACHED!
BNO-MABU-300-MP-2343-10202-001 |  | PIPING ISOMETRIC A01.L2-403065 | MP - PIPING | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 27/07/2025 |  | ANDREA.SANTOS |  | 100 | 08/08/2025 | BNO-MABU-300-MP-2343-10202-001-A01.DWG | 629,13 KB | 27/07/2025 09:15:06 | [11 empty] | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00416 | A01 | 07/27/2025 | BNO/MABU-SNEPCO-2025-INC-00449 | 07/27/2025
BNO-MABU-300-MP-2343-10203-001 |  | PIPING ISOMETRIC A04.M2-463205 | MP - PIPING | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 27/07/2025 |  | ANDREA.SANTOS |  | 100 | 08/08/2025 | BNO-MABU-300-MP-2343-10203-001-A01.DWG | 628,92 KB | 27/07/2025 09:15:47 | [11 empty] | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00416 | A01 | 07/27/2025 | BNO/MABU-SNEPCO-2025-INC-00449 | 07/27/2025
BNO-MABU-300-MP-2358-10001-001 |  | PRODUCTION FLOWLINE INTERFACE HOOKUP DRAWINGS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 29/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/29/2025 | 10/17/2025 | 11/05/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-2358-10002-001 |  | WATER INJECTION FLOWLINE INTERFACE HOOKUP DRAWINGS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 14/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/14/2025 | 09/12/2025 | 10/03/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-2358-10003-001 |  | TOPSIDE GAS LIFT INTERFACE HOOKUP DRAWINGS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 14/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/14/2025 | 09/12/2025 | 10/03/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-2358-10004 |  | PIPING SPECIALTY ITEM LIST | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ENG_IFR CONSOLIDATION | 28/05/2025 |  | ANDREA.SANTOS | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 11/06/2025 | BNO-MABU-300-MP-2358-10004_R01.XLSX | 130,3 KB | 28/05/2025 08:42:33 |  | 28/05/2025 09:47:06 | R01 | IFR - ISSUED FOR REVIEW | 17/06/2025 09:42:06 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00157 | R01 | 06/11/2025 | BNO-MABU-SNEPCO-2025-INC-00241 | 05/28/2025 | BNO/EXT/MABU/00595 | 06/10/2025 | CODE 3 - MINOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-MP-2358-10004-001 |  | WATERFLOOD SYSTEM INTERFACE HOOKUP DRAWINGS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 19/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/19/2025 | 10/21/2025 | 11/11/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-2358-10005-001 |  | DIESEL AND FUEL GAS SYSTEM HOOKUP DRAWING | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 29/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/29/2025 | 10/17/2025 | 11/05/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-2358-10015-001 |  | PIPING SUPPORT DRAWINGS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 29/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/29/2025 | 10/03/2025 | 10/22/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-3323-10001 |  | TBE FOR STUD BOLTS AND NUTS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ISSUED | 26/06/2025 | 27/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 04/07/2025 | BNO-MABU-300-MP-3323-10001_R01.XLS | 904 KB | 26/06/2025 12:59:17 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/04/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00194 | R01 | 06/23/2025 | BNO-MABU-SNEPCO-2025-INC-00341 | 06/26/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10099 | 07/27/2025 | INFO | NA
BNO-MABU-300-MP-3323-10002 |  | TBE FOR FITTINGS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA | 14/04/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 22/08/2025 | BNO-MABU-300-MP-3323-10002_R01.XLSX | 925,18 KB | 14/04/2025 05:08:41 |  | 15/04/2025 07:06:00 | R01 | IDC - INTERNAL COMMENTS | [7 empty] | IFR - ISSUED FOR REVIEW | 8/22/2025 | 10/10/2025 | 10/29/2025 | BON-DAE-WESTPAQ-2025-TX-00069 | R01 | 4/14/2025 | BNO/MABU-SNEPCO-2025-INC-00155 | 4/15/2025 | BNO/EXT/MABU/00514 | 4/25/2025 | 3 | BNO-MABU-DAE-2025-TN-10040 | 05/07/2025 | INFO | NA
BNO-MABU-300-MP-3323-10003 |  | TBE FOR FLANGES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA | 15/04/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 22/08/2025 | BNO-MABU-300-MP-3323-10003_R01.XLS | 901 KB | 15/04/2025 03:52:48 |  | 15/04/2025 06:03:59 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 8/22/2025 | 10/10/2025 | 10/29/2025 | BON-DAE-WESTPAQ-2025-TX-00056 | A01 | 04/04/2025 | BNO-MABU-SNEPCO-2025-INC-00153 | 4/15/2025 | BNO/EXT/MABU/00514 | 4/25/2025 | 3 | BNO-MABU-DAE-2025-TN-10040 | 05/07/2025 | INFO | NA
BNO-MABU-300-MP-3323-10004 |  | TBE FOR GASKETS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 22/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/22/2025 | 10/10/2025 | 10/29/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-3323-10005 |  | TBE FOR PIPES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA | 15/04/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 18/08/2025 | BNO-MABU-300-MP-3323-10005_R01.XLS | 873 KB | 15/04/2025 04:17:36 |  | 15/04/2025 06:03:59 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 8/18/2025 | 10/06/2025 | 10/23/2025 | BON-DAE-WESTPAQ-2025-TX-00056 | A01 | 04/04/2025 | BNO-MABU-SNEPCO-2025-INC-00153 | 4/15/2025 | BNO/EXT/MABU/00514 | 4/25/2025 | 3 | BNO-MABU-DAE-2025-TN-10040 | 05/07/2025 | INFO | NA
BNO-MABU-300-MP-3323-10006 |  | TBE FOR VA LVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 13/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/13/2025 | 10/02/2025 | 10/20/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-3323-10007 |  | TBE FOR SPRING SUPPORTS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 13/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/13/2025 | 10/02/2025 | 10/20/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-3323-10008 |  | TBE FOR PRODUCTION & GAS LIFT HEAVY WALL PIPING | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-3323-10009 |  | TBE FOR PIPING SPECIAL ITEMS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-3323-10010 |  | TBE FOR WI HEAVY WALL INCONEL CLAD PIPING & FITTINGS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 13/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/13/2025 | 10/02/2025 | 10/20/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-3323-10011 |  | TBE FOR PIPING SUPPORT MATERIALS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-3323-10012 |  | TBE FOR SPECIAL VALVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-3323-10013 |  | TBE FOR HUB CONNECTOR (GRAYLOC) | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 22/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/22/2025 | 10/10/2025 | 10/29/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-3323-10014 |  | TBE FOR BARRED TEES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR CONSOLIDATION | 15/04/2025 |  | ANDREA.SANTOS | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 22/08/2025 | BNO-MABU-300-MP-3323-10014_R01.PDF | 718,85 KB | 15/04/2025 04:53:03 |  | 15/04/2025 06:03:59 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 8/22/2025 | 10/10/2025 | 10/29/2025 | BON-DAE-WESTPAQ-2025-TX-00070 | R01 | 4/14/2025 | BNO-MABU-SNEPCO-2025-INC-00153 | 4/15/2025 | BNO/EXT/MABU/00514 | 4/25/2025 | 3 |  |  | NR | NA
BNO-MABU-300-MP-4018-10001-001 |  | PIPE SUPPORT STANDARD COMPONENTS DETAILS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 01/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/01/2025 | 9/19/2025 | 10/08/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-4018-10002-001 |  | PIPING PLAN & ELEVATION (STARBOARD SUBSEA MODULE) ELEVATION LOOKING EAST - HYDRAULIC POWER / METHANOL INJECTION PUMP / PIGS L-R | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR CONSOLIDATION | 01/07/2025 |  | ANDREA.SANTOS |  | 50 | 14/07/2025 | BNO-MABU-300-MP-4018-10002-001_R01.DWG | 5,36 MB | 01/07/2025 17:18:56 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/14/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00278 | R01 | 06/30/2025 | BNO-MABU-SNEPCO-2025-INC-00361 | 07/01/2025 | BNO/EXT/MABU/00679 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4018-10003-001 |  | PIPING PLAN & ELEVATION (STARBOARD SUBSEA MODULE) ELEVATION LOOKING NORTH - HYDRAULIC POWER / METHANOL INJECTION PUMP / PIGS L-R | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 11/07/2025 |  | ANDREA.SANTOS |  | 50 | 24/07/2025 | BNO-MABU-300-MP-4018-10003-001_R01.DWG | 8,42 MB | 11/07/2025 02:17:14 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/24/2025 | 8/15/2025 | 09/03/2025 | BON-DAE-WESTPAQ-2025-TX-00340 | R01 | 07/10/2025 | BNO-MABU-SNEPCO-2025-INC-00390 | 07/10/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4018-10004-001 |  | PIPING PLAN & ELEVATION (PORT SUBSEA MODULE) ELEVATION LOOKING SOUTH - SWITCH GEAR AND SUBSEA CONTROL BUILDING | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR CONSOLIDATION | 01/07/2025 |  | ANDREA.SANTOS |  | 50 | 14/07/2025 | BNO-MABU-300-MP-4018-10004-001_R01.DWG | 14,74 MB | 01/07/2025 17:19:25 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/14/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00278 | R01 | 06/30/2025 | BNO-MABU-SNEPCO-2025-INC-00361 | 07/01/2025 | BNO/EXT/MABU/00678 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4018-10005-001 |  | PIPING PLAN & ELEVATION (PORT SUBSEA MODULE) ELEVATION LOOKING EAST - SWITCH GEAR AND SUBSEA CONTROL BUILDING / CORROSION INHIBITOR INJECTION PUMP SKID | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR CONSOLIDATION | 01/07/2025 |  | ANDREA.SANTOS |  | 50 | 14/07/2025 | BNO-MABU-300-MP-4018-10005-001_R01.DWG | 6,02 MB | 01/07/2025 17:19:18 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/14/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00278 | R01 | 06/30/2025 | BNO-MABU-SNEPCO-2025-INC-00361 | 07/01/2025 | BNO/EXT/MABU/00678 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4018-10006-001 |  | PIPING PLAN & ELEVATION (STARBOARD SUBSEA MODULE) PLAN @ LEVEL 1 (T.O.S EL.+105.182M) - PIG LAUCHER AND RECEIVER | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR CONSOLIDATION | 01/07/2025 |  | ANDREA.SANTOS |  | 50 | 14/07/2025 | BNO-MABU-300-MP-4018-10006-001_R01.DWG | 8,6 MB | 01/07/2025 17:19:14 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/14/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00278 | R01 | 07/14/2025 | BNO-MABU-SNEPCO-2025-INC-00361 | 07/01/2025 | BNO/EXT/MABU/00678 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4018-10007-001 |  | PIPING PLAN & ELEVATION (STARBOARD SUBSEA MODULE) PLAN @ LEVEL 2 (T.O.S EL.+114.802M) - METHANOL INJECTION PUMP | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 01/07/2025 |  | ANDREA.SANTOS |  | 50 | 14/07/2025 | BNO-MABU-300-MP-4018-10007-001_R01.DWG | 4,47 MB | 01/07/2025 17:19:09 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/14/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00278 | R01 | 06/30/2025 | BNO-MABU-SNEPCO-2025-INC-00361 | 07/01/2025 | BNO/EXT/MABU/00688 (OVERDUE, RCVD LATE FROM CPY AND SHARED WITH MABU DL ON 25-07-25 | 07/25/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4018-10008-001 |  | PIPING PLAN & ELEVATION (STARBOARD SUBSEA MODULE) PLAN @ MAIN DECK (T.O.S EL.+99.059M) - RISER AREA | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR CONSOLIDATION | 11/07/2025 |  | ANDREA.SANTOS |  | 50 | 24/07/2025 | BNO-MABU-300-MP-4018-10008-001_R01.DWG | 5,56 MB | 11/07/2025 02:17:42 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/10/2025 | 8/15/2025 | 09/03/2025 | BON-DAE-WESTPAQ-2025-TX-00340 | R01 | 07/10/2025 | BNO-MABU-SNEPCO-2025-INC-00390 | 07/10/2025 | BNO/EXT/MABU/00678 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4018-10008-002 |  | PIPING PLAN & ELEVATION (STARBOARD SUBSEA MODULE) PLAN @ MAINDECK (T.O.S EL.++99.059M) - RISER AREA | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 11/07/2025 |  | ANDREA.SANTOS |  | 50 | 24/07/2025 | BNO-MABU-300-MP-4018-10008-002_R01.DWG | 2,25 MB | 11/07/2025 02:12:44 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/24/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00340 | R01 | 07/10/2025 | BNO-MABU-SNEPCO-2025-INC-00390 | 07/10/2025
BNO-MABU-300-MP-4018-10009-001 |  | PIPING PLAN & ELEVATION (PORT SUBSEA MODULE) PLAN @ LEVEL 2 (T.O.S EL.+114.802M) - SWITCH GEAR AND SUBSEA CONTROL BUILDING | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 11/07/2025 |  | ANDREA.SANTOS |  | 50 | 24/07/2025 | BNO-MABU-300-MP-4018-10009-001_R01.DWG | 2,77 MB | 11/07/2025 02:12:48 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/24/2025 | 8/15/2025 | 09/03/2025 | BON-DAE-WESTPAQ-2025-TX-00340 | R01 | 07/10/2025 | BNO-MABU-SNEPCO-2025-INC-00390 | 07/10/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4018-10010-001 |  | PIPING PLAN & ELEVATION (PORT SUBSEA MODULE) PLAN @ MEZZANINE (T.O.S EL.+109.800M) - CORROSIN INHIBITOR INJECTION PUMP SKID | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 01/07/2025 |  | ANDREA.SANTOS |  | 50 | 14/07/2025 | BNO-MABU-300-MP-4018-10010-001_R01.DWG | 4,17 MB | 01/07/2025 17:19:05 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/14/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00278 | R01 | 06/30/2025 | BNO-MABU-SNEPCO-2025-INC-00361 | 07/01/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4018-10011-001 |  | PIPING PLAN & ELEVATION (MAIN RACK 2) ELEVATION LOOKING SOUTH - WATERFLOOD INJECTION PUMP / TURBINE SYSTEM | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 11/07/2025 |  | ANDREA.SANTOS |  | 50 | 24/07/2025 | BNO-MABU-300-MP-4018-10011-001_R01.DWG | 23 MB | 11/07/2025 02:17:38 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/24/2025 | 8/15/2025 | 09/03/2025 | BON-DAE-WESTPAQ-2025-TX-00340 | R01 | 07/10/2025 | BNO-MABU-SNEPCO-2025-INC-00390 | 07/10/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4018-10012-001 |  | PIPING PLAN & ELEVATION (MAIN RACK 2) PLAN AT LEVEL 2 - WATERFLOOD INJECTION PUMP / TURBINE SYSTEM | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR CONSOLIDATION | 01/07/2025 |  | ANDREA.SANTOS |  | 50 | 14/07/2025 | BNO-MABU-300-MP-4018-10012-001_R01.DWG | 3,73 MB | 01/07/2025 17:19:00 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/14/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00278 | R01 | 07/01/2025 | BNO-MABU-SNEPCO-2025-INC-00361 | 07/01/2025 | BNO/EXT/MABU/00678 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4018-10013-001 |  | PIPING PLAN & ELEVATION (PORT SUBSEA MODULE) MEZZANINE DECK | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 11/07/2025 |  | ANDREA.SANTOS |  | 50 | 24/07/2025 | BNO-MABU-300-MP-4018-10013-001_R01.DWG | 4,25 MB | 11/07/2025 02:12:52 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/24/2025 | 8/15/2025 | 09/03/2025 | BON-DAE-WESTPAQ-2025-TX-00340 | R01 | 07/10/2025 | BNO-MABU-SNEPCO-2025-INC-00390 | 07/10/2025 | [5 empty] | NR | NA
BNO-MABU-300-MP-4018-10014-001 |  | PIPING PLAN & ELEVATION (STARBOARD MODULE) MEZZANINE DECK | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 27/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/27/2025 | 8/15/2025 | 09/03/2025 | [10 empty] | NR | NA
BNO-MABU-300-MP-4018-10015-001 |  | PIPING_PLAN_&_ELEVATION_MAIN_RACK_2_PLAN_AT_LEVEL_3-WATERFLOOD_I | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 01/07/2025 |  | ANDREA.SANTOS |  | 50 | 14/07/2025 | BNO-MABU-300-MP-4018-10015-001_R01.DWG | 2,43 MB | 01/07/2025 17:21:24 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/14/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00278 | R01 | 07/01/2025 | BNO-MABU-SNEPCO-2025-INC-00361 | 07/01/2025 | BNO/EXT/MABU/00688 (OVERDUE RCVD FROM CPY LATE ON 25-07-25. | 07/25/2025 | CODE 3 - MINOR COMMENTS
BNO-MABU-300-MP-4018-10016-001 |  | PIPING PLAN & ELEVATION (STARBOARD SUBSEA MODULE) PLAN @ LEVEL 1 (T.O.S EL.+105.182M) - PRODUCTION MANIFOLD | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ENG_IFR CONSOLIDATION | 08/07/2025 |  | ANDREA.SANTOS |  | 50 | 22/07/2025 | BNO-MABU-300-MP-4018-10016-001_R01.DWG | 5,08 MB | 08/07/2025 13:42:11 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/22/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00318 | R01 | 07/08/2025 | BNO-MABU-SNEPCO-2025-INC-00380 | 07/08/2025 | BNO/EXT/MABU/00678 | 07/14/2025 | CODE 3 - MINOR COMMENTS
BNO-MABU-300-MP-4024-10001-001 |  | PLOT PLAN LAYOUT (OVERALL) | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ISSUED | 29/03/2025 | 20/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 26/03/2025 | BNO-MABU-300-MP-4024-10001-001_R01.DWG | 6,35 MB | 29/03/2025 04:04:28 |  | 01/04/2025 05:46:19 | R01 | IFR - ISSUED FOR REVIEW | 10/04/2025 06:14:17 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 3/26/2025 | 05/09/2025 | 5/28/2025 | BON-DAE-WESTPAQ-2025-TX-00051 | R01 | 3/28/2025 | BNO-MABU-SNEPCO-2025-INC-00128 | 04/01/2025 | BNO/EXT/MABU/00497 | 04/10/2025 |  | BNO-MABU-DAE-2025-TN-10029 | 4/23/2025 | INFO | NA
BNO-MABU-300-MP-4033-10001-001 |  | EQUIPMENT LAYOUT (STARBOARD SUBSEA MODULE) ELEVATION LOOKING EAST - HYDRAULIC POWER / METHANOL INJECTION PUMP / PIGS L-R | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 26/06/2025 |  | ANDREA.SANTOS |  | 50 | 07/07/2025 | BNO-MABU-300-MP-4033-10001-001_R01.DWG | 3,52 MB | 26/06/2025 02:46:14 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/07/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00249 | R01 | 06/24/2025 | BNO-MABU-SNEPCO-2025-INC-00328 | 06/24/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS
BNO-MABU-300-MP-4033-10002-001 |  | EQUIPMENT LAYOUT (STARBOARD SUBSEA MODULE) ELEVATION LOOKING NORTH - HYDRAULIC POWER / METHANOL INJECTION PUMP / PIGS L-R | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR CONSOLIDATION | 26/06/2025 |  | ANDREA.SANTOS |  | 50 | 07/07/2025 | BNO-MABU-300-MP-4033-10002-001_R01.DWG | 4,73 MB | 26/06/2025 02:46:29 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/08/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00249 | R01 | 06/24/2025 | BNO-MABU-SNEPCO-2025-INC-00328 | 06/24/2025 | BNO/EXT/MABU/00679 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4033-10003-001 |  | EQUIPMENT LAYOUT (PORT SUBSEA MODULE) ELEVATION LOOKING SOUTH - SWITCH GEAR AND SUBSEA CONTROL BUILDING | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 26/06/2025 |  | ANDREA.SANTOS |  | 50 | 08/07/2025 | BNO-MABU-300-MP-4033-10003-001_R01.DWG | 6,95 MB | 26/06/2025 02:52:49 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/08/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00249 | R01 | 06/24/2025 | BNO-MABU-SNEPCO-2025-INC-00328 | 06/24/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4033-10004-001 |  | EQUIPMENT LAYOUT (PORT SUBSEA MODULE) ELEVATION LOOKING EAST - SWITCH GEAR AND SUBSEA CONTROL BUILDING / CORROSION INHIBITOR INJECTION PUMP SKID | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR CONSOLIDATION | 26/06/2025 |  | ANDREA.SANTOS |  | 50 | 08/07/2025 | BNO-MABU-300-MP-4033-10004-001_R01.DWG | 3,13 MB | 26/06/2025 02:55:34 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/08/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00249 | R01 | 06/24/2025 | BNO-MABU-SNEPCO-2025-INC-00328 | 06/24/2025 | BNO/EXT/MABU/00679 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4033-10005-001 |  | EQUIPMENT LAYOUT (STARBOARD SUBSEA MODULE) PLAN @ LEVEL 1 (T.O.S EL.+105.182M) - PIG LAUCHER AND RECEIVER | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR CONSOLIDATION | 26/06/2025 |  | ANDREA.SANTOS |  | 50 | 08/07/2025 | BNO-MABU-300-MP-4033-10005-001_R01.DWG | 1,85 MB | 26/06/2025 03:03:20 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/08/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00249 | R01 | 06/24/2025 | BNO/MABU-SNEPCO-2025-INC-00328 | 06/24/2025 | BNO/EXT/MABU/00679 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4033-10006-001 |  | EQUIPMENT LAYOUT (STARBOARD SUBSEA MODULE) PLAN @ LEVEL 2 (T.O.S EL.+114.802M) - METHANOL INJECTION PUMP | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 26/06/2025 |  | ANDREA.SANTOS |  | 50 | 08/07/2025 | BNO-MABU-300-MP-4033-10006-001_R01.DWG | 4,06 MB | 26/06/2025 03:12:49 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/08/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00249 | R01 | 06/24/2025 | BNO-MABU-SNEPCO-2025-INC-00328 | 06/24/2025 | BNO_EXT_MABU_00682 | 07/14/2025 | OVERDUE |  |  | NR | NA
BNO-MABU-300-MP-4033-10007-001 |  | EQUIPMENT LAYOUT (STARBOARD SUBSEA MODULE) PLAN @ MAIN DECK (T.O.S EL.+99.059M) - RISER AREA | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 26/06/2025 |  | ANDREA.SANTOS |  | 50 | 08/07/2025 | BNO-MABU-300-MP-4033-10007-001_R01.DWG | 2,75 MB | 26/06/2025 03:13:03 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/08/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00249 | R01 | 06/24/2025 | BNO-MABU-SNEPCO-2025-INC-00328 | 06/24/2025 | [5 empty] | NR | NA
BNO-MABU-300-MP-4033-10008-001 |  | EQUIPMENT LAYOUT (PORT SUBSEA MODULE) PLAN @ LEVEL 2 (T.O.S EL.+114.802M) - SWITCH GEAR AND SUBSEA CONTROL BUILDING | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR CONSOLIDATION | 26/06/2025 |  | ANDREA.SANTOS |  | 50 | 10/07/2025 | BNO-MABU-300-MP-4033-10008-001_R01.DWG | 1,84 MB | 26/06/2025 06:01:48 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/10/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00256 | R01 | 06/26/2025 | BNO-MABU-SNEPCO-2025-INC-00336 | 06/26/2025 | BNO/EXT/MABU/00679 | 07/14/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4033-10009-001 |  | EQUIPMENT LAYOUT (PORT SUBSEA MODULE) PLAN @ MEZZANINE (T.O.S EL.+109.800M) - CORROSIN INHIBITOR INJECTION PUMP SKID | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 26/06/2025 |  | ANDREA.SANTOS |  | 50 | 08/07/2025 | BNO-MABU-300-MP-4033-10009-001_R01.DWG | 2,02 MB | 26/06/2025 03:13:24 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/08/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00249 | R01 | 06/24/2025 | BNO-MABU-SNEPCO-2025-INC-00328 | 06/24/2025 | BNO_EXT_MABU_00682 | 07/14/2025 | CODE 2 - NO COMMENTS |  |  | NR | NA
BNO-MABU-300-MP-4033-10010-001 |  | EQUIPMENT LAYOUT (MAIN RACK 2) ELEVATION LOOKING SOUTH - WATERFLOOD INJECTION PUMP / TURBINE SYSTEM | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR COMMENTS - MABU | 26/06/2025 |  | ANDREA.SANTOS |  | 50 | 08/07/2025 | BNO-MABU-300-MP-4033-10010-001_R01.DWG | 2,69 MB | 26/06/2025 03:13:38 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/08/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00249 | R01 | 06/24/2025 | BNO-MABU-SNEPCO-2025-INC-00328 | 06/24/2025 | BNO/EXT/MABU/00680 | 07/14/2025 | CODE 2 - NO COMMENTS |  |  | INFO | NA
BNO-MABU-300-MP-4033-10011-001 |  | EQUIPMENT LAYOUT (MAIN RACK 2) PLAN AT LEVEL 2 - WATERFLOOD INJECTION PUMP / TURBINE SYSTEM | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 26/06/2025 |  | ANDREA.SANTOS |  | 50 | 08/07/2025 | BNO-MABU-300-MP-4033-10011-001_R01.DWG | 3,19 MB | 26/06/2025 03:14:02 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/08/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00249 | R01 | 06/24/2025 | BNO-MABU-SNEPCO-2025-INC-00328 | 06/24/2025 | [5 empty] | INFO | NA
BNO-MABU-300-MP-4033-10012-001 |  | EQUIPMENT_EQUIPMENT_LAYOUT_(STARBOARD_SUBSEA_MODULE)_PLAN_@_LEVEL_1_ | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 26/06/2025 |  | ANDREA.SANTOS |  | 50 | 08/07/2025 | BNO-MABU-300-MP-4033-10012-001_R01.DWG | 3,28 MB | 26/06/2025 03:14:20 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/08/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00249 | R01 | 06/24/2025 | BNO-MABU-SNEPCO-2025-INC-00328 | 06/24/2025 | BNO_EXT_MABU_00682 | 07/14/2025 | OVERDUE
BNO-MABU-300-MP-4306-10001 |  | PIPE SUPPORT MTO | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 26/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/26/2025 | 10/14/2025 | 10/31/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-4306-10002 |  | TOPSIDES PIPING BULK MTO | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 21/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/21/2025 | 9/22/2025 | 10/13/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-4306-10003 |  | WI HEAVY WALL INCONEL CLAD PIPING & FITTINGS - MTO | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 07/11/2025 | 09/12/2025 | 10/03/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-4306-10004 |  | PRODUCTION & GAS LIFT HEAVY WALL PIPING - MTO | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 01/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/01/2025 | 9/19/2025 | 10/08/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-4306-10005 |  | TOPSIDES PIPING INSULATION MTO | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 15/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/15/2025 | 9/16/2025 | 10/07/2025 | [10 empty] | R | P2
BNO-MABU-300-MP-4337-10001 |  | PIPE SUPPORT LISTS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 01/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/01/2025 | 10/03/2025 | 10/22/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-4338-10001 |  | ISOMETRIC LIST | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 13/06/2025 | [14 empty] | IFR - ISSUED FOR REVIEW | 06/13/2025 | [12 empty] | INFO | NA
BNO-MABU-300-MP-4338-10002 |  | CRITICAL LINE LIST | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ISSUED | 02/06/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 13/06/2025 | BNO-MABU-300-MP-4338-10002_R01.XLSM | 243,31 KB | 02/06/2025 03:34:01 |  | 02/06/2025 07:11:40 | R01 | IFR - ISSUED FOR REVIEW | 24/06/2025 05:45:14 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 06/13/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00177 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00252 | 06/02/2025 | BNO_EXT_MABU_00634 | 06/24/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10097 | 07/24/2025 | R | P2
BNO-MABU-300-MP-4363-10001 |  | PIPING TIE-IN LIST | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA | 28/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 11/06/2025 | BNO-MABU-300-MP-4363-10001_R01.XLSX | 126,13 KB | 28/05/2025 08:50:31 |  | 28/05/2025 09:47:06 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:05:48 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00157 | R01 | 05/28/2025 | BNO-MABU-SNEPCO-2025-INC-000241 | 5/28/2025 | BNO_EXT_MABU_00599 | 06/16/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10084 | 06/30/2025 | INFO | NA
BNO-MABU-300-MP-4368-10001 |  | VALVE LIST | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 14/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/14/2025 | 09/12/2025 | 10/03/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10001 |  | MATERIAL REQUISITION FOR BOLTS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10002 |  | MATERIAL REQUISITION FOR BALL VALVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10003 |  | MATERIAL REQUISITION FOR FLANGES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10004 |  | MATERIAL REQUISITION FOR PIPES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10005 |  | MATERIAL REQUISITION FOR FITTINGS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10006 |  | MATERIAL REQUISITION FOR GASKETS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10007 |  | MATERIAL REQUISITION FOR HUB CONNECTOR (GRAYLOC) | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10008 |  | MATERIAL REQUISITION FOR DOUBLE BLOCK & BLEED VALVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10009 |  | MATERIAL REQUISITION FOR GLOBE VALVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10010 |  | MATERIAL REQUISITION FOR CHECK VALVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10011 |  | MATERIAL REQUISITION FOR GATE VALVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10012 |  | MATERIAL REQUISITION FOR NEEDLE VALVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10013 |  | MATERIAL REQUISITION FOR SPECTACLE BLANK AND PADDLE BLANK | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10014 |  | MATERIAL REQUISITION FOR STRAINER | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10015 |  | MATERIAL REQUISITION - WI HEAVY WALL INCONEL CLAD PIPING & FITTINGS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10016 |  | MATERIAL REQUISITION FOR SPRING SUPPORTS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10017 |  | MATERIAL REQUISITION - PRODUCTION & GAS LIFT HEAVY WALL PIPING | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10018 |  | MATERIAL REQUISITION FOR PIPING SPECIAL ITEMS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10019 |  | MATERIAL REQUISITION FOR PIPING SUPPORT MATERIALS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10020 |  | MATERIAL REQUISITION FOR SPECIAL TYPE VA LVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7303-10021 |  | MATERIAL REQUISITION FOR BARRED TEE | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 18/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/18/2025 | 10/06/2025 | 10/23/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7402-10001 |  | 60% MODEL REVIEW REPORT | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 12/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/12/2025 | 10/31/2025 | 11/19/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7402-10002 |  | 90% MODEL REVIEW REPORT | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 03/10/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 10/03/2025 | 10/24/2025 | 11/07/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7737-10001 |  | SPECIFICATION FOR TOPSIDE PIPING SYSTEMS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ISSUED | 07/05/2025 | 07/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 22/05/2025 | BNO-MABU-300-MP-7737-10001_R01.DOCX | 2,48 MB | 29/04/2025 05:20:38 |  | 29/04/2025 05:54:10 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 5/22/2025 | 07/10/2025 | 7/29/2025 | BON-DAE-WESTPAQ-2025-TX-00083 | R01 | 4/28/2025 | BNO-MABU-SNEPCO-2025-INC-00168 | 4/29/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10087 | 07/07/2025 | R | P2
BNO-MABU-300-MP-7737-10002 |  | SPECIFICATION FOR VALVES | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ISSUED | 30/04/2025 | 27/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 18/04/2025 | BNO-MABU-300-MP-7737-10002_R01.DOCX | 846,63 KB | 30/04/2025 05:52:51 |  | 02/05/2025 07:31:52 | R01 | IFR - ISSUED FOR REVIEW | 15/05/2025 05:19:14 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/18/2025 | 06/06/2025 | 6/25/2025 | BON-DAE-WESTPAQ-2025-TX-00087 | R01 | 4/30/2025 | BNO-MABU-SNEPCO-2025-INC-00175 | 05/02/2025 | BNO_EXT_MABU_00542 | 05/15/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10099 | 07/28/2025 | R | P2
BNO-MABU-300-MP-7737-10003 |  | SPECIFICATION FOR SPECIAL PIPING ITEMS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ENG_IFR COMMENTS - MABU | 09/05/2025 |  | ANDREA.SANTOS | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 18/04/2025 | BNO-MABU-300-MP-7737-10003_R01.DOCX | 834,45 KB | 09/05/2025 08:31:05 |  |  |  |  | 14/05/2025 05:14:35 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/18/2025 | 06/06/2025 | 6/25/2025 | BON-DAE-WESTPAQ-2025-TX-00099 | R01 | 05/09/2025 | BNO-MABU-SNEPCO-2025-INC-00190 | 05/09/2025 | [5 empty] | R | P2
BNO-MABU-300-MP-7737-10004 |  | SPECIFICATIONS FOR PIPING STRESS ANALYSIS PHILOSOPHY | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ISSUED | 04/06/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 13/06/2025 | BNO-MABU-300-MP-7737-10004_R01.DOCX | 2,47 MB | 30/05/2025 05:09:21 |  |  |  |  | 24/06/2025 09:22:19 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00161 | R01 | 05/30/2025 | BNO/MABU-SNEPCO-2025-INC-00266 | 06/04/2025 | BNO_EXT_MABU_00637 | 06/24/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10097 | 07/24/2025 | R | P2
BNO-MABU-300-MP-7737-10005 |  | TECHNICAL SPECIFICATION - INTERLOCK & DOOR INTERLOCK SYSTEM TO PIG LAUNCHING/RECEIVING | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ISSUED | 25/06/2025 | 27/07/2025 |  | ISSUED AS CODE 2 - NO COMMENTS | 100 | 04/07/2025 | BNO-MABU-300-MP-7737-10005_R01.DOCX | 1,61 MB | 25/06/2025 05:57:02 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/04/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00244 | R01 | 06/23/2025 | BNO-MABU-SNEPCO-2025-INC-00325 | 06/24/2025 | BNO/EXT/MABU/00688 (OVERDUE) RECEIVED FROM CPY ON 25-07-2025) | 07/25/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10099 | 07/27/2025 | NR | NA
BNO-MABU-300-MP-7737-10006 |  | STANDARD SPECIFICATION FOR INSULATION | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ISSUED | 04/06/2025 | 07/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-MP-7737-10006_R01.DOCX | 1,3 MB | 02/06/2025 04:36:27 |  |  |  |  | 24/06/2025 09:22:21 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 06/13/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00179 | R01 | 06/02/2025 | BNO-MABU-SNEPCO-2025-INC-00266 | 06/04/2025 | BNO_EXT_MABU_00637 | 06/24/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10087 | 07/07/2025
BNO-MABU-300-MP-7737-10008 |  | SPECIFICATION FOR PIPING SUPPORT MATERIALS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ENG_IFR COMMENTS - MABU | 05/06/2025 |  | ANDREA.SANTOS | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 19/06/2025 | BNO-MABU-300-MP-7737-10008_R01.DOCX | 828,94 KB | 05/06/2025 05:31:08 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00190 | R01 | 06/05/2025 | BNO/MABU-SNEPCO-2025-INC-00268 | 06/05/2025 | BNO/EXT/MABU/00640 | 6/26/2025 | CODE 3 - MINOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-MP-7737-10009 |  | SPECIFICATION FOR VARIABLE AND CONSTANT LOAD SPRING SUPPORTS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ISSUED | 03/07/2025 | 27/07/2025 |  | ISSUED AS CODE 1 - APPROVED | 100 | 16/07/2025 | BNO-MABU-300-MP-7737-10009_R01.PDF | 576,01 KB | 03/07/2025 12:15:34 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00295 | R01 | 07/02/2025 | BNO-MABU-SNEPCO-2025-INC-00368 | 07/03/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10099 | 07/27/2025 | R | P2
BNO-MABU-300-MP-7753-10001 |  | 60% MODEL REVIEW TERMS OF REFERENCE | MP - PIPING | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | ISSUED | 18/06/2025 | 27/07/2025 |  |  | 100 | 02/07/2025 | BNO-MABU-300-MP-7753-10001_A01.DOCX | 2,54 MB | 18/06/2025 13:41:36 |  |  |  |  | 04/06/2025 05:22:33 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 07/02/2025 | 07/02/2025 |  | BON-DAE-WESTPAQ-2025-TX-00215 | A01 | 06/18/2025 | BNO/MABU-SNEPCO-2025-INC-00300 | 07/02/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10099 | 07/27/2025 | INFO | NA
BNO-MABU-300-MP-7753-10002 |  | 90% MODEL REVIEW TERMS OF REFERENCE | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 08/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 07/08/2025 | 08/01/2025 | 8/20/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-7880-10002-001 |  | SPECIAL PIPING SUPPORT DRAWINGS | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 07/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 05/07/2025 | 6/25/2025 | 7/14/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MP-8005-10001 |  | PIPING STRESS ANALYSIS REPORT - PUMPS S-4046-A/B E P-4047 | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 19/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/19/2025 | 9/23/2025 | 10/10/2025 | [10 empty] | R | P2
BNO-MABU-300-MP-8005-10002 |  | PIPING STRESS ANALYSIS REPORT - LAUNCHER AND RECEIVER A-0820J | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 19/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/19/2025 | 9/23/2025 | 10/10/2025 | [10 empty] | R | P2
BNO-MABU-300-MP-8005-10003 |  | PIPING STRESS ANALYSIS REPORT - LAUNCHER AND RECEIVER A-0820K | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 19/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/19/2025 | 9/23/2025 | 10/10/2025 | [10 empty] | R | P2
BNO-MABU-300-MP-8005-10004 |  | PIPING STRESS ANALYSIS REPORT - SYSTEMS S-14/S-15 | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 19/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/19/2025 | 9/23/2025 | 10/10/2025 | [10 empty] | R | P2
BNO-MABU-300-MP-8005-10005 |  | PIPING STRESS ANALYSIS REPORT - SYSTEMS S-03/S-07 | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 19/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/19/2025 | 9/23/2025 | 10/10/2025 | [10 empty] | R | P2
BNO-MABU-300-MP-8005-10006 |  | PIPING STRESS ANALYSIS REPORT - SYSTEMS S-11/12/13/15 | MP - PIPING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 19/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 8/19/2025 | 9/23/2025 | 10/10/2025 | [10 empty] | R | P2
BNO-MABU-300-MP-8502-10003 |  | REQUEST FOR ORIGINAL EQUIPMENT MANUFACTURER (OEM) DOCUMENTS AND DRAWINGS | MP - PIPING | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A4 | 0 | NÃO SE APLICA | 14/04/2025 |  |  |  | 50 | 25/04/2025 | BNO-MABU-300-MP-8502-10003_A01.DOCX | 145,58 KB | 14/04/2025 02:04:17 |  | 14/04/2025 06:47:34 | A01 | IFI - ISSUED FOR INFORMATION | [7 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00067 | A01 | 04/11/2025 | BNO-MABU-SNEPCO-2025-INC-00150 | 4/14/2025 | BNO/EXT/MABU/00503 | 4/17/2025 | 4
BNO-MABU-300-MP-8502-10004 |  | DAE REQUEST MABU TO REVIEW THE ATTACHED CALCULATION SHEETS COMPARING DED RECOMMENDED PIPE WALL THICKNESSES | NÃO SE APLICA | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.17-MP-PIPING | A0 | 0 | ISSUED | 05/06/2025 | 09/07/2025 |  | ISSUED AS CODE 1 - APPROVED | 50 | 19/06/2025 | BNO-MABU-300-MP-8502-10004_R01.DOCX | 631,98 KB | 05/06/2025 09:39:54 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BNO-MABU-300-MP-8502-10004_DED Piping Wall Thickness for J1, J2, J3 and 235841A Piping Classes | R01 | 06/05/2025 | [5 empty] | BNO-MABU-DAE-2025-TN-10089 | 07/09/2025
BNO-MABU-300-MP-8502-10005 |  | GASLIFT LINE TO UMBILICAL INTERFACE CONNECTION DETAILS | MP - PIPING | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 09/07/2025 | BNO-MABU-300-MP-8502-10005=A01.DOCX | 6,25 MB | 09/07/2025 05:57:22 | [11 empty] | IFI - ISSUED FOR INFORMATION
BNO-MABU-300-MR-2105-10001 |  | MECHANICAL DATASHEET FOR GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MR - MECHANICAL ROTATING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING | A4 | 0 | ENG_IFR CONSOLIDATION | 26/05/2025 |  | S.IYALEKHUE | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 09/06/2025 | BNO-MABU-300-MR-2105-10001_R01.XLSX | 1,13 MB | 26/05/2025 06:46:07 |  | 26/05/2025 11:54:00 | R01 | IFR - ISSUED FOR REVIEW | 23/06/2025 10:16:20 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 06/06/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00148 | R01 | 05/26/2025 | BNO-MABU-SNEPCO-2025-INC-00231 | 05/26/2025 | BNO/EXT/MABU/00616 | 6/19/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-MR-2105-10002 |  | MECHANICAL DATASHEET FOR METHANOL INJECTION PUMPS (P-4270A/B/C/D) | MR - MECHANICAL ROTATING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING | A4 | 0 | ENG_IFR CONSOLIDATION | 16/05/2025 |  | S.IYALEKHUE | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 04/04/2025 | BNO-MABU-300-MR-2105-10002_R01.XLSX | 217,32 KB | 16/05/2025 09:45:57 |  | 16/05/2025 11:20:59 | R01 | IFR - ISSUED FOR REVIEW | 30/05/2025 09:44:55 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 04/04/2025 | 06/06/2025 | 6/27/2025 | BON-DAE-WESTPAQ-2025-TX-00115 | R01 | 5/16/2025 | BNO-MABU-SNEPCO-2025-INC-00205 | 5/16/2025 | BNO_EXT_MABU_00573 | 5/30/2025 | 3 |  |  | R | P2
BNO-MABU-300-MR-2105-10003 |  | MECHANICAL DATASHEET FOR CORROSION INHIBITOR INJECTION PUMPS (P-4280A/B/C/D) | MR - MECHANICAL ROTATING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING | A4 | 0 | ENG_IFR CONSOLIDATION | 16/05/2025 |  | S.IYALEKHUE | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 28/02/2025 | BNO-MABU-300-MR-2105-10003_R01.XLSX | 214,84 KB | 16/05/2025 09:49:36 |  | 16/05/2025 11:20:59 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 2/28/2025 | 05/02/2025 | 5/23/2025 | BON-DAE-WESTPAQ-2025-TX-00115 | R01 | 5/16/2025 | BNO-MABU-SNEPCO-2025-INC-00205 | 5/16/2025 | BNO/EXT/MABU/00575 | 06/02/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-MR-2105-10004 |  | MECHANICAL DATASHEET FOR UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MR - MECHANICAL ROTATING | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 23/06/2025 |  | S.IYALEKHUE | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 07/07/2025 | BNO-MABU-300-MR-2105-10004_A01.PDF | 259,02 KB | 23/06/2025 04:11:45 |  | 23/05/2025 04:58:09 | R01 | IFR - ISSUED FOR REVIEW | 10/06/2025 05:31:18 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  | 07/07/2025 |  | BON-DAE-WESTPAQ-2025-TX-00237 | A01 | 06/23/2025 | BNO/MABU-SNEPCO-2025-INC-00320 | 06/23/2025 | BNO/EXT/MABU/00668 | 07/09/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10092 | 07/16/2025 | R | P2
BNO-MABU-300-MR-7303-10001 |  | MATERIAL REQUISITION FOR GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MR - MECHANICAL ROTATING | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 26/06/2025 |  | S.IYALEKHUE | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 11/07/2025 | BNO-MABU-300-MR-7303-10001_A01.DOCX | 977,28 KB | 26/06/2025 09:40:25 |  | 26/05/2025 11:54:00 | R01 | IFR - ISSUED FOR REVIEW | 23/06/2025 10:16:21 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00255 | A01 | 06/26/2025 | BNO-MABU-SNEPCO-2025-INC-00338 | 06/26/2025 | BNO_EXT_MABU_00692 | 07/17/2025 | OVERDUE | BNO-MABU-DAE-20205-TN-10092 | 07/16/2025 | R | P2
BNO-MABU-300-MR-7303-10002 | BNO-MABU-300-MR-7303-10002 | MATERIAL REQUISITION FOR METHANOL INJECTION PUMPS (P-4270A/B/C/D) | MR - MECHANICAL ROTATING | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 06/07/2025 |  | S.IYALEKHUE |  | 50 | 18/07/2025 | BNO-MABU-300-MR-7303-10002_A01.DOCX | 882,63 KB | 06/07/2025 10:42:26 |  | 14/05/2025 07:21:56 | R01 | IFR - ISSUED FOR REVIEW | 29/05/2025 09:48:22 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 05/09/2025 | 07/18/2025 |  | BON-DAE-WESTPAQ-2025-TX-00307 | A01 | 07/06/2025 | BNO-MABU-SNEPCO-2025-INC-00374 | 07/06/2025 | [5 empty] | R | P2
BNO-MABU-300-MR-7303-10003 |  | MATERIAL REQUISITION FOR CORROSION INHIBITOR INJECTION PUMPS (P-4280A/B/C/D) | MR - MECHANICAL ROTATING | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 06/07/2025 |  | S.IYALEKHUE |  | 50 | 18/07/2025 | BNO-MABU-300-MR-7303-10003_A01.DOCX | 891,97 KB | 06/07/2025 10:44:06 |  | 16/05/2025 11:20:59 | R01 | IFR - ISSUED FOR REVIEW | 30/05/2025 07:14:24 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 05/09/2025 | 07/18/2025 | 08/01/2025 | BON-DAE-WESTPAQ-2025-TX-00307 | A01 | 07/06/2025 | BNO-MABU-SNEPCO-2025-INC-00374 | 07/18/2025 | BNO/EXT/MABU/00711 (OVERDUE) | 07/24/2025 | CODE 4 - MAJOR COMMENTS |  |  | R | P2
BNO-MABU-300-MR-7303-10004 |  | MATERIAL REQUISITION FOR THE UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MR - MECHANICAL ROTATING | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING | A4 | 0 | NÃO SE APLICA |  |  |  | ISSUED AS CODE 2 - NO COMMENTS | 50 | 11/07/2025 | BNO-MABU-300-MR-7303-10004_A01.DOCX | 881,13 KB | 27/06/2025 08:51:01 |  | 27/05/2025 09:45:07 | R01 | IFR - ISSUED FOR REVIEW | 23/06/2025 10:16:23 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  | 07/11/2025 |  | BON-DAE-WESTPAQ-2025-TX-00266 | A01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00350 | 06/27/2025 | BNO_EXT_MABU_00692 | 07/17/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10092 | 07/16/2025 | R | P2
BNO-MABU-300-MR-7303-10005 |  | WATERFLOOD INJECTION PUMP SIZING CALCULATION AND REPORT (POWER REQUIREMENT) | MR - MECHANICAL ROTATING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING | A4 | 0 | ENG_IFR CONSOLIDATION | 10/06/2025 |  | S.IYALEKHUE | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 24/06/2025 | BNO-MABU-300-MR-7303-10005_R01.XLSX | 605,43 KB | 10/06/2025 09:55:17 |  |  |  |  | 30/06/2025 06:18:46 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 07/24/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00196 | R01 | 06/10/2025 | BNO-MABU-SNEPCO-2025-INC-00277 | 06/13/2025 | BNO_EXT_MABU_00646 | 06/30/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10084 | 07/02/2025 | R | P2
BNO-MABU-300-MR-7771-10001 |  | SPECIFICATION FOR THE GT DRIVEN WATERFLOOD INJECTION PUMP (P-4047) | MR - MECHANICAL ROTATING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING | A4 | 0 | ENG_IFR CONSOLIDATION | 04/05/2025 |  | S.IYALEKHUE | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 10/04/2025 | BNO-MABU-300-MR-7771-10001_R01.DOCX | 944,99 KB | 04/05/2025 07:58:34 |  | 06/05/2025 05:42:46 | R01 | IFR - ISSUED FOR REVIEW | 22/05/2025 04:45:11 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 04/10/2025 | 06/12/2025 | 07/03/2025 | BON-DAE-WESTPAQ-2025-TX-00091 | R01 | 05/02/2025 | BNO-MABU-SNEPCO-2025-INC-00181 | 05/06/2025 | [5 empty] | R | P2
BNO-MABU-300-MR-7771-10002 |  | SPECIFICATION FOR METHANOL INJECTION PUMPS P-4280A/B/C/D | MR - MECHANICAL ROTATING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING | A4 | 0 | ENG_IFR CONSOLIDATION | 07/05/2025 |  | S.IYALEKHUE | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 10/04/2025 | BNO-MABU-300-MR-7771-10002_R01.DOCX | 857,06 KB | 29/04/2025 02:57:37 |  | 29/04/2025 04:45:17 | R01 | IFR - ISSUED FOR REVIEW | 14/05/2025 05:14:36 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 04/10/2025 | 06/12/2025 | 07/03/2025 | BON-DAE-WESTPAQ-2025-TX-00085 | R01 | 4/29/2025 | BNO-MABU-SNEPCO-2025-INC-00166 | 4/29/2025 | [5 empty] | R | P2
BNO-MABU-300-MR-7771-10003 |  | SPECIFICATION FOR CORROSION INHIBITOR INJECTION PUMPS (P-4270A/B/C/D) | MR - MECHANICAL ROTATING | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING | A4 | 0 | ENG_IFR CONSOLIDATION | 07/05/2025 |  | S.IYALEKHUE | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 10/04/2025 | BNO-MABU-300-MR-7771-10003_R01.DOCX | 862,06 KB | 29/04/2025 02:58:09 |  | 29/04/2025 04:45:17 | R01 | IFR - ISSUED FOR REVIEW | 22/05/2025 04:45:13 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 04/10/2025 | 06/12/2025 | 07/03/2025 | BON-DAE-WESTPAQ-2025-TX-00085 | R01 | 4/29/2025 | BNO-MABU-SNEPCO-2025-INC-00166 | 4/29/2025 | [5 empty] | R | P2
BNO-MABU-300-MR-7771-10004 |  | SPECIFICATION FOR THE UPGRADED WATERFLOOD INJECTION PUMP (P-4046A) | MR - MECHANICAL ROTATING | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.18-MR-MECHANICAL_ROTATING | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 20/06/2025 |  | S.IYALEKHUE |  | 50 | 04/07/2025 | BNO-MABU-300-MR-7771-10004_A01.DOCX | 889,18 KB | 20/06/2025 06:23:02 |  | 06/05/2025 05:42:46 | R01 | IFR - ISSUED FOR REVIEW | 22/05/2025 04:45:15 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00233 | R01 | 06/20/2025 | BNO/MABU-SNEPCO-2025-INC-00312 | 06/20/2025 | BNO/EXT/MABU/00657 | 07/04/2025 | OVERDUE |  |  | R | P2
BNO-MABU-300-MS-1208-10001 |  | PIG LAUNCHER DESIGN CALCULATION FOR PRODUCTION FLOWLINE AND REPORT | MS - MECHANICAL STATIC | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.19-MS-MECHANICAL_STATIC | A4 | 0 | ISSUED | 25/06/2025 | 08/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 04/07/2025 | BNO-MABU-300-MS-1208-10001_A01.XLSX | 679,81 KB | 25/06/2025 04:16:03 |  | 06/05/2025 05:42:46 | R01 | IFR - ISSUED FOR REVIEW | 04/06/2025 08:16:56 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 4/15/2025 | 07/04/2025 | 07/08/2025 | BON-DAE-WESTPAQ-2025-TX-00240 | A01 | 06/23/2025 | BNO-MABU-SNEPCO-2025-INC-00324 | 06/24/2025 | BNO_EXT_MABU_00690 | 07/16/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10088 | 07/08/2025 | R | P2
BNO-MABU-300-MS-2105-10001 |  | MECHANICAL DATASHEET FOR PIG LAUNCHER/RECEIVER (A-0820J/K) | MS - MECHANICAL STATIC | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.19-MS-MECHANICAL_STATIC | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 11/04/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 04/11/2025 | 6/13/2025 | 07/04/2025 | [10 empty] | R | P2
BNO-MABU-300-MS-4322-10001 |  | MTO FOR PIG LAUNCHER AND RECEIVER (A-0820J /K) | MS - MECHANICAL STATIC | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.19-MS-MECHANICAL_STATIC | A4 | 0 | NÃO SE APLICA |  |  |  | ISSUED AS CODE 2 - NO COMMENTS | 50 | 11/07/2025 | BNO-MABU-300-MS-4322-10001_A01.XLSX | 126,76 KB | 26/06/2025 09:52:38 |  | 09/05/2025 06:32:13 | R01 | IFR - ISSUED FOR REVIEW | 21/05/2025 06:23:51 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 5/28/2025 | 07/11/2025 | 8/20/2025 | BON-DAE-WESTPAQ-2025-TX-00255 | A01 | 07/11/2025 | BNO-MABU-SNEPCO-2025-INC-00338 | 06/26/2025 | BNO/EXT/MABU/00681 | 07/14/2025 | CODE 1 - APPROVED | BNO-MABU-DAE-2025-TN-10093 | 07/17/2025 | INFO | NA
BNO-MABU-300-MS-7303-10001 |  | MATERIAL REQUISITION FOR QUICK OPENING END CLOSURES FOR PIG LAUNCHER AND RECEIVER (QOE-A-0820J /K) | MS - MECHANICAL STATIC | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.19-MS-MECHANICAL_STATIC | A4 | 0 | ISSUED | 08/05/2025 | 07/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 02/04/2025 | BNO-MABU-300-MS-7303-10001_R01.DOCX | 881,59 KB | 08/05/2025 04:02:37 |  | 09/05/2025 06:32:13 | R01 | IFR - ISSUED FOR REVIEW | 21/05/2025 06:21:15 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 04/02/2025 | 06/04/2025 | 6/25/2025 | BON-DAE-WESTPAQ-2025-TX-00095 | R01 | 05/08/2025 | BNO-MABU-SNEPCO-2025-INC-00186 | 05/09/2025 | [5 empty] | INFO | NA
BNO-MABU-300-MS-7771-10001 |  | SPECIFICATIONS FOR PIG LAUNCHER/RECEIVER (A-0820J /K) | MS - MECHANICAL STATIC | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.19-MS-MECHANICAL_STATIC | A4 | 0 | ISSUED | 05/06/2025 | 07/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 19/06/2025 | BNO-MABU-300-MS-7771-10001_R01.DOCX | 1,51 MB | 05/06/2025 05:11:29 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00188 | R01 | 06/05/2025 | BNO/MABU-SNEPCO-2025-INC-00268 | 06/05/2025 | BNO/EXT/MABU/00640 | 6/26/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10100 | 07/28/2025 | R | P2
BNO-MABU-300-MX-4018-10001-001 |  | GA DRAWING FOR SUBSEA WELLS PIG LAUNCHER AND RECEIVER | MX - OVERAL MECHANICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.20-MX-MECHANICAL | A0 | 0 | ENG_IFR LEAD ASSIGNMENT | 12/07/2025 |  | S.IYALEKHUE |  | 50 | 25/07/2025 | BNO-MABU-300-MX-4018-10001-001_R01.DWG | 850,23 KB | 12/07/2025 07:02:34 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/25/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00356 | R01 | 07/12/2025 | BNO-MABU-SNEPCO-2025-INC-00397 | 07/12/2025
BNO-MABU-300-MX-6612-10001 |  | MECHANICAL EQUIPMENT LIST | MX - OVERAL MECHANICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.20-MX-MECHANICAL | A4 | 0 | ENG_IFR CONSOLIDATION | 30/05/2025 |  | S.IYALEKHUE | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 13/06/2025 | BNO-MABU-300-MX-6612-10001_R01.XLSX | 142,75 KB | 30/05/2025 09:07:36 |  | 30/05/2025 09:49:21 | R01 | IFR - ISSUED FOR REVIEW | 24/06/2025 05:45:16 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00165 | R01 | 05/30/2025 | BNO-MABU-SNEPCO-2025-INC-00250 | 5/30/2025 | BNO/EXT/MABU/00630 | 6/24/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-MX-7180-10001 |  | MECHANICAL HANDLING PHILOSOPHY | MX - OVERAL MECHANICAL | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.20-MX-MECHANICAL | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 10/07/2025 |  | S.IYALEKHUE |  | 50 | 23/07/2025 | BNO-MABU-300-MX-7180-10001_A01.DOCX | 968,25 KB | 10/07/2025 06:53:18 |  | 26/05/2025 11:54:00 | R01 | IFR - ISSUED FOR REVIEW | 16/06/2025 05:15:17 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 06/06/2025 | 07/23/2025 |  | BON-DAE-WESTPAQ-2025-TX-00337 | A01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00386 | 07/09/2025 |  |  | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10092 | 07/16/2025 | INFO | NA
BNO-MABU-300-MX-7180-10002 |  | MECHANICAL HANDLING STUDY REPORT - WATERFLOOD INJECTION PUMPS | MX - OVERAL MECHANICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.20-MX-MECHANICAL | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 17/06/2025 |  | S.IYALEKHUE | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 01/07/2025 | BNO-MABU-300-MX-7180-10002_R01.DOCX | 2,93 MB | 17/06/2025 07:25:25 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/01/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00209 | R01 | 06/16/2025 | BNO-MABU-SNEPCO-2025-INC-00298 | 06/18/2025 | BNO/EXT/MABU/00688 (OVERDUE, RCVD LATE FROM CPY AND SHARED WITH MABU DLL ON SAME DATE 25-07-25 |  | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10084 | 07/01/2025 | NR | NA
BNO-MABU-300-MX-7180-10003 |  | MECHANICAL HANDLING STUDY REPORT | MX - OVERAL MECHANICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.20-MX-MECHANICAL | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 13/06/2025 |  | S.IYALEKHUE | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 27/06/2025 | BNO-MABU-300-MX-7180-10003_R01.DOCX | 1,69 MB | 13/06/2025 07:22:22 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00203 | R01 | 06/13/2025 | BNO-MABU-SNEPCO-2025-INC-00280 | 06/13/2025 | BNO/EXT/MABU/00688 (OVERDUE, RCVD FROM CPY, AND SHARED WITH MABU DL ON 25-07-25 | 07/25/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10084 | 07/01/2025 | R | P2
BNO-MABU-300-MX-7180-10004 |  | RELIABILITY_ OPERABILITY AND MAINTAINABILITY REVIEWS REPORT | MX - OVERAL MECHANICAL | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.20-MX-MECHANICAL | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 30/06/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 6/30/2025 | 09/01/2025 | 9/22/2025 | [10 empty] | INFO | NA
BNO-MABU-300-MX-8502-10001 |  | RAM STUDY ASSUMPTIONS ALIGNMENT AND CONFIRMATION | MX - OVERAL MECHANICAL | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A0 | 0 | ENGINEERING CONSOLIDATION | 24/06/2025 |  | S.IYALEKHUE |  | 0 | 03/07/2025 | BNO-MABU-300-MX-8502-10001_A01.DOCX | 176,1 KB | 19/06/2025 08:48:12 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00220 | A01_IFI | 06/19/2025 | N/A |  |  |  |  | BNO-MABU-DAE-2025-TN-10088 | 07/08/2025
BNO-MABU-300-MX-8502-10002 |  | RAM STUDY DOCUMENT AND INFORMATION REQUEST | MX - OVERAL MECHANICAL | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A0 | 0 | ENGINEERING CONSOLIDATION | 12/07/2025 |  | S.IYALEKHUE |  | 0 | 25/07/2025 | BNO-MABU-300-MX-8502-10002=A01.DOCX | 173,68 KB | 12/07/2025 06:46:01 | [11 empty] | IFI - ISSUED FOR INFORMATION |  | 07/25/2025 |  | BON-DAE-WESTPAQ-2025-TX-00355 | A01 | 07/12/2025 | N/A
BNO-MABU-300-PX-0580-10001 |  | UTILITY CONSUMPTION SUMMARY | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 27/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/27/2025 | 07/08/2025 | 7/18/2025 | [10 empty] | NR | NA
BNO-MABU-300-PX-0580-10002 |  | BN SYSTEM PRESSURE SETTING REPORT | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 22/07/2025 | BNO-MABU-300-PX-0580-10002_R01.DOCX | 828,01 KB | 08/07/2025 13:52:34 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/22/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00319 | R01 | 07/08/2025 | BNO-MABU-SNEPCO-2025-INC-00380 | 07/08/2025 | [5 empty] | R | P2
BNO-MABU-300-PX-0580-10003 |  | EQUIPMENT & LINE SIZING VALIDATION REPORT | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 28/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/28/2025 | 07/09/2025 | 7/21/2025 | [10 empty] | R | P2
BNO-MABU-300-PX-0580-10004 |  | PROCESS SIMULATION REPORT | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ISSUED | 26/06/2025 | 21/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 11/07/2025 | BNO-MABU-300-PX-0580-10004_R01.DOCX | 1,19 MB | 26/06/2025 08:50:22 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00258 | R01 | 06/26/2025 | BNO-MABU-SNEPCO-2025-INC-00337 | 06/26/2025 | BNO_EXT_MABU_00687 | 07/16/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10096 | 07/22/2025 | R | P2
BNO-MABU-300-PX-0580-10005 |  | PURGE AND LEAK TEST PACK (REVIEW OF SHUTDOWN REQUIREMENTS) | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 19/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/19/2025 | 6/30/2025 | 07/10/2025 | [10 empty] | INFO | NA
BNO-MABU-300-PX-1216-10001 |  | HEAT AND MASS BALANCE REPORT | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ISSUED | 16/05/2025 | 09/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 28/04/2025 | BNO-MABU-300-PX-1216-10001_R01.XLSX | 582,51 KB | 16/05/2025 02:22:38 |  | 16/05/2025 08:58:53 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW | 4/28/2025 | 06/09/2025 | 6/19/2025 | BON-DAE-WESTPAQ-2025-TX-00109 | R01 | 05/15/2025 | BNO-MABU-SNEPCO-2025-INC-00204 | 05/16/2025 | BNO/EXT/MABU/00567 | 05/29/2025 |  | BNO-MABU-DAE-2025-TN-10070 | 06/10/2025 | INFO | NA
BNO-MABU-300-PX-1380-10001 |  | WATERFLOOD INJECTION SIZING CALCULATION REPORT P-4047 | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR COMMENTS - MABU | 17/07/2025 |  | ANDREA.SANTOS,FLAVIAMORAES.FRM,S.IYALEKHUE |  | 50 | 31/07/2025 | BNO-MABU-300-PX-1380-10001_A01.DOCX | 1,42 MB | 17/07/2025 09:12:14 |  | 13/06/2025 04:21:32 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFA - ISSUED FOR APPROVAL | 06/27/2025 | 07/31/2025 |  | BON-DAE-WESTPAQ-2025-TX-00375 | A01 | 07/17/2025 | BNO-MABU-SNEPCO-2025-INC-00413 | 07/17/2025 | [5 empty] | R | P2
BNO-MABU-300-PX-1380-10002 |  | DRAINAGE SYSTEM CALCULATION NOTES | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 10/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 23/07/2025 | BNO-MABU-300-PX-1380-10002_R01.DOCX | 4,49 MB | 10/07/2025 07:13:27 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/23/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00334 | R01 |  | BNO-MABU-SNEPCO-2025-INC-00387 | 07/09/2025 | [5 empty] | R | P2
BNO-MABU-300-PX-1380-10003 |  | METHANOL PUMP PROCESS CALCULATION NOTES | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | NÃO SE APLICA |  |  |  |  | 50 | 21/07/2025 | BNO-MABU-300-PX-1380-10003_A01.DOCX | 1,31 MB | 07/07/2025 05:21:00 | [11 empty] | IFA - ISSUED FOR APPROVAL | 06/30/2025 | 07/21/2025 |  | BON-DAE-WESTPAQ-2025-TX-00313 | A01 | 07/07/2025 | BNO-MABU-SNEPCO-2025-INC-00377 | 07/07/2025 | BNO/EXT/MABU/00652 | 07/03/2025 | OVERDUE |  |  | R | P2
BNO-MABU-300-PX-1380-10004 |  | CORROSION INHIBITOR PUMP PROCESS CALCULATION NOTES | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ISSUED | 18/06/2025 | 07/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 02/07/2025 | BNO-MABU-300-PX-1380-10004_R01.DOCX | 1,99 MB | 18/06/2025 15:02:21 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/02/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00217 | R01 | 06/18/2025 | BNO-MABU-SNEPCO-2025-INC-00302 | 06/18/2025 | BNO/EXT/MABU/00673 | 07/11/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10087 | 07/07/2025 | R | P2
BNO-MABU-300-PX-1380-10005 |  | WATERFLOOD INJECTION PUMPS SIZING CALCULATION REPORT P-4046 A | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR COMMENTS - MABU | 17/07/2025 |  | ANDREA.SANTOS,FLAVIAMORAES.FRM,S.IYALEKHUE |  | 50 | 31/07/2025 | BNO-MABU-300-PX-1380-10005_A01.DOCX | 1,38 MB | 17/07/2025 09:24:52 |  | 13/06/2025 04:21:32 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFA - ISSUED FOR APPROVAL | 06/27/2025 | 07/31/2025 |  | BON-DAE-WESTPAQ-2025-TX-00376 | A01 | 07/17/2025 | BNO-MABU-SNEPCO-2025-INC-00413 | 07/17/2025 | [5 empty] | R | P2
BNO-MABU-300-PX-1380-10008 |  | CONTROL VALVES CALCULATION NOTES | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR CONSOLIDATION | 02/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 15/07/2025 | BNO-MABU-300-PX-1380-10008_R01.DOCX | 184,41 KB | 02/07/2025 16:30:05 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/15/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00294 | R01 | 07/01/2025 | BNO-MABU-SNEPCO-2025-INC-00362 | 07/02/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-1380-10009 |  | FLOW INSTRUMENTS CALCULATION NOTES | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR COMMENTS - MABU | 02/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 15/07/2025 | BNO-MABU-300-PX-1380-10009_R01.DOCX | 244,71 KB | 02/07/2025 05:38:49 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/15/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00286 | R01 | 07/01/2025 | BNO-MABU-SNEPCO-2025-INC-00362 | 07/02/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-1380-10010 |  | PRESSURE INSTRUMENTS CALCULATION NOTES | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR COMMENTS - MABU | 29/06/2025 |  | FLAVIAMORAES.FRM |  | 50 | 11/07/2025 | BNO-MABU-300-PX-1380-10010_R01.DOCX | 278,67 KB | 29/06/2025 13:45:46 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00269 | R01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00353 | 06/29/2025 | BNO/EXT/MABU/00705 (OVERDUE0 | 07/23/2025 | CODE 3 - MINOR COMMENTS |  |  | INFO | NA
BNO-MABU-300-PX-1380-10011 |  | TEMPERATURE INSTRUMENTS CALCULATION NOTES | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ISSUED | 29/06/2025 | 21/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 11/07/2025 | BNO-MABU-300-PX-1380-10011_R01.DOCX | 192,33 KB | 29/06/2025 13:05:53 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00271 | R01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00353 | 06/29/2025 | BNO/EXT/MABU/00702 | 07/22/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10096 | 07/22/2025 | INFO | NA
BNO-MABU-300-PX-1380-10012 |  | FLARE SYSTEM CALCULATION NOTES | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 28/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/28/2025 | 07/09/2025 | 7/21/2025 | [10 empty] | R | P2
BNO-MABU-300-PX-1380-10013 |  | DESPRESSURIZATION SYSTEM CALCULATION NOTES | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 19/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/19/2025 | 6/30/2025 | 07/10/2025 | [10 empty] | R | P2
BNO-MABU-300-PX-1380-10015 |  | PROCESS SAFETY TIME CALCULATIONS | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 01/08/2025 | BNO-MABU-300-PX-1380-10015_R01.DOCX | 964,89 KB | 19/07/2025 04:15:15 | [11 empty] | IFR - ISSUED FOR REVIEW | 5/19/2025 | 6/30/2025 | 7/18/2025 | BON-DAE-WESTPAQ-2025-TX-00384 | R01 | 07/19/2025 | BNO-MABU-SNEPCO-2025-INC-00421 | 07/19/2025 | [5 empty] | R | P2
BNO-MABU-300-PX-2105-10001 |  | PROCESS DATASHEETS FOR SAND DETECTOR | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR COMMENTS - MABU | 12/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 25/07/2025 | BNO-MABU-300-PX-2105-10001_A01.DOCX | 758,18 KB | 12/07/2025 05:30:51 |  | 28/05/2025 07:25:32 | R01 | IFR - ISSUED FOR REVIEW | 01/07/2025 05:37:33 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 06/11/2025 | 07/25/2025 |  | BON-DAE-WESTPAQ-2025-TX-00347 | A01 | 07/11/2025 | BNO-MABU-SNEPCO-2025-INC-00396 | 07/11/2025
BNO-MABU-300-PX-2105-10002 |  | PROCESS DATASHEETS FOR CHOKE VALVES | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR COMMENTS - MABU | 29/06/2025 |  | FLAVIAMORAES.FRM |  | 50 | 11/07/2025 | BNO-MABU-300-PX-2105-10002_R01.DOCX | 169,91 KB | 29/06/2025 14:00:55 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00269 | R01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00353 | 07/11/2025 | BNO/EXT/MABU/00702 | 07/22/2025 | OVERDUE |  |  | INFO | NA
BNO-MABU-300-PX-2105-10003 |  | PROCESS DATASHEET FOR WATERFLOOD INJECTION PUMP UPGRADE (P-4046A) | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR COMMENTS - MABU | 25/07/2025 |  | ANDREA.SANTOS,S.IYALEKHUE,FLAVIAMORAES.FRM |  | 50 | 08/08/2025 | BNO-MABU-300-PX-2105-10003_A01.XLSX | 128,96 KB | 25/07/2025 10:03:40 |  | 16/05/2025 11:20:59 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFI - ISSUED FOR INFORMATION | 05/12/2025 | 7/14/2025 | 7/24/2025 | BON-DAE-WESTPAQ-2025-TX-00409 | A01 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00447 | 07/25/2025 | BNO/EXT/MABU/00567 | 05/29/2025 |  | BNO-MABU-DAE-2025-TN-10094 | 07/18/2025 | R | P2
BNO-MABU-300-PX-2105-10004 |  | PROCESS DATASHEET FOR CORROSION INHIBITOR PUMP | PX - PROCESS | R02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ISSUED | 03/05/2025 | 06/06/2025 |  | ISSUED AS CODE 2 - NO COMMENTS | 50 | 28/05/2025 | BNO-MABU-300-PX-2105-10004_R02.XLSB | 114,43 KB | 17/04/2025 07:27:41 |  | 28/03/2025 10:28:00 | R01 | IFR - ISSUED FOR REVIEW | 20/05/2025 04:29:39 | R02 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 5/28/2025 | 07/09/2025 | 7/21/2025 | BON-DAE-WESTPAQ-2025-TX-00072 | R02 | 4/15/2025 | BNO/MABU-SNEPCO-2025-INC-00156 | 4/15/2025 | OVERDUE |  |  | BNO-MABU-DAE-2025-TN-10040 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2105-10006 |  | PROCESS DATASHEETS FOR CONTROL VALVES | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR CONSOLIDATION | 29/06/2025 |  | FLAVIAMORAES.FRM |  | 50 | 11/07/2025 | BNO-MABU-300-PX-2105-10006_R01.XLSX | 141,4 KB | 29/06/2025 16:14:42 | [11 empty] | IFR - ISSUED FOR REVIEW | 06/28/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00261 | R01 | 06/27/2025 | BNO-MABU-SNEPCO-2025-INC-00355 | 06/29/2025 | BNO/EXT/MABU/00705 (OVERDUE) | 07/23/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-PX-2105-10007 |  | PROCESS DATASHEETS FOR ON/OFF VALVES | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR COMMENTS - MABU | 09/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 23/07/2025 | BNO-MABU-300-PX-2105-10007_A01.DOCX | 184,42 KB | 09/07/2025 12:34:41 | [11 empty] | IFA - ISSUED FOR APPROVAL | 07/02/2025 | 07/23/2025 |  | BON-DAE-WESTPAQ-2025-TX-00325 | A01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-003802 | 07/09/2025 | [5 empty] | R | P2
BNO-MABU-300-PX-2105-10008 |  | PROCESS DATASHEETS FOR SHUTDOWN VALVES | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR COMMENTS - MABU | 03/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 30/06/2025 | BNO-MABU-300-PX-2105-10008_A01.DOCX | 199,36 KB | 03/07/2025 14:58:08 | [11 empty] | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00207 | A01 | 06/16/2025 | BNO-MABU-SNEPCO-2025-INC-00287 | 06/16/2025 | BNO/EXT/MABU/00652 | 07/03/2025 | OVERDUE |  |  | R | P2
BNO-MABU-300-PX-2105-10009 |  | PROCESS DATASHEET FOR TEMPERATURE INSTRUMENTS | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 24/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 23/07/2025 | BNO-MABU-300-PX-2105-10009_A01.DOCX | 192,47 KB | 09/07/2025 06:54:08 | [11 empty] | IFA - ISSUED FOR APPROVAL | 06/30/2025 | 07/23/2025 |  | BON-DAE-WESTPAQ-2025-TX-00327 | A01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00382 | 07/09/2025 | BNO/EXT/MABU/00655 | 07/03/2025 | OVERDUE |  |  | R | P2
BNO-MABU-300-PX-2105-10010 |  | PROCESS DATASHEET FOR FLOW INSTRUMENTS | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR COMMENTS - MABU | 03/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 16/07/2025 | BNO-MABU-300-PX-2105-10010_R01.DOCX | 244,87 KB | 03/07/2025 13:43:46 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/16/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00299 | R01 | 07/02/2025 | BNO-MABU-SNEPCO-2025-INC-00368 | 07/03/2025 | [5 empty] | R | P2
BNO-MABU-300-PX-2105-10011 |  | PROCESS DATASHEET FOR PRESSURE INSTRUMENTS | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR COMMENTS - MABU | 25/07/2025 |  | ARY.CARVALHO |  | 50 | 08/08/2025 | BNO-MABU-300-PX-2105-10011_A01.DOCX | 282,7 KB | 25/07/2025 08:18:28 |  |  |  |  | 01/07/2025 05:37:35 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 06/13/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00407 | A01 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00447 | 07/25/2025 | BNO_EXT_MABU_00648 | 07/01/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10084 | 07/01/2025 | R | P2
BNO-MABU-300-PX-2105-10012 |  | PROCESS DATASHEET FOR WATERFLOOD INJECTION PUMP NEW (P-4047) | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR COMMENTS - MABU | 25/07/2025 |  | ANDREA.SANTOS,S.IYALEKHUE,FLAVIAMORAES.FRM |  | 50 | 08/08/2025 | BNO-MABU-300-PX-2105-10012_A01.XLSX | 116,29 KB | 25/07/2025 10:04:05 |  | 16/05/2025 11:20:59 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFI - ISSUED FOR INFORMATION | 5/27/2025 | 07/08/2025 | 7/18/2025 | BON-DAE-WESTPAQ-2025-TX-00409 | A01 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00447 | 07/25/2025 | BNO/EXT/MABU/00567 | 5/19/2025 |  | BNO-MABU-DAE-2025-TN-10094 | 07/18/2025 | R | P2
BNO-MABU-300-PX-2105-10013 |  | PROCESS DATASHEET FOR HAND VALVES | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR CONSOLIDATION | 03/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 16/07/2025 | BNO-MABU-300-PX-2105-10013_A01.DOCX | 168,96 KB | 03/07/2025 13:51:39 | [11 empty] | IFA - ISSUED FOR APPROVAL | 07/04/2025 | 07/16/2025 |  | BON-DAE-WESTPAQ-2025-TX-00299 | A01 | 07/02/2025 | BNO/MABU-SNEPCO-2025-INC-00309 | 07/03/2025 | BNO_EXT_MABU_00682 | 07/14/2025 | OVERDUE |  |  | INFO | NA
BNO-MABU-300-PX-2105-10014 |  | PROCESS DATASHEETS FOR RELIEF VALVES | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR COMMENTS - MABU | 14/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 28/07/2025 | BNO-MABU-300-PX-2105-10014_R01.DOCX | 171,75 KB | 14/07/2025 05:02:49 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/28/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00365 | R01 | 07/14/2025 | BNO-MABU-SNEPCO-2025-INC-00403 | 07/14/2025 | [5 empty] | R | P2
BNO-MABU-300-PX-2105-10015 |  | PROCESS DATASHEET FOR METHANOL INJECTION PUMP | PX - PROCESS | R01 | 3 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ISSUED | 26/03/2025 | 26/05/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 12/05/2025 | BNO-MABU-300-PX-2105-10015_R01.XLSX | 114,55 KB | 27/03/2025 06:46:06 |  |  |  |  | 21/05/2025 04:32:25 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 05/12/2025 | 6/23/2025 | 07/03/2025 | BON-DAE-WESTPAQ-2025-TX-00021 | R01 | 3/14/2025 | BNO-MABU-SNEPCO-2025-INC-00129 | 04/01/2025 | BNO/EXT/MABU/00504 | 4/22/2025 | 3 |  |  | R | P2
BNO-MABU-300-PX-2365-10005-001 |  | P&ID- PRODUCTION SYSTEM-SUBSEA WELLS LAUNCHERS / RECEIVERS-MODIFICATION | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR COMMENTS - MABU | 23/07/2025 |  | PAULO.MAURICIO,G.JAMES,JOSESIMAO.EP |  | 50 | 06/08/2025 | BNO-MABU-300-PX-2365-10005-001.002 | 7,59 MB | 23/07/2025 09:26:23 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 21/05/2025 04:32:12 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00397 | A01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00435 | 07/23/2025 | [5 empty] | R | P2
BNO-MABU-300-PX-2365-10006-001 |  | P&ID- PRODUCTION SYSTEM -OIL/ OIL HEAT EXCHANGER-MODIFICATION | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR COMMENTS - MABU | 23/07/2025 |  | PAULO.MAURICIO,G.JAMES,JOSESIMAO.EP |  | 50 | 06/08/2025 | BNO-MABU-300-PX-2365-10006-001.002 | 4,75 MB | 23/07/2025 09:27:09 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 21/05/2025 04:32:27 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00397 | A01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00435 | 07/23/2025 | [5 empty] | R | P2
BNO-MABU-300-PX-2365-10007-001 |  | P&ID- PRODUCTION SYSTEMS GAS LIFT COMPRESSOR-MODIFICATION | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR COMMENTS - MABU | 23/07/2025 |  | JOSESIMAO.EP,FLAVIAMORAES.FRM,PAULO.MAURICIO,G.JAMES,PAULO.FERNANDES |  | 50 | 06/08/2025 | BNO-MABU-300-PX-2365-10007-001.002 | 1,9 MB | 23/07/2025 09:27:46 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 21/05/2025 04:32:21 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00397 | A01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00435 | 07/23/2025 | [5 empty] | R | P2
BNO-MABU-300-PX-2365-10008-001 |  | P&ID- PRODUCTION SYSTEMS GAS RISER LIFT METERS-MODIFICATION | PX - PROCESS | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR COMMENTS - MABU | 23/07/2025 |  | JOSESIMAO.EP,FLAVIAMORAES.FRM,PAULO.MAURICIO,G.JAMES,PAULO.FERNANDES |  | 50 | 06/08/2025 | BNO-MABU-300-PX-2365-10008-001_A01.PDF | 413,89 KB | 23/07/2025 08:56:47 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 21/05/2025 04:32:23 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00397 | A01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00435 | 07/23/2025 | [5 empty] | R | P2
BNO-MABU-300-PX-2365-10009-001 |  | P&ID - BN PRODUCTION SYSTEMS GAS RISER LIFT METER | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 07/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 11/02/2025 | BNO-MABU-300-PX-2365-10009-001_R01.PDF | 338,76 KB | 01/04/2025 14:50:48 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 21/05/2025 04:32:18 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00053 | R01 | 3/28/2025 | BNO-MABU-SNEPCO-2025-INC-00130 | 04/02/2025 | BNO/EXT/MABU/00504 | 4/22/2025 | 3 | BNO-MABU-DAE-2025-TN-10039 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10010-001 |  | P&ID - BN PRODUCTION SYSTEM PIG LAUNCHER /RECEIVER (A-0820J) | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 01/04/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 10 | 11/02/2025 | BNO-MABU-300-PX-2365-10010-001_R01.PDF | 357,28 KB | 01/04/2025 14:50:34 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 21/05/2025 04:32:14 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00053 | R01 | 3/28/2025 | BNO-MABU-SNEPCO-2025-INC-00130 | 04/02/2025 | BNO/EXT/MABU/00504 | 4/22/2025 | 3 | BNO-MABU-DAE-2025-TN-10028 | 4/23/2025 | R | P2
BNO-MABU-300-PX-2365-10011-001 |  | P&ID - BN PRODUCTION SYSTEM PIG LAUNCHER /RECEIVER (A-0820K) | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 03/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 11/02/2025 | BNO-MABU-300-PX-2365-10011-001_R01.PDF | 358,33 KB | 01/04/2025 14:49:52 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 02/05/2025 03:29:31 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00053 | R01 | 3/28/2025 | BNO-MABU-SNEPCO-2025-INC-00130 | 04/02/2025 | BNO/EXT/MABU/00513 | 4/25/2025 | 3 | BNO-MABU-DAE-2025-TN-10038 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10012-001 |  | P&ID- PRODUCTION SYSTEMS - PRODUCTION MANIFOLD -MODIFICATION | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 03/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 11/02/2025 | BNO-MABU-300-PX-2365-10012-001_R01.PDF | 388,21 KB | 01/04/2025 14:49:36 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 02/05/2025 03:29:31 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00053 | R01 | 3/28/2025 | BNO-MABU-SNEPCO-2025-INC-00130 | 04/02/2025 | BNO/EXT/MABU/00513 | 4/25/2025 | 3 | BNO-MABU-DAE-2025-TN-10038 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10013-001 |  | P&ID - PRODUCTION SYSTEMS- PRODUCTION FLOWLINES & INSTRUMENT - MODIFICATION | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 03/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 11/02/2025 | BNO-MABU-300-PX-2365-10013-001_R01.PDF | 255,68 KB | 01/04/2025 14:51:46 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 02/05/2025 03:29:31 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00053 | R01 | 3/28/2025 | BNO-MABU-SNEPCO-2025-INC-00132 | 04/02/2025 | BNO/EXT/MABU/00513 | 4/25/2025 | 3 | BNO-MABU-DAE-2025-TN-10038 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10017-001 |  | P&ID - UTILITY SYSTEMS WATERFLOOD SYSTEM INJECTION WATER TANK & CHARGE PUMPS-MODIFICATION | PX - PROCESS | A01 | 3 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR COMMENTS - MABU | 25/07/2025 |  | JOSESIMAO.EP,FLAVIAMORAES.FRM,PAULO.MAURICIO,G.JAMES,PAULO.FERNANDES |  | 50 | 08/08/2025 | BNO-MABU-300-PX-2365-10017-001.003 | 2,55 MB | 25/07/2025 09:36:52 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 21/05/2025 04:32:16 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00401 | A01 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00447 | 07/25/2025 | BNO/EXT/MABU/00504 | 4/22/2025 |  | BNO-MABU-DAE-2025-TN-10039 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10018-001 |  | P&ID - UTILITY SYSTEMS WATERFLOOD SYSTEM WATERFLOOD INJECTION PUMP SHT. 1 OF 2-MODIFICATION | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 03/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 11/02/2025 | BNO-MABU-300-PX-2365-10018-001_R01.PDF | 376,58 KB | 01/04/2025 14:50:06 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 02/05/2025 03:29:31 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00053 | R01 | 3/28/2025 | BNO-MABU-SNEPCO-2025-INC-00130 | 04/02/2025 | BNO/EXT/MABU/00513 | 4/25/2025 | 3 | BNO-MABU-DAE-2025-TN-10038 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10019-001 |  | P&ID - UTILITY SYSTEMS WATERFLOOD INJECTION - LAUNCHER/RECEIVERS-MODIFICATION | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 25/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 08/08/2025 | BNO-MABU-300-PX-2365-10019-001.002 | 3,23 MB | 25/07/2025 09:40:47 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 02/05/2025 03:29:31 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00407 | A01 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00447 | 07/25/2025 | BNO/EXT/MABU/00513 | 4/25/2025 |  | BNO-MABU-DAE-2025-TN-10038 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10020-001 |  | P&ID - UTILITY SYSTEMS -WATERFLOOD INJECTION PUMP NO. 1 TURBINE UTILITIES-MODIFICATION | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 03/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 11/02/2025 | BNO-MABU-300-PX-2365-10020-001_R01.PDF | 351,04 KB | 01/04/2025 14:52:21 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 02/05/2025 03:29:31 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00053 | R01 | 3/28/2025 | BNO-MABU-SNEPCO-2025-INC-00130 | 04/02/2025 | BNO/EXT/MABU/00513 | 4/25/2025 | 3 | BNO-MABU-DAE-2025-TN-10038 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10021-001 |  | P&ID - BN WATERFLOOD SYSTEM - WATERFLOOD INJECTION PUMP | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 03/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 11/02/2025 | BNO-MABU-300-PX-2365-10021-001_R01.PDF | 339,24 KB | 01/04/2025 14:52:09 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 02/05/2025 03:29:31 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00053 | R01 | 3/28/2025 | BNO-MABU-SNEPCO-2025-INC-00130 | 04/02/2025 | BNO/EXT/MABU/00513 | 4/25/2025 | 3 | BNO-MABU-DAE-2025-TN-10038 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10022-001 |  | P&ID - BN UTILITY SYSTEMS - WATERFLOOD INJECTION PUMP TURBINE PACKAGE | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 03/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 11/02/2025 | BNO-MABU-300-PX-2365-10022-001_R01.PDF | 338,42 KB | 01/04/2025 14:49:23 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 02/05/2025 03:29:31 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00053 | R01 | 3/28/2025 | BNO-MABU-SNEPCO-2025-INC-00130 | 04/02/2025 | BNO/EXT/MABU/00513 | 4/25/2025 | 3 | BNO-MABU-DAE-2025-TN-10038 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10024-001 |  | P&ID- UTILITY SYSTEMS FUEL GAS DISTRIBUTION-MODIFICATION | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 01/04/2025 |  |  | ISSUED AS CODE 2 - NO COMMENTS | 10 | 11/02/2025 | BNO-MABU-300-PX-2365-10024-001_R01.PDF | 369,42 KB | 01/04/2025 14:52:33 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | [7 empty] | IFA - ISSUED FOR APPROVAL | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00053 | R01 | 3/28/2025 | BNO-MABU-SNEPCO-2025-INC-00130 | 04/02/2025 | BNO/EXT/MABU/00512 | 4/24/2025 | 2 | BNO-MABU-DAE-2025-TN-10039 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10027-001 |  | P&ID- UTILITY SYSTEMS FLOWLINE CORROSION INHIBITOR PUMPS -MODIFICATION | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 03/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 11/02/2025 | BNO-MABU-300-PX-2365-10027-001_R01.PDF | 385,19 KB | 01/04/2025 14:52:03 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 02/05/2025 03:29:31 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00053 | R01 | 3/28/2025 | BNO-MABU-SNEPCO-2025-INC-00130 | 04/02/2025 | BNO/EXT/MABU/00513 | 4/25/2025 | 3 | BNO-MABU-DAE-2025-TN-10038 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10029-001 |  | P&ID - UTILITY SYSTEM HYDRATE INHIBITOR SYSTEM MODIFICATION | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 29/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 12/08/2025 | BNO-MABU-300-PX-2365-10029-001_A01.PID | 4,04 MB | 29/07/2025 08:32:43 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 02/05/2025 03:29:31 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 02/11/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00423 | A01 | 07/29/2025 | BNO/MABU-SNEPCO-2025-INC-00461 | 07/29/2025 | BNO/EXT/MABU/00513 | 4/25/2025 |  | BNO-MABU-DAE-2025-TN-10038 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10030-001 |  | P&ID - BN UTILITY SYSTEMS - CORROSION INHIBITOR SYSTEM PACKAGE - MODIFICATION | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 29/07/2025 |  | FLAVIAMORAES.FRM |  | 85 | 12/08/2025 | BNO-MABU-300-PX-2365-10030-001_A01.PID | 3,33 MB | 29/07/2025 08:36:11 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | [7 empty] | IFA - ISSUED FOR APPROVAL | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00423 | A01 | 07/29/2025 | BNO/MABU-SNEPCO-2025-INC-00461 | 07/29/2025 | BNO/EXT/MABU/00515 | 4/25/2025 |  | BNO-MABU-DAE-2025-TN-10039 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10033-001 |  | P&ID - PRODUCTION SYSTEM- SUBSEA / BLOWDOWN RELIEF HEADER-MODIFICATION | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 01/04/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 10 | 11/02/2025 | BNO-MABU-300-PX-2365-10033-001_R01.PDF | 293,75 KB | 01/04/2025 14:49:30 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 09/05/2025 10:07:58 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00053 | R01 | 3/28/2025 | BNO-MABU-SNEPCO-2025-INC-00130 | 04/02/2025 | BNO/EXT/MABU/00511 | 4/24/2025 | 3 | BNO-MABU-DAE-2025-TN-10039 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10034-001 |  | P&ID - PRODUCTION SYSTEM- COMPRESSION RELIEF HEADER - MODIFICATION | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 01/04/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 10 | 11/02/2025 | BNO-MABU-300-PX-2365-10034-001_R01.PDF | 276,01 KB | 01/04/2025 14:51:52 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 09/05/2025 10:07:59 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00053 | R01 | 3/28/2025 | BNO-MABU-SNEPCO-2025-INC-00130 | 04/02/2025 | BNO/EXT/MABU/00511 | 4/24/2025 | 3 | BNO-MABU-DAE-2025-TN-10039 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10035-001 |  | P&ID - PRODUCTION SYSTEMS OPEN DRAIN SYSTEM | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR COMMENTS - MABU | 23/07/2025 |  | JOSESIMAO.EP,FLAVIAMORAES.FRM,PAULO.MAURICIO,G.JAMES,PAULO.FERNANDES |  | 50 | 06/08/2025 | BNO-MABU-300-PX-2365-10035-001.002 | 4,62 MB | 23/07/2025 09:03:48 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | [7 empty] | IFA - ISSUED FOR APPROVAL | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00397 | A01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00435 | 07/23/2025 | [5 empty] | R | P2
BNO-MABU-300-PX-2365-10037-001 |  | P&ID - BN UTILITY SYSTEMS - WATER HEADER DISTRIBUTION SYSTEM MODIFICATION | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR COMMENTS - MABU | 25/07/2025 |  | JOSESIMAO.EP,FLAVIAMORAES.FRM,PAULO.MAURICIO,G.JAMES,PAULO.FERNANDES |  | 50 | 08/08/2025 | BNO-MABU-300-PX-2365-10037-001.002 | 1,79 MB | 25/07/2025 09:44:01 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | [7 empty] | IFA - ISSUED FOR APPROVAL | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00407 | A01 | 07/25/2025 | BNO-MABU-SNEPCO-2025-INC-00447 | 07/25/2025 | BNO/EXT/MABU/00515 | 4/25/2025 |  | BNO-MABU-DAE-2025-TN-10039 | 05/07/2025 | R | P2
BNO-MABU-300-PX-2365-10039-001 |  | P&ID - DIESEL DAY TANK SYSTEM- MODIFICATION | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 01/04/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 10 | 11/02/2025 | BNO-MABU-300-PX-2365-10039-001_R01.PDF | 301,24 KB | 01/04/2025 14:50:29 |  | 02/04/2025 09:18:06 | R01 | IDC - INTERNAL COMMENTS | 09/05/2025 10:08:00 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 02/11/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00053 | R01 | 3/28/2025 | BNO-MABU-SNEPCO-2025-INC-00130 | 04/02/2025 | BNO/EXT/MABU/00511 | 4/24/2025 | 3 | BNO-MABU-DAE-2025-TN-10038 | 05/07/2025
BNO-MABU-300-PX-2365-10040-001 |  | FIREWATER PUMPS AND NETWORK P&IDS | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 14/03/2025 |  |  |  | 0 | 14/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/14/2025 | 9/15/2025 | 9/25/2025 | [10 empty] | R | P2
BNO-MABU-300-PX-2365-10041-001 |  | P&ID DELUGE DISTRIBUTION | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 14/03/2025 |  |  |  | 0 | 14/07/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 7/14/2025 | 9/15/2025 | 9/25/2025 | [10 empty] | R | P2
BNO-MABU-300-PX-2365-10045-001 |  | DEMOLITION P&ID - PRODUCTION SYSTEMS PRODUCTION MANIFOLD | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 14/07/2025 | 30/07/2025 |  | ISSUED AS CODE 1 - APPROVED | 100 | 28/07/2025 | BNO-MABU-300-PX-2365-10045-001_C01.DWG | 879,06 KB | 14/07/2025 03:23:07 |  | 28/03/2025 12:36:29 | R01 | IFR - ISSUED FOR REVIEW | 25/03/2025 10:13:11 | R01 | 2-NO COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  | 07/07/2025 | 07/28/2025 | BON-DAE-WESTPAQ-2025-TX-00363 | C01 | 07/14/2025 | BNO/MABU-SNEPCO-2025-INC-00401 | 07/14/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025 | INFO | NA
BNO-MABU-300-PX-2365-10046-001 |  | DEMOLITION P&ID - PRODUCTION SYSTEM-SUBSEA WELLSLAUNCHERS / RECEIVERS | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 14/07/2025 | 30/07/2025 |  | ISSUED AS CODE 1 - APPROVED | 100 | 28/07/2025 | BNO-MABU-300-PX-2365-10046-001_C01.DWG | 917,57 KB | 14/07/2025 03:23:43 |  | 28/03/2025 12:36:29 | R01 | IFR - ISSUED FOR REVIEW | 25/03/2025 10:13:13 | R01 | 2-NO COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  | 07/07/2025 | 07/28/2025 | BON-DAE-WESTPAQ-2025-TX-00023 | C01 | 07/14/2025 | BNO/MABU-SNEPCO-2025-INC-00401 | 07/14/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025 | INFO | NA
BNO-MABU-300-PX-2365-10047-001 |  | DEMOLITION P&ID - PRODUCTION SYSTEM -OIL/ OIL HEAT EXCHANGER | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 14/07/2025 | 30/07/2025 |  |  | 100 | 28/07/2025 | BNO-MABU-300-PX-2365-10047-001_C01.DWG | 747,92 KB | 14/07/2025 03:24:32 |  | 28/03/2025 12:36:29 | R01 | IFR - ISSUED FOR REVIEW | 25/03/2025 10:13:14 | R01 | 2-NO COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  | 07/07/2025 | 07/28/2025 | BON-DAE-WESTPAQ-2025-TX-00363 | C01 | 07/14/2025 | BNO/MABU-SNEPCO-2025-INC-00401 | 07/14/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025 | INFO | NA
BNO-MABU-300-PX-2365-10048-001 |  | DEMOLITION P&ID - PRODUCTION SYSTEMS GAS RISER LIFT METERS | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR CONSOLIDATION | 14/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 28/07/2025 | BNO-MABU-300-PX-2365-10048-001_C01.DWG | 1,36 MB | 14/07/2025 03:25:00 |  | 28/03/2025 12:36:29 | R01 | IFR - ISSUED FOR REVIEW | 25/03/2025 10:13:16 | R01 | 2-NO COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  | 07/07/2025 | 07/28/2025 | BON-DAE-WESTPAQ-2025-TX-00363 | C01 | 07/14/2025 | BNO/MABU-SNEPCO-2025-INC-00401 | 07/14/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2365-10050-001 |  | DEMOLITION P&ID - UTILITY SYSTEMS FUEL GAS DISTRIBUTION | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR CONSOLIDATION | 14/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 28/07/2025 | BNO-MABU-300-PX-2365-10050-001_C01.DWG | 1,01 MB | 14/07/2025 03:25:26 |  | 28/03/2025 12:36:29 | R01 | IDC - INTERNAL COMMENTS | 25/03/2025 10:13:17 | R01 | 2-NO COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  | 07/07/2025 | 07/28/2025 | BON-DAE-WESTPAQ-2025-TX-00363 | C01 | 07/14/2025 | BNO/MABU-SNEPCO-2025-INC-00401 | 07/14/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2365-10051-001 |  | DEMOLITION P&ID - UTILITY SYSTEMS - WATERFLOOD SYSTEM INJECTION WATER TANK & CHARGE PUMPS | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR CONSOLIDATION | 14/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 28/07/2025 | BNO-MABU-300-PX-2365-10051-001_C01.DWG | 935,05 KB | 14/07/2025 03:26:12 |  | 28/03/2025 12:17:15 | R01 | IFR - ISSUED FOR REVIEW | 25/03/2025 10:13:18 | R01 | 2-NO COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  | 07/07/2025 | 07/28/2025 | BON-DAE-WESTPAQ-2025-TX-00363 | C01 | 07/14/2025 | BNO/MABU-SNEPCO-2025-INC-00401 | 07/14/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2365-10052-001 |  | DEMOLITION P&ID - UTILITY SYSTEMS - WATERFLOOD INJECTION LAUNCHER/RECEIVERS | PX - PROCESS | A01 | 3 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 23/06/2025 | 11/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 07/07/2025 | BNO-MABU-300-PX-2365-10052-001_A01.DWG | 289,63 KB | 23/06/2025 01:05:40 |  | 28/03/2025 12:36:29 | R01 | IFR - ISSUED FOR REVIEW | 25/03/2025 10:13:20 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  | 07/07/2025 |  | BON-DAE-WESTPAQ-2025-TX-00239 | A01 | 06/23/2025 | BNO/MABU-SNEPCO-2025-INC-00318 | 06/23/2025 | BNO/EXT/MABU/00683 | 07/14/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10090 | 07/10/2025 | INFO | NA
BNO-MABU-300-PX-2365-10053-001 |  | DEMOLITION P&ID - UTILITY SYSTEMS - WATERFLOOD INJECTION PUMP NO. 1 TURBINE UTILITIES | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 23/06/2025 | 21/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 07/07/2025 | BNO-MABU-300-PX-2365-10053-001_A01.DWG | 404,01 KB | 23/06/2025 01:07:14 |  | 28/03/2025 12:36:29 | R01 | IFR - ISSUED FOR REVIEW | 25/03/2025 10:13:22 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL |  |  |  | BON-DAE-WESTPAQ-2025-TX-00239 | A01 | 06/23/2025 | BNO/MABU-SNEPCO-2025-INC-00318 | 06/23/2025 | BNO_EXT_MABU_00670 OVERDUE | 07/10/2025 | CODE 2 - NO COMMENTS |  |  | INFO | NA
BNO-MABU-300-PX-2365-10054-001 |  | DEMOLITION P&ID - UTILITY SYSTEMS - WATERFLOOD SYSTEM WATERFLOOD INJECTION PUMP SHT. 1 OF 2 | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR CONSOLIDATION | 16/07/2025 |  | FLAVIAMORAES.FRM |  | 100 | 30/07/2025 | BNO-MABU-300-PX-2365-10054-001_C01.DWG | 769,55 KB | 16/07/2025 08:43:29 |  | 28/03/2025 12:36:29 | R01 | IFR - ISSUED FOR REVIEW | 25/03/2025 10:13:23 | R01 | 2-NO COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  |  | 07/30/2025 | BON-DAE-WESTPAQ-2025-TX-00371 | C01 | 07/16/2025 | BNO-MABU-SNEPCO-2025-INC-00409 | 07/16/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2365-10055-001 |  | DEMOLITION P&ID - UTILITY SYSTEMS FLOWLINE CORROSION INHIBITOR PUMPS | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR CONSOLIDATION | 14/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 28/07/2025 | BNO-MABU-300-PX-2365-10055-001_C01.DWG | 1,08 MB | 14/07/2025 03:26:40 |  | 28/03/2025 12:36:29 | R01 | IFR - ISSUED FOR REVIEW | 25/03/2025 10:13:24 | R01 | 2-NO COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  |  | 07/28/2025 | BON-DAE-WESTPAQ-2025-TX-00363 | C01 | 07/14/2025 | BNO/MABU-SNEPCO-2025-INC-00401 | 07/14/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2365-10056-001 |  | DEMOLITION P&ID - UTILITY SYSTEMS HYDRATE INHIBITOR SYSTEM | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR CONSOLIDATION | 16/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 30/07/2025 | BNO-MABU-300-PX-2365-10056-001_C01.DWG | 937,6 KB | 16/07/2025 08:45:53 |  | 28/03/2025 12:36:29 | R01 | IFR - ISSUED FOR REVIEW | 25/03/2025 10:13:26 | R01 | 2-NO COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  | 07/07/2025 | 07/30/2025 | BON-DAE-WESTPAQ-2025-TX-00371 | C01 | 07/16/2025 | BNO/MABU-SNEPCO-2025-INC-00371 | 07/16/2025 | BNO/EXT/MABU/00672 | 07/11/2025 | CODE 2 - NO COMMENTS |  |  | INFO | NA
BNO-MABU-300-PX-2365-10057-001 |  | DEMOLITION P&ID - PRODUCTION SYSTEM - SUBSEA/BLOWDOWN RELIEF HEADER | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR CONSOLIDATION | 16/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 30/07/2025 | BNO-MABU-300-PX-2365-10057-001_C01.DWG | 651,73 KB | 16/07/2025 08:49:54 |  | 28/03/2025 12:36:29 | R01 | IFR - ISSUED FOR REVIEW | 25/03/2025 10:13:27 | R01 | 2-NO COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  | 07/07/2025 | 07/30/2025 | BON-DAE-WESTPAQ-2025-TX-00371 | C01 | 07/16/2025 | BNO/MABU-SNEPCO-2025-INC-00409 | 07/16/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2365-10058-001 |  | DEMOLITION P&ID - PRODUCTION SYSTEM - COMPRESSION RELIEF HEADER | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR CONSOLIDATION | 16/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 30/07/2025 | BNO-MABU-300-PX-2365-10058-001_C01.DWG | 559,79 KB | 16/07/2025 08:50:45 |  | 28/03/2025 12:36:29 | R01 | IFR - ISSUED FOR REVIEW | 25/03/2025 10:13:29 | R01 | 2-NO COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  | 07/07/2025 | 07/30/2025 | BON-DAE-WESTPAQ-2025-TX-00371 | C01 | 07/16/2025 | BNO/MABU-SNEPCO-2025-INC-00409 | 07/16/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2365-10059-001 |  | DEMOLITION P&ID - UTILITY SYSTEMS - WATER HEADER DISTRIBUTION SYSTEM | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR CONSOLIDATION | 16/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 30/07/2025 | BNO-MABU-300-PX-2365-10059-001_C01.DWG | 517,61 KB | 16/07/2025 08:53:25 |  | 28/03/2025 12:36:29 | R01 | IFR - ISSUED FOR REVIEW | 25/03/2025 10:13:30 | R01 | 2-NO COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  | 07/07/2025 | 07/30/2025 | BON-DAE-WESTPAQ-2025-TX-00371 | C01 | 07/16/2025 | BNO/MABU-SNEPCO-2025-INC-00409 | 07/16/2025 | BNO/EXT/MABU/00672 | 07/11/2025 | CODE 2 - NO COMMENTS |  |  | INFO | NA
BNO-MABU-300-PX-2365-10060-001 |  | DEMOLITION P&ID - DIESEL DAY TANK SYSTEM | PX - PROCESS | R01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 03/05/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 14/02/2025 | BNO-MABU-300-PX-2365-10060-001_R01.DWG | 319,41 KB | 27/03/2025 06:32:09 |  | 28/03/2025 12:36:29 | R01 | IDC - INTERNAL COMMENTS | 02/04/2025 11:12:01 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 2/14/2025 | 07/01/2025 | 7/22/2025 | BON-DAE-WESTPAQ-2025-TX-00023 | R01 | 3/14/2025 | BNO-MABU-SNEPCO-2025-INC-00107 | 3/17/2025 | BNO/EXT/MABU/00475 | 3/24/2025 | 3 | BNO-MABU-DAE-2025-TN-10025 | 04/09/2025
BNO-MABU-300-PX-2365-10061-001 |  | TIE-IN P&ID PRODUCTION SYSTEMS PRODUCTION MANIFOLD TP 01-TP 06 | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A0 | 0 | ISSUED | 14/07/2025 | 30/07/2025 |  |  | 100 | 28/07/2025 | BNO-MABU-300-PX-2365-10061-001_R01.DWG | 532,66 KB | 14/07/2025 03:32:08 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00364 | R01 | 07/13/2025 | BNO/MABU-SNEPCO-2025-INC-00402 | 07/14/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025
BNO-MABU-300-PX-2365-10062-001 |  | TIE-IN P&D PRODUCTION SYSTEMS GAS RISER LIFT METERS TP 07 & TP 08. | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A0 | 0 | ISSUED | 14/07/2025 | 30/07/2025 |  |  | 100 | 28/07/2025 | BNO-MABU-300-PX-2365-10062-001_R01.DWG | 832,91 KB | 14/07/2025 03:44:11 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00364 | R01 | 07/13/2025 | BNO/MABU-SNEPCO-2025-INC-00402 | 07/14/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025
BNO-MABU-300-PX-2365-10063-001 |  | TIE-IN P&ID UTILITY SYSTEMS FLOWLINE CORROSION INHIBITOR PUMPS TP 025, 026 & 056. | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A0 | 0 | ISSUED | 14/07/2025 | 30/07/2025 |  |  | 100 | 28/07/2025 | BNO-MABU-300-PX-2365-10063-001_R01.DWG | 617,13 KB | 14/07/2025 03:45:34 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00364 | R01 | 07/13/2025 | BNO/MABU-SNEPCO-2025-INC-00402 | 07/14/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025
BNO-MABU-300-PX-2365-10064-001 |  | TIE-IN P&ID UTILITY SYSTEMS WATERFLOOD SYSTEM INJECTION WATER TANK & CHARGE PUMPS TP 028A. | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A0 | 0 | ISSUED | 14/07/2025 | 30/07/2025 |  |  | 100 | 28/07/2025 | BNO-MABU-300-PX-2365-10064-001_R01.DWG | 577,27 KB | 14/07/2025 03:46:23 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00364 | R01 | 07/13/2025 | BNO/MABU-SNEPCO-2025-INC-00402 | 07/14/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025
BNO-MABU-300-PX-2365-10065-001 |  | TIE-IN P&ID UTILITY SYSTEMS WEATERFLOOD INJECTION PUMP NO. 1 TURBINE UTILITIES TP 049 & 050. | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A0 | 0 | ISSUED | 14/07/2025 | 30/07/2025 |  |  | 100 | 28/07/2025 | BNO-MABU-300-PX-2365-10065-001_R01.DWG | 454,67 KB | 14/07/2025 03:46:57 | [11 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00364 | R01 | 07/13/2025 | BNO/MABU-SNEPCO-2025-INC-00402 | 07/14/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025
BNO-MABU-300-PX-2366-10001-001 |  | FLOWSHEET LEGEND SHT 1 | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 06/07/2025 | 24/07/2025 |  | ISSUED AS CODE 1 - APPROVED | 100 | 18/07/2025 | BNO-MABU-300-PX-2366-10001-001_A01.DWG | 930,6 KB | 06/07/2025 13:44:01 |  |  |  |  | 04/04/2025 13:43:21 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 3/11/2025 | 7/18/2025 |  | BON-DAE-WESTPAQ-2025-TX-00306 | A01 | 7/6/2025 | BNO-MABU-SNEPCO-2025-INC-00375 | 7/7/2025 | NOT RECEIVED | 7/7/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10098 | 07/24/2025 | INFO | NA
BNO-MABU-300-PX-2366-10002-001 |  | FLOWSHEET LEGEND SHT 2 | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 06/07/2025 | 24/07/2025 |  | ISSUED AS CODE 1 - APPROVED | 100 | 18/07/2025 | BNO-MABU-300-PX-2366-10002-001_A01.DWG | 842,11 KB | 06/07/2025 13:44:19 |  |  |  |  | 04/04/2025 13:45:57 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 3/11/2025 | 7/18/2025 |  | BON-DAE-WESTPAQ-2025-TX-00306 | A01 | 7/6/2025 | BNO-MABU-SNEPCO-2025-INC-00375 | 7/7/2025 | NOT RECEIVED | 7/21/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10098 | 07/24/2025 | INFO | NA
BNO-MABU-300-PX-2366-10003-001 |  | FLOWSHEET LEGEND SHT 3 | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 06/07/2025 | 24/07/2025 |  |  | 100 | 18/07/2025 | BNO-MABU-300-PX-2366-10003-001_A01.DWG | 641,15 KB | 06/07/2025 13:44:37 |  |  |  |  | 04/04/2025 13:45:59 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 3/11/2025 | 7/18/2025 | 7/11/2025 | BON-DAE-WESTPAQ-2025-TX-00306 | A01 | 7/18/2025 | BNO-MABU-SNEPCO-2025-INC-00375 | 7/7/2025 | NOT RECEIVED | 7/21/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10097 | 07/24/2025 | INFO | NA
BNO-MABU-300-PX-2366-10004-001 |  | FLOWSHEET LEGEND SHT 4 | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 06/07/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 18/07/2025 | BNO-MABU-300-PX-2366-10004-001_A01.DWG | 684,02 KB | 06/07/2025 13:44:55 |  |  |  |  | 04/04/2025 13:46:00 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 3/11/2025 | 7/18/2025 | 7/11/2025 | BON-DAE-WESTPAQ-2025-TX-00306 | A01 | 7/18/2025 | BNO-MABU-SNEPCO-2025-INC-00375 | 7/7/2025 | NOT RECEIVED | 7/21/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10097 | 07/24/2025 | INFO | NA
BNO-MABU-300-PX-2366-10005-001 |  | FLOWSHEET LEGEND SHT 5 | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 06/07/2025 | 24/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 18/07/2025 | BNO-MABU-300-PX-2366-10005-001_A01.DWG | 694,75 KB | 06/07/2025 13:45:09 |  |  |  |  | 04/04/2025 13:46:02 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 3/11/2025 | 7/18/2025 | 7/11/2025 | BON-DAE-WESTPAQ-2025-TX-00306 | A01 | 7/18/2025 | BNO-MABU-SNEPCO-2025-INC-00375 | 7/7/2025 | NOT RECEIVED | 7/21/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10097 | 07/24/2025 | INFO | NA
BNO-MABU-300-PX-2366-10006-001 |  | PFS - BONGA NORTH WELLS FLOWLINES LAUNCHER RECEIVERS | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 29/06/2025 | 27/07/2025 |  | ISSUED AS CODE 1 - APPROVED | 100 | 11/07/2025 | BNO-MABU-300-PX-2366-10006-001_A01.DWG | 315,89 KB | 27/06/2025 09:54:09 |  |  |  |  | 04/04/2025 13:43:13 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 2/21/2025 | 7/11/2025 |  | BON-DAE-WESTPAQ-2025-TX-00260 | A01 | 6/27/2025 | BNO-MABU-SNEPCO-2025-INC-00352 | 6/30/2025 | NOT RECEIVED. LATER: BNO/EXT/MABU/00726 (OVERDUE) | 07/28/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10099 | 07/27/2025 | INFO | NA
BNO-MABU-300-PX-2366-10007-001 |  | PFS - WELL/FLOWLINES/PRODUCTION /RECEIVER TEST -MODIFICATION | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 29/06/2025 | 27/07/2025 |  |  | 100 | 11/07/2025 | BNO-MABU-300-PX-2366-10007-001_A01.DWG | 314,45 KB | 29/06/2025 14:11:33 |  |  |  |  | 04/04/2025 13:43:11 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 2/21/2025 | 7/11/2025 |  | BON-DAE-WESTPAQ-2025-TX-00260 | A01 | 6/27/2025 | BNO-MABU-SNEPCO-2025-INC-00352 | 6/30/2025 | NOT RECEIVED | 7/7/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10099 | 07/28/2025 | INFO | NA
BNO-MABU-300-PX-2366-10008-001 |  | PFS - PRODUCTION MANIFOLD_ TEST SEPARATOR - MODIFICATION | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | DCC_IFR RECEIVED FROM ASSAI | 29/06/2025 |  | DCC_WPQ |  | 50 | 11/07/2025 | BNO-MABU-300-PX-2366-10008-001_A01.DWG | 297,9 KB | 29/06/2025 15:05:49 |  |  |  |  | 04/04/2025 13:46:04 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 2/21/2025 | 7/11/2025 |  | BON-DAE-WESTPAQ-2025-TX-00260 | A01 | 6/27/2025 | BNO-MABU-SNEPCO-2025-INC-00352 | 6/30/2025 | NOT RECEIVED | 7/7/2025 | OVERDUE |  |  | INFO | NA
BNO-MABU-300-PX-2366-10009-001 |  | PFS - HEATING AND TREATING OIL - MODIFICATION | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 29/06/2025 | 27/07/2025 |  |  | 100 | 11/07/2025 | BNO-MABU-300-PX-2366-10009-001_A01.DWG | 321,54 KB | 29/06/2025 15:10:24 |  |  |  |  | 04/04/2025 13:45:53 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 2/21/2025 | 7/11/2025 |  | BON-DAE-WESTPAQ-2025-TX-00260 | A01 | 6/27/2025 | BNO-MABU-SNEPCO-2025-INC-00352 | 6/30/2025 | NOT RECEIVED | 7/7/2025 | OVERDUE |  |  | INFO | NA
BNO-MABU-300-PX-2366-10010-001 |  | PFS - GAS SALES AND RISER LIFT - MODIFICATION | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 29/06/2025 | 27/07/2025 |  |  | 100 | 11/07/2025 | BNO-MABU-300-PX-2366-10010-001_A01.DWG | 605,5 KB | 29/06/2025 15:15:34 |  | 09/05/2025 07:06:21 | R02 | IFA - ISSUED FOR APPROVAL | 22/05/2025 06:05:29 | R02 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 2/21/2025 | 7/11/2025 |  | BON-DAE-WESTPAQ-2025-TX-00260 | A01 | 6/27/2025 | BNO-MABU-SNEPCO-2025-INC-00352 | 6/30/2025 | NOT RECEIVED | 7/7/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10099 | 07/27/2025 | INFO | NA
BNO-MABU-300-PX-2366-10011-001 |  | PFS - WATERFLOOD SRS AND INJECTION - MODIFICATION | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 29/06/2025 | 30/07/2025 |  |  | 100 | 11/07/2025 | BNO-MABU-300-PX-2366-10011-001_A01.DWG | 404,46 KB | 29/06/2025 15:20:55 |  |  |  |  | 04/04/2025 13:45:54 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 2/21/2025 | 7/11/2025 |  | BON-DAE-WESTPAQ-2025-TX-00260 | A01 | 6/28/2025 | BNO-MABU-SNEPCO-2025-INC-00352 | 6/30/2025 | NOT RECEIVED | 7/7/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025 | INFO | NA
BNO-MABU-300-PX-2366-10012-001 |  | PFS - FUEL GAS-MODIFICATION | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 29/06/2025 | 30/07/2025 |  |  | 100 | 11/07/2025 | BNO-MABU-300-PX-2366-10012-001_A01.PDF | 772,6 KB | 29/06/2025 15:26:40 |  |  |  |  | 04/04/2025 13:43:15 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 2/21/2025 | 7/11/2025 |  | BON-DAE-WESTPAQ-2025-TX-00260 | A01 | 6/27/2025 | BNO-MABU-SNEPCO-2025-INC-00352 | 6/30/2025 | NOT RECEIVED | 7/7/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025 | INFO | NA
BNO-MABU-300-PX-2366-10013-001 |  | PFS - BONGA NORTH WATERFLOOD INJECTION PUMP | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 29/06/2025 | 30/07/2025 |  |  | 100 | 11/07/2025 | BNO-MABU-300-PX-2366-10013-001_A01.DWG | 284,87 KB | 29/06/2025 15:34:42 |  |  |  |  | 04/04/2025 13:43:16 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 2/21/2025 | 7/11/2025 |  | BON-DAE-WESTPAQ-2025-TX-00260 | A01 | 6/27/2025 | BNO-MABU-SNEPCO-2025-INC-00352 | 6/30/2025 | NOT RECEIVED | 7/7/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10105 | 07/30/2025 | INFO | NA
BNO-MABU-300-PX-2366-10014-001 |  | PFS - CHEMICAL INJECTION - MODIFICATION | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 29/06/2025 | 27/07/2025 |  |  | 100 | 11/07/2025 | BNO-MABU-300-PX-2366-10014-001_A01.DWG | 405,9 KB | 29/06/2025 15:39:51 |  |  |  |  | 04/04/2025 13:43:18 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 2/21/2025 | 7/11/2025 |  | BON-DAE-WESTPAQ-2025-TX-00260 | A01 | 6/27/2025 | BNO-MABU-SNEPCO-2025-INC-00352 | 6/30/2025 | NOT RECEIVED | 7/7/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10099 | 07/28/2025 | INFO | NA
BNO-MABU-300-PX-2366-10015-001 |  | PFS - BONGA NORTH CHEMICAL INJECTION: CORROSION INHIBITOR SYSTEM | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 29/06/2025 | 27/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 100 | 11/07/2025 | BNO-MABU-300-PX-2366-10015-001_A01.DWG | 276,92 KB | 29/06/2025 15:45:16 |  |  |  |  | 04/04/2025 13:43:20 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 2/21/2025 | 7/11/2025 |  | BON-DAE-WESTPAQ-2025-TX-00260 | A01 | 6/27/2025 | BNO-MABU-SNEPCO-2025-INC-00352 | 6/30/2025 | NOT RECEIVED | 7/7/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10099 | 07/27/2025 | INFO | NA
BNO-MABU-300-PX-2366-10016-001 |  | PFS - VENTS AND FLARE BOOM - MODIFICATION | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 29/06/2025 | 27/07/2025 |  | ISSUED AS CODE 1 - APPROVED | 100 | 11/07/2025 | BNO-MABU-300-PX-2366-10016-001_A01.DWG | 354,25 KB | 29/06/2025 15:44:51 |  |  |  |  | 04/04/2025 13:45:56 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 2/21/2025 | 7/11/2025 |  | BON-DAE-WESTPAQ-2025-TX-00260 | A01 | 6/27/2025 | BNO-MABU-SNEPCO-2025-INC-00352 | 6/30/2025 | NOT RECEIVED | 7/7/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10099 | 07/27/2025 | INFO | NA
BNO-MABU-300-PX-2366-10017-001 |  | PFS - DIESEL SUPPLY SYSTEM- MODIFICATION | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | NÃO SE APLICA | 27/03/2025 |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 10 | 21/02/2025 | BNO-MABU-300-PX-2366-10017-001_R01.DWG | 321,02 KB | 27/03/2025 05:58:53 |  |  |  |  | 21/05/2025 06:04:00 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 2/21/2025 | 7/29/2025 | 8/19/2025 | BON-DAE-WESTPAQ-2025-TX-00022 | R01 | 3/14/2025 | BNO-MABU-SNEPCO-2025-INC-00184 | 05/07/2025 |  |  |  | BNO-MABU-DAE-2025-TN-10026 | 04/09/2025
BNO-MABU-300-PX-2366-10018-001 |  | PFS - MISCELLANEOUS SYSTEMS - MODIFICATION | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ISSUED | 29/06/2025 | 27/07/2025 |  | ISSUED AS CODE 1 - APPROVED | 100 | 11/07/2025 | BNO-MABU-300-PX-2366-10018-001_A01.DWG | 271,15 KB | 29/06/2025 15:44:26 |  |  |  |  | 21/05/2025 05:36:43 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 2/21/2025 | 7/11/2025 |  | BON-DAE-WESTPAQ-2025-TX-00260 | A01 | 6/27/2025 | BNO-MABU-SNEPCO-2025-INC-00352 | 6/30/2025 | NOT RECEIVED | 7/7/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10099 | 07/27/2025 | INFO | NA
BNO-MABU-300-PX-2368-10001-001 |  | PSFS - BONGA NORTH WELLS FLOWLINES LAUNCHER RECEIVERS | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | DCC_IFR RECEIVED FROM ASSAI | 23/07/2025 |  | F.NEVES |  | 100 | 06/08/2025 | BNO-MABU-300-PX-2368-10001-001_C01.DWG | 751 KB | 23/07/2025 06:38:35 |  | 28/03/2025 12:09:49 | R01 | IFR - ISSUED FOR REVIEW | 08/04/2025 11:15:02 | R01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED | 05/12/2025 | 07/14/2025 |  | BON-DAE-WESTPAQ-2025-TX-00399 | C01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00437 | 07/23/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2368-10002-001 |  | PSFS-WELL/FLOWLINES/PRODUCTION /RECEIVER TEST-MODIFICATION | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | DCC_IFR RECEIVED FROM ASSAI | 23/07/2025 |  | F.NEVES |  | 100 | 06/08/2025 | BNO-MABU-300-PX-2368-10002-001_C01.DWG | 741,61 KB | 23/07/2025 06:38:55 |  | 28/03/2025 12:09:49 | R01 | IFR - ISSUED FOR REVIEW | 08/04/2025 11:15:04 | R01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED | 03/10/2025 | 07/14/2025 |  | BON-DAE-WESTPAQ-2025-TX-00399 | C01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00437 | 07/23/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2368-10003-001 |  | PSFS - PRODUCTION MANIFOLD_ TEST SEPARATOR - MODIFICATION | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | ENG_IFR LEAD ASSIGNMENT | 23/07/2025 |  | ANDREA.SANTOS |  | 100 | 06/08/2025 | BNO-MABU-300-PX-2368-10003-001_C01.DWG | 831,93 KB | 23/07/2025 06:41:27 |  | 28/03/2025 12:09:49 | R01 | IFR - ISSUED FOR REVIEW | 08/04/2025 11:15:06 | R01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED | 03/10/2025 | 07/14/2025 |  | BON-DAE-WESTPAQ-2025-TX-00399 | C01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00437 | 07/23/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2368-10004-001 |  | PSFS - HEATING & TREATING OIL | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | DCC_IFR RECEIVED FROM ASSAI | 23/07/2025 |  | F.NEVES |  | 100 | 06/08/2025 | BNO-MABU-300-PX-2368-10004-001_C01.DWG | 799,97 KB | 23/07/2025 06:41:45 |  | 28/03/2025 12:09:49 | R01 | IFR - ISSUED FOR REVIEW | 08/04/2025 11:15:10 | R01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED | 03/10/2025 | 07/14/2025 |  | BON-DAE-WESTPAQ-2025-TX-00399 | C01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00437 | 07/23/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2368-10005-001 |  | PSFS - GAS SALES -RISER LIFT | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | DCC_IFR RECEIVED FROM ASSAI | 23/07/2025 |  | F.NEVES |  | 100 | 06/08/2025 | BNO-MABU-300-PX-2368-10005-001_C01.DWG | 810,02 KB | 23/07/2025 06:42:03 |  | 28/03/2025 12:09:49 | R01 | IFR - ISSUED FOR REVIEW | 08/04/2025 11:15:12 | R01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED | 03/10/2025 | 07/14/2025 |  | BON-DAE-WESTPAQ-2025-TX-00399 | C01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00437 | 07/23/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2368-10006-001 |  | PSFS - WATERFLOOD SRS AND INJECTION | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | DCC_IFR RECEIVED FROM ASSAI | 23/07/2025 |  | F.NEVES |  | 100 | 06/08/2025 | BNO-MABU-300-PX-2368-10006-001_C01.DWG | 1,15 MB | 23/07/2025 06:42:32 |  | 28/03/2025 12:09:49 | R01 | IFR - ISSUED FOR REVIEW | 08/04/2025 11:15:18 | R01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED | 03/10/2025 | 07/14/2025 |  | BON-DAE-WESTPAQ-2025-TX-00399 | C01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00437 | 07/23/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2368-10007-001 |  | PSFS - FUEL GAS | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | DCC_IFR RECEIVED FROM ASSAI | 23/07/2025 |  | F.NEVES |  | 100 | 06/08/2025 | BNO-MABU-300-PX-2368-10007-001_C01.DWG | 815,41 KB | 23/07/2025 06:42:48 |  | 28/03/2025 12:09:49 | R01 | IFR - ISSUED FOR REVIEW | 08/04/2025 11:15:16 | R01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED | 03/10/2025 | 07/14/2025 |  | BON-DAE-WESTPAQ-2025-TX-00437 | C01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00399 | 07/23/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2368-10008-001 |  | PSFS - BONGA NORTH WATERFLOOD INJECTION PUMP | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | DCC_IFR RECEIVED FROM ASSAI | 23/07/2025 |  | F.NEVES |  | 100 | 06/08/2025 | BNO-MABU-300-PX-2368-10008-001_C01.DWG | 849,21 KB | 23/07/2025 06:43:13 |  | 28/03/2025 12:09:49 | R01 | IFR - ISSUED FOR REVIEW | 08/04/2025 11:15:08 | R01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED | 03/10/2025 | 07/14/2025 |  | BON-DAE-WESTPAQ-2025-TX-00399 | C01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00437 | 07/23/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2368-10009-001 |  | PSFS - CHEMICAL INJECTION | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | DCC_IFR RECEIVED FROM ASSAI | 23/07/2025 |  | F.NEVES |  | 100 | 06/08/2025 | BNO-MABU-300-PX-2368-10009-001_C01.DWG | 1,25 MB | 23/07/2025 06:43:49 |  | 28/03/2025 12:09:49 | R01 | IFR - ISSUED FOR REVIEW | 08/04/2025 11:15:22 | R01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED | 03/10/2025 | 07/14/2025 |  | BON-DAE-WESTPAQ-2025-TX-00437 | C01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00399 | 07/23/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2368-10010-001 |  | PSFS - BONGA NORTH CHEMICAL INJECTION: CORROSION INHIBITOR SYSTEM | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | DCC_IFR RECEIVED FROM ASSAI | 23/07/2025 |  | F.NEVES |  | 100 | 06/08/2025 | BNO-MABU-300-PX-2368-10010-001_C01.DWG | 558,2 KB | 23/07/2025 06:44:16 |  | 28/03/2025 12:09:49 | R01 | IFR - ISSUED FOR REVIEW | 08/04/2025 11:15:20 | R01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED | 03/10/2025 | 07/14/2025 |  | BON-DAE-WESTPAQ-2025-TX-00399 | C01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00437 | 07/23/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2368-10011-001 |  | PSFS - VENTS AND FLARE BOOM - MODIFICATION | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | DCC_IFR RECEIVED FROM ASSAI | 23/07/2025 |  | F.NEVES |  | 100 | 06/08/2025 | BNO-MABU-300-PX-2368-10011-001_C01.DWG | 796,29 KB | 23/07/2025 06:44:34 |  | 28/03/2025 12:09:49 | R01 | IFR - ISSUED FOR REVIEW | 08/04/2025 11:15:14 | R01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED | 03/10/2025 | 07/14/2025 |  | BON-DAE-WESTPAQ-2025-TX-00399 | C01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00437 | 07/23/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2368-10012-001 |  | PSFS - MISCELLANEOUS SYSTEMS | PX - PROCESS | C01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A3 | 0 | DCC_IFR RECEIVED FROM ASSAI | 23/07/2025 |  | F.NEVES |  | 100 | 06/08/2025 | BNO-MABU-300-PX-2368-10012-001_C01.DWG | 709,83 KB | 23/07/2025 06:44:52 |  | 28/03/2025 12:09:49 | R01 | IFR - ISSUED FOR REVIEW | 08/05/2025 06:18:42 | R01 | 2-NO COMMENTS | 01/01/1900 |  |  |  | AFC/AFU - APPROVED | 03/10/2025 | 07/14/2025 |  | BON-DAE-WESTPAQ-2025-TX-00399 | C01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00437 | 07/23/2025 | [5 empty] | INFO | NA
BNO-MABU-300-PX-2908-10001 |  | RELIEF VALVES CALCULATION NOTES | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR COMMENTS - MABU | 03/07/2025 |  | FLAVIAMORAES.FRM |  | 50 | 16/07/2025 | BNO-MABU-300-PX-2908-10001_A01.DOCX | 1,86 MB | 03/07/2025 14:48:51 | [11 empty] | IFA - ISSUED FOR APPROVAL |  | 07/16/2025 |  | BON-DAE-WESTPAQ-2025-TX-00303 | A01 | 07/03/2025 | BNO-MABU-SNEPCO-2025-INC-00370 | 07/03/2025 | BNO/EXT/MABU/00707 | 07/24/2025 | OVERDUE |  |  | R | P2
BNO-MABU-300-PX-3363-10001 |  | PROCESS SAFEGUARDING MEMORANDUM | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | NÃO SE APLICA |  |  |  |  | 50 | 23/07/2025 | BNO-MABU-300-PX-3363-10001_A01.PDF | 3,99 MB | 09/07/2025 06:45:32 |  | 28/05/2025 07:36:01 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFA - ISSUED FOR APPROVAL | 06/11/2025 | 07/23/2025 |  | BON-DAE-WESTPAQ-2025-TX-00327 | A01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00382 | 07/09/2025 | BNO/EXT/MABU/00652 | 07/03/2025 | OVERDUE | BNO-MABU-DAE-2025-TN-10102 | 07/28/2025 | R | P2
BNO-MABU-300-PX-4322-10001 |  | PROCESS LINE LIST | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ISSUED | 16/05/2025 | 07/07/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 22/04/2025 | BNO-MABU-300-PX-4322-10001_R01.XLSM | 225,88 KB | 16/05/2025 02:27:22 |  | 16/05/2025 08:58:53 | R01 | IFR - ISSUED FOR REVIEW | 01/07/2025 05:37:36 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/22/2025 | 7/16/2025 | 7/28/2025 | BON-DAE-WESTPAQ-2025-TX-00109 | R01 | 5/15/2025 | BNO-MABU-SNEPCO-2025-INC-00204 | 5/16/2025 | BNO_EXT_MABU_00648 | 07/01/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10087 | 07/07/2025 | INFO | NA
BNO-MABU-300-PX-5517-10001 |  | ISOLATION PHILOSOPHY | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR COMMENTS - MABU | 19/07/2025 |  | JOSESIMAO.EP |  | 50 | 01/08/2025 | BNO-MABU-300-PX-5517-10001_A01.DOCX | 860,52 KB | 19/07/2025 03:55:04 |  | 29/04/2025 05:13:46 | R01 | IFR - ISSUED FOR REVIEW | 26/05/2025 09:46:04 | R01 | 2-NO COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 04/10/2025 | 6/27/2025 | 07/09/2025 | BON-DAE-WESTPAQ-2025-TX-00382 | A01 | 07/19/2025 | BNO-MABU-SNEPCO-2025-INC-00167 | 07/19/2025 | [5 empty] | R | P2
BNO-MABU-300-PX-5527-10001 |  | RELIEF & BLOW DOWN PHILOSOPHY | PX - PROCESS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ENG_IFR COMMENTS - MABU | 10/07/2025 |  | JOSESIMAO.EP |  | 50 | 23/07/2025 | BNO-MABU-300-PX-5527-10001_A01.DOCX | 814,25 KB | 10/07/2025 06:42:50 |  | 27/05/2025 10:37:52 | R01 | IFR - ISSUED FOR REVIEW | 01/07/2025 05:37:38 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 06/06/2025 | 07/23/2025 |  | BON-DAE-WESTPAQ-2025-TX-00338 | A01 | 07/09/2025 | BNO-MABU-SNEPCO-2025-INC-00386 | 07/23/2025 | [5 empty] | R | P2
BNO-MABU-300-PX-5527-10002 |  | DRAINAGE & VENTING PHILOSOPHY | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ISSUED | 29/05/2025 | 23/06/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 12/06/2025 | BNO-MABU-300-PX-5527-10002_R01.DOCX | 807,59 KB | 29/05/2025 10:15:06 |  | 29/05/2025 16:10:31 | R01 | IFR - ISSUED FOR REVIEW | 01/07/2025 05:37:40 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00158 | R01 | 05/29/2025 | BNO-MABU-SNEPCO-2025-INC-00244 | 5/29/2025 | BNO_EXT_MABU_00648 | 07/01/2025 | CODE 3 - MINOR COMMENTS | BNO-MABU-DAE-2025-TN-10080 | 06/23/2025 | R | P2
BNO-MABU-300-PX-7180-10001 |  | PROCESS AND MECHANICAL ISOLATION REVIEW REPORT | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 20/05/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 5/20/2025 | 07/01/2025 | 07/11/2025 | [10 empty] | R | P1
BNO-MABU-300-PX-7753-10002 |  | TERMS OF REFERENCE FOR PROCESS AND MECHANICAL ISOLATION REVIEW | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A4 | 0 | ISSUED | 21/05/2025 | 26/05/2025 |  | ISSUED AS CODE 3 - MINOR COMMENTS | 50 | 23/04/2025 | BNO-MABU-300-PX-7753-10002_R01.DOCX | 841,85 KB | 29/04/2025 04:48:34 |  | 29/04/2025 05:13:46 | R01 | IFR - ISSUED FOR REVIEW | 21/05/2025 05:36:44 | R01 | 2-NO COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | 4/23/2025 | 06/04/2025 | 6/16/2025 | BON-DAE-WESTPAQ-2025-TX-00082 | R01 | 4/28/2025 | BNO-MABU-SNEPCO-2025-INC-00167 | 4/29/2025 | OVERDUE |  |  |  |  | INFO | NA
BNO-MABU-300-PX-8502-10001 |  | TQ FOR GAS LIFT HEATER BYPASS | PX - PROCESS | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A4 | 0 | NÃO SE APLICA | 07/04/2025 |  |  |  | 0 | 28/03/2025 | BNO-MABU-300-PX-8502-10001_A01.DOCX | 1,51 MB | 28/03/2025 02:56:27 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BNO-DAE-WESTPAQ-2025-TX-00045 | IFI A01 | 03/28/2025 | N/A |  |  |  |  | BNO-MABU-DAE-2025-TN-10089 | 07/09/2025
BNO-MABU-300-PX-8502-10002 |  | TQ FOR NATIVE FILES PDF FOR COMPANY SUPPLIED DOCUMENTS | PX - PROCESS | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A4 | 0 | NÃO SE APLICA | 07/04/2025 |  |  |  | 0 | 28/03/2025 | BNO-MABU-300-PX-8502-10002_A01.DOCX | 149,97 KB | 28/03/2025 03:07:01 | [11 empty] | IFI - ISSUED FOR INFORMATION
BNO-MABU-300-PX-8502-10003 |  | TQ FOR WATER INJECTION PUMPS DYNAMIC SIMULATION REPORT / MODEL DONE EARLY ENGINEERING | PX - PROCESS | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A4 | 0 | NÃO SE APLICA | 08/04/2025 |  |  |  | 0 | 22/04/2025 | BNO-MABU-300-PX-8502-10003_A01.DOCX | 147,76 KB | 08/04/2025 09:15:56 | [11 empty] | IFI - ISSUED FOR INFORMATION
BNO-MABU-300-PX-8502-10004 |  | REQUEST FOR EXISTING BONGA MAIN LINE LIST | PX - PROCESS | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A4 | 0 | NÃO SE APLICA | 10/04/2025 |  |  |  | 0 | 24/04/2025 | BNO-MABU-300-PX-8502-10004_A01.DOCX | 146,21 KB | 10/04/2025 06:19:16 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00064 | A01 | 04/10/2025 | N/A |  |  |  |  | BNO-MABU-DAE-2025-TN-10089 | 07/08/2025
BNO-MABU-300-PX-8502-10005 |  | PIG LAUNCHING / RECEIVING OPERATING PROCEDURE | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A0 | 0 | ENG_IFR CONSOLIDATION | 24/06/2025 |  | FLAVIAMORAES.FRM | ISSUED AS CODE 4 - MAJOR COMMENTS | 50 | 17/06/2025 | BNO-MABU-300-PX-8502-10005_R01.DOCX | 175,25 KB | 03/06/2025 04:03:49 |  | 03/06/2025 10:19:21 | R01 | IFR - ISSUED FOR REVIEW | 24/06/2025 04:06:27 | R01 | 4-MAJOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00176 | R01 | 06/03/2025 | BNO-MABU-SNEPCO-2025-INC-00260 | 06/03/2025 | BNO/EXT/MABU/00614 | 6/19/2025 | CODE 4 - MAJOR COMMENTS
BNO-MABU-300-PX-8502-10006 |  | LABORATORY REPORT FOR VAPOR PRESSURE OF THE CORROSION INHIBITOR CORRTREAT DF 16946 | PX - PROCESS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.23-PX-PROCESS | A0 | 0 | ENG_IFR CONSOLIDATION | 21/06/2025 |  | FLAVIAMORAES.FRM | NOT ISSUED | 50 | 17/06/2025 | BNO-MABU-300-PX-8502-10006_R01.DOCX | 173,84 KB | 03/06/2025 04:04:23 |  | 03/06/2025 10:19:21 | R01 | IFR - ISSUED FOR REVIEW | [7 empty] | IFR - ISSUED FOR REVIEW |  |  |  | BON-DAE-WESTPAQ-2025-TX-00176 | R01 | 06/03/2025 | BNO-MABU-SNEPCO-2025-INC-00260 | 06/03/2025 | BNO/EXT/MABU/00620 | 06/20/2025
BNO-MABU-300-QA-5733-10001 | BNO-MABU-300-QA-5733-10001 |  | QA - QUALITY | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.24-QA-QUALITY | A0 | 0 | NÃO SE APLICA |  |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 0 |  | BNO-MABU-300-QA-5733-10001 _R01.DOCX | 1,35 MB | 05/06/2025 06:09:12 |  |  |  |  | 24/06/2025 05:45:17 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | [8 empty] | BNO/EXT/MABU/00634 | 6/24/2025 | CODE 3 - MINOR COMMENTS
BNO-MABU-300-QA-5733-10002 |  |  | QA - QUALITY | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.24-QA-QUALITY | A0 | 0 | NÃO SE APLICA |  |  |  | ISSUED AS CODE 3 - MINOR COMMENTS | 0 |  | BNO-MABU-300-QA-5733-10002_R01.DOCX | 1,34 MB | 05/06/2025 06:14:51 |  |  |  |  | 24/06/2025 05:45:19 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFR - ISSUED FOR REVIEW | [8 empty] | BNO/EXT/MABU/00634 | 6/24/2025 | CODE 3 - MINOR COMMENTS
BNO-MABU-300-QA-5798-10001 |  | QUALITY PLAN | QA - QUALITY | A02 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.24-QA-QUALITY | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 18/07/2025 |  | THEODORE_EBUNOHA |  | 50 | 01/08/2025 | BNO-MABU-300-QA-5798-10001_A02.DOCX | 1,29 MB | 18/07/2025 03:53:11 |  | 11/04/2025 09:47:14 | R01 | IFR - ISSUED FOR REVIEW | 07/05/2025 06:26:29 | R01 | 3-MINOR COMMENTS |  |  |  |  | AFC/AFU - APPROVED |  |  |  | BON-DAE-WESTPAQ-2025-TX-00380 | A02 | 07/18/2025 | BNO/MABU-SNEPCO-2025-INC-00414 | 07/18/2025 | BNO/EXT/MABU/00651 | 07/03/2025 | CODE 3 - MINOR COMMENTS |  |  | NR | NA
BNO-MABU-300-RA-3375-10001 |  | TOPSIDES PAINTING AND COATING SPECIFICATION | RA - MATERIALS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.25-RA-MATERIALS | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 23/07/2025 |  | PAULO.RAMALHO |  | 50 | 06/08/2025 | BNO-MABU-300-RA-3375-10001_A01.DOCX | 914,47 KB | 23/07/2025 16:08:19 |  | 22/05/2025 06:53:30 | R01 | IFR - ISSUED FOR REVIEW | 03/06/2025 10:20:08 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 4/17/2025 | 6/19/2025 | 07/10/2025 | BON-DAE-WESTPAQ-2025-TX-00403 | A01 | 07/23/2025 | BNO-MABU-SNEPCO-2025-INC-00443 | 07/23/2025 | [5 empty] | R | P2
BNO-MABU-300-RA-3375-10002 |  | SPECIFICATIONS AND PROCEDURES FOR TOPSIDES WELDING | RA - MATERIALS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.25-RA-MATERIALS | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 22/06/2025 |  | PAULO.RAMALHO,ANDREA.SANTOS |  | 50 | 04/07/2025 | BNO-MABU-300-RA-3375-10002_R01.DOCX | 924,6 KB | 22/06/2025 00:48:32 | [11 empty] | IFR - ISSUED FOR REVIEW | 07/04/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00238 | R01 | 06/22/2025 | BNO-MABU-SNEPCO-2025-INC-00316 | 06/22/2025 | BNO/EXT/MABU/00688 (OVERDUE RECEIVED FROM CPY ON 25-07-25 AND SHARED SAME DATE. | 07/25/2025 | CODE 3 - MINOR COMMENTS |  |  | R | P2
BNO-MABU-300-RA-6919-10001 |  | CORROSION MANAGEMENT FRAMEWORK AND INSPECTION PLAN | RA - MATERIALS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.25-RA-MATERIALS | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 04/08/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 08/04/2025 | 9/15/2025 | 10/06/2025 | [10 empty] | R | P2
BNO-MABU-300-RA-7769-10001-001 |  | CORROSION MANAGEMENT DRAWINGS | RA - MATERIALS | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.25-RA-MATERIALS | A3 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 01/09/2025 | [14 empty] | IDC - INTERNAL COMMENTS | 09/01/2025 | 10/13/2025 | 11/03/2025 | [10 empty] | INFO | NA
BNO-MABU-300-RA-8241-10001 |  | MATERIALS SELECTION REPORT | RA - MATERIALS | A01 | 2 | BNO - BONGA NORTH | BNO / 02-DED / 02.25-RA-MATERIALS | A4 | 0 | ENG_IFR LEAD ASSIGNMENT | 19/07/2025 |  | PAULO.RAMALHO |  | 50 | 01/08/2025 | BNO-MABU-300-RA-8241-10001_A01.DOCX | 1,12 MB | 19/07/2025 03:47:32 |  | 22/05/2025 06:53:30 | R01 | IFR - ISSUED FOR REVIEW | 03/06/2025 10:20:10 | R01 | 3-MINOR COMMENTS |  |  |  |  | IFA - ISSUED FOR APPROVAL | 4/25/2025 | 6/27/2025 | 7/18/2025 | BON-DAE-WESTPAQ-2025-TX-00381 | A01 | 07/19/2025 | BNO-MABU-SNEPCO-2025-INC-00419 | 07/19/2025 | [5 empty] | R | P2
BNO-MABU-SULZER-2025-TQ-10001 |  | ENGR ANDREA SANTOS TO PROVIDE DETAILS | NÃO SE APLICA | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.001-TQR | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0
BNO-WESTPAQ-DAE-2025-LT-10008 |  | 3D MODEL PROGRESS | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | BNO-WESTPAQ-DAE-2025-LT-10008=A01.PDF | 238,88 KB | 18/05/2025 01:35:51 | [11 empty] | IFI - ISSUED FOR INFORMATION
BON-DAE-WESTPAQ-2025-LT-10006 |  | RE-REQUEST FOR ACCELERATION IN DED | NÃO SE APLICA | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 15/05/2025 | BON-DAE-WESTPAQ-2025-LT-10006_A01.PDF | 1,68 MB | 30/04/2025 04:01:56 | [11 empty] | IFI - ISSUED FOR INFORMATION
BON-DAE-WESTPAQ-2025-LT-10007 |  | RE-MOBILIZATION OF ADDITIONAL PERSONNEL | NÃO SE APLICA | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 23/05/2025 | BON-DAE-WESTPAQ-2025-LT-10007=A01.PDF | 1,91 MB | 12/05/2025 02:04:28 | [11 empty] | IFI - ISSUED FOR INFORMATION
BON-DAE-WESTPAQ-2025-LT-10008 |  | RE-PERFORMANCE AND PROGRESS REPORTING | NÃO SE APLICA | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A4 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 23/05/2025 | BON-DAE-WESTPAQ-2025-LT-10008=A01.PDF | 1,66 MB | 12/05/2025 02:05:25 | [11 empty] | IFI - ISSUED FOR INFORMATION
BON-DAE-WESTPAQ-2025-LT-10009 |  | RE-3D MODEL PERFORMANCE AND PROGRESS | NÃO SE APLICA | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 02/06/2025 | BON-DAE-WESTPAQ-2025-LT-10009=A01.PDF | 1,43 MB | 19/05/2025 09:02:34
BON-DAE-WESTPAQ-2025-LT-10010 |  | PIPING SPECIFICATION AND PIPE WALL THICKNESS CALCULATION | NÃO SE APLICA | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 02/06/2025 | BON-DAE-WESTPAQ-2025-LT-10010=A01.PDF | 1,44 MB | 19/05/2025 14:42:23
BONGA NORTH HAZOP P&IDS – MODIFICATIONS |  | BONGA NORTH HAZOP P&IDS – MODIFICATIONS | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 14/07/2025 | BONGA NORTH HAZOP P&IDS – MODIFICATIONS=A01.ZIP | 6,16 MB | 01/07/2025 16:20:21 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00277 | A01 | 06/30/2025
MILESTONE 5.1 |  | NOTIFICATION OF COMPLETION ENGINEERING REVIEWS - INTEGRATED DESIGN REVIEW, DETAILED DESIGN HAZOP(S) | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 24/07/2025 | MILESTONE 5.1=A01.PDF | 287,29 KB | 10/07/2025 15:56:27 | [15 empty] | BON-DAE-WESTPAQ-2025-TX-00343 | A01 | 07/10/2025
NOTIFICATION OF COMPLETION 4.3 |  | NOTIFICATION OF COMPLETION 4.3 - MECHANICAL DELIVERABLES CRITICAL FOR ENGINEERING REVIEWS AS IDENTIFIED | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/08/2025 | NOTIFICATION OF COMPLETION 4.3=A01.PDF | 282,53 KB | 23/07/2025 05:46:33 | [11 empty] | IFI - ISSUED FOR INFORMATION
NOTIFICATION OF COMPLETION 4.5 |  | NOTIFICATION OF COMPLETION 4.5 - STRUCTURAL DELIVERABLES CRITICAL FOR ENGINEERING REVIEWS AS IDENTIFIED | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/08/2025 | NOTIFICATION OF COMPLETION 4.5=A01.PDF | 220,32 KB | 23/07/2025 05:46:41 | [11 empty] | IFI - ISSUED FOR INFORMATION
NOTIFICATION OF COMPLETION 4.8 |  | NOTIFICATION OF COMPLETION 4.8 - TECHNICAL SAFETY DELIVERABLES CRITICAL FOR ENGINEERING REVIEWS AS IDENTIFIED | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 06/08/2025 | NOTIFICATION OF COMPLETION 4.8=A01.PDF | 221,64 KB | 23/07/2025 05:46:37 | [11 empty] | IFI - ISSUED FOR INFORMATION
NOTIFICATION OF COMPLETION_3.1 |  | NOTIFICATION OF COMPLETION DETAILED DESIGN PHILOSOPHIES, PROJECT DESIGN BASIS AND ISSUE IFR .DOCX | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 14/07/2025 | NOTIFICATION OF COMPLETION_3.1=A01.PDF | 288,07 KB | 01/07/2025 05:25:23 | [11 empty] | IFI - ISSUED FOR INFORMATION | 07/14/2025 |  |  | BON-DAE-WESTPAQ-2025-TX-00284 | A01 | 06/30/2025
NOTIFICATION OF COMPLETION_3.2 |  | NOTIFICATION OF COMPLETION PROCESS SIMULATIONS AND HMB.DOCX | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 14/07/2025 | NOTIFICATION OF COMPLETION_3.2=A01.PDF | 290,72 KB | 01/07/2025 05:26:45 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00284 | A01 | 06/30/2025
NOTIFICATION OF COMPLETION_4.2 |  | NOTIFICATION_OF_COMPLETION_PROCESS_DELIVERABLES_CRITICAL_FOR_ENGINEERING_REVIEWS_AS_IDENTIFIED_IN_MDR | AA - PROJECT MANAGEMENT | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 14/07/2025 | NOTIFICATION OF COMPLETION_4.2=A01.PDF | 303,1 KB | 01/07/2025 05:27:00 | [11 empty] | IFI - ISSUED FOR INFORMATION |  |  |  | BON-DAE-WESTPAQ-2025-TX-00284 | A01 | 06/30/2025
PPF-173 |  | SINGLE TENDER JUSTIFICATION FORM PPF-173_BONGA NORTH_SIL & ALARM RATIONALIZATION.DOC._A01 | NÃO SE APLICA | A01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 |  | PPF-173=A01.PDF | 266,89 KB | 20/06/2025 13:02:40
WPQ-DAE-DED-0001 |  | NOTIFICATION OF COMPLETION FOR ENGINEERING REVIEWS - BOWTIE AND HAZID_MILESTONE 4.1& 5.5 | AA - PROJECT MANAGEMENT | R01 | 1 | BNO - BONGA NORTH | BNO / 02-DED / 02.004-OTHER | A0 | 0 | NÃO SE APLICA |  |  |  |  | 0 | 16/05/2025 | WPQ-DAE-DED-0001_R01.PDF | 725,01 KB | 04/05/2025 07:45:42 | [11 empty] | IFI - ISSUED FOR INFORMATION